## Slide 1
SCENARIO 1 – No Public Consultation
Task | Milestone
23 Oct | Conclusion of Dublin meeting
26-2 Nov | WPs to hold calls to reflect conclusions of Dublin meeting and advance work
3 Nov | CCWG conference call to confirm Dublin conclusions
3-10 Nov | Drafting of report language
10 Nov | Report sections sent to CCWG for review & CCWG call for rapporteurs to walk through edits
10-17 Nov | CCWG to read sections and flag any concerns
17 Nov | CCWG call to sign off edits
18-19 Nov | Finalization of WS1 report
20 Nov | Chairs send to Chartering Organizations

## Slide 2
SCENARIO 2 - Public Consultation - PART 1
Date | Milestone
23 Oct | Conclusion of Dublin meeting
26-2 Nov | WPs to hold calls to reflect conclusions of Dublin meeting and advance work
3 Nov | CCWG conference call to confirm Dublin conclusions
3-10 Nov | Drafting of report language
10 Nov | Report sections sent to CCWG for review & CCWG call for rapporteurs to walk through edits
10-17 Nov | CCWG to read sections and flag any concerns
17 Nov | CCWG call to sign off edits
18-19 Nov | Finalization of WS1 report
20 Nov | Third draft proposal published for public comments
1 Jan | Close of public comment period
8 Jan | Staff analysis of public comment

## Slide 3
SCENARIO 2 - Public Consultation - PART 2
Date | Milestone
8-19 Jan | WP calls to analyze comments and tease out recommendations
19 Jan | CCWG call for WPs to report conclusions of comment analysis. Pre-identify areas for further refinement.
21 Jan | CCWG call to confirm areas for refinement
21-26 Jan | WPs to refine language
26 Jan | Report sections sent to CCWG for review & CCWG call for rapporteurs to walk through edits
26-29 Jan | CCWG to read sections and flag any concerns
29 Jan | CCWG call to sign off edits
30-31 | CCWG Finalization of WS1 report
1 Feb | Chairs send to Chartering Organizations

## Slide 4
SCENARIO 3 - Public Consultation & Expedited Analysis) - PART 1
Date | Milestone
23 Oct | Conclusion of Dublin meeting
26-2 Nov | WPs to hold calls to reflect conclusions of Dublin meeting and advance work
3 Nov | CCWG conference call to confirm Dublin conclusions
3-10 Nov | Drafting of report language
10 Nov | Report sections sent to CCWG for review & CCWG call for rapporteurs to walk through edits
10-17 Nov | CCWG to read sections and flag any concerns
17 Nov | CCWG call to sign off edits
18-19 Nov | Finalization of WS1 report
20 Nov | Third draft proposal published for public comments
1 Jan | Close of public comment period
6 Jan | Staff analysis of public comment

## Slide 5
SCENARIO 3 - Public Consultation & Expedited Analysis) - PART 1
Date | Milestone
6-12 Jan | WP call to analyze comments and tease out recommendations
14 Jan | CCWG call for WPs to report conclusions of comment analysis
14-19 Jan | WPs to refine language
19 Jan | Report sections sent to CCWG for review & CCWG call for rapporteurs to walk through edits
19-22 Jan | CCWG to read sections and flag any concerns
22 Jan | CCWG call to sign off edits
23-24 Jan | CCWG Finalization of WS1 report
25 Jan | Chairs send to Chartering Organizations