JULY – Drafting

| DATE | TASK | COMMENTS |
| --- | --- | --- |
| 19 | XPlane finalize graphics |  |
| 21 | - ICG - CCWG Coordination (09:00 -10:00 UTC) - WP2 (13:00 UTC) - CCWG ACCT (19:00 UTC) |  |
| 22 | - STWP (11:00 UTC) - WP1 (19:00 UTC) |  |
| 23 | - CCWG ACCT (12:00 UTC) |  |
| 27 | - WP2 (13:00 UTC) - WP1 (19:00 UTC) |  |
| 28 | - CCWG ACCT (12:00 UTC) - WP1 (19:00 UTC) - Document freeze for 2nd draft publication (midnight UTC) | This allows time for translations, formatting and proof reading. |
| 28-31 | Document Freeze & Formatting | Need to publish Public Comment tool before publication of 2nd draft. |
| 31 | Launch of 40 Day Public Comment Period |  |

* NOTE: Aim to publish Public Comment tool by 22 July, but no later than 28 July.

AUGUST – Engagement

| DATE | TASK | COMMENTS |
| --- | --- | --- |
| 1-3 | Tentative Call with Advisors | Staff to suggest engagement plan for consideration. |
| 3-7 | Two (2) Outreach Webinars | To accommodate different timezones. Need schedule based on availability. |
| 17-21 | Briefing Call with Larry Strickling focused on answering his questions | Identify most suitable date – after advisors briefing. |
| 17-21 | Briefing Call with Board | Identify most suitable date – after advisors briefing. |
| 17-21 | Tentative Call with Advisors | To take place after the Board Call. |

SEPTEMBER – Review & Finalization

| DATE | TASK | COMMENTS |
| --- | --- | --- |
| 9 | Close of 40 Day Comment Period |  |
| 12 | Produce 1st Public Comment Tool for Review |  |
| 30 | End Review/Publication of Public Comment | Will need to devise a plan: staff to propose. |

OCTOBER – Submission to Chartering Organizations

| DATE | TASK | COMMENTS |
| --- | --- | --- |
| 9 | Submit Final Report to Chartering Orgs |  |
| 12-21 | SO/AC Approval Period |  |
| 18-22 | ICANN54 |  |
| 22 | Submission to the ICANN Board |  |