## Slide 1
USG Stewardship Project Costs
Meeting with BFC, CCWG/CWG co-chairs | 28 January 2016

## Slide 2: Purpose of the Call
The Board Finance Committee (BFC) is seeking help and collaboration from the CCWG and CWG co-chairs on how to address key concerns regarding the escalating costs of the USG IANA Stewardship Transition and Accountability WS1 work (THE PROJECT).
The purpose of today’s call is not to make decisions, but to get a common understanding of the issues, get everyone’s input and ideas, so that next week we can present to this group some concrete proposals.
Notes: This is a simpler agenda slide, the outline for your presentation.

## Slide 3: Summary of THE PROJECT costs [1 of 2]
FY15: the cost of THE PROJECT was US$ 8.7m
FY16: a budget of US$ 7m was approved to cover the cost of (a) THE PROJECT and (b) two other phases of work: Implementation and Bylaws Drafting. The FY16 budget was used up be end of November 2015 (i.e. during the first 5 months of the Financial Year)
The CFO has informed the BFC that an additional US$ 9m is projected for the remainder of FY16 in order to: (a) complete THE PROJECT in February 2016 with the delivery of the Final Proposal, and (b) undertake the two other phases of work: Implementation and Bylaws Drafting. The cost of Accountability WS2 will be the subject of a further budget request.
The total cost in FY15 and FY16 is estimated to reach US$ 25m by end of June 2016 (of which USD 11.5 m is for external legal costs).
Notes: This is a simpler agenda slide, the outline for your presentation.

## Slide 4: Summary of THE PROJECT costs [2 of 2]
Financials
In million |  | FY15 Actuals | FY16 Forecast Full year | 2-year Total
 |  | (1) | (2) | (3)=(1)+(2)
Total spend |  | 8.7 | 15 to 16 | 24 to 25
External Legal costs |  | 4.0 | 7.0-7.5 | 11-11.5
Other professional services* |  | 0.6 | 2.4 | 3.0
Staff support |  | 1.1 | 2.4 | 3.5
Travel/Meetings** |  | 0.7 | 1.6 | 2.3
Language Services |  | 1.5 | 1.4-1.9 | 3.0-3.5
Admin |  | 0.2 | 0.3 | 0.5
*: includes education/engagement, government affairs, support (graphics/secretariat), other.
**: includes approximately $0.1m for the 1-day CCWG meeting in Marrakech during ICANN 55.
Notes: Do nothing

## Slide 5: Issues to Address
The US$ 7m budget in FY16 was used up by end November 2015.
The bills for December 2015 and January 2016 will need to be paid soon. However, the ICANN CFO does not have an approved revised FY16 budget from which to fund these bills.
Therefore the BFC must recommend a revised budget to the Board for approval. Before making a recommendation to the Board, the BFC must complete its due diligence and develop answers to the following five questions:
  Is the additional expenditure of US$ 9m from December 2015 to June 2016 reasonably estimated?
  Who is accountable?
  What new control mechanisms are in place to ensure that the approved additional expenditure is not exceeded?
  How will the additional expenditure be funded?
  How will WS2 work and budget be estimate? How will it be managed?
Notes: This is a simpler agenda slide, the outline for your presentation.

## Slide 6: Question 1: Is the additional expenditure of US$9m for THE PROJECT from December 2015 to June 2016 reasonably estimated?
FY16 USG Stewardship Transition – Expenses
  See slide 7
FY16 USG Transition – Legal Costs
  See slide 8
Notes: This is a simpler agenda slide, the outline for your presentation.

## Slide 7: FY16 USG Stewardship Transition - Expenses
Financials
In million |  | FY16 Actuals Jul-Dec (6 mos) | FY16 Forecast Jan-Jun (6 mos) | FY16 Forecast Full year (12 mos) |  | FY16 Budget Envelope | Var. Fcst Vs Budget
 |  | (1) | (2) | (3)=(1)+(2) |  | (4) | (3)-(4)
Total spend |  | 8.6 | 6.5 to 7.5 | 15 to 16 |  | 7 | 8 to 9
External Legal costs |  | 4.4 | 2.6-3.1 | 7.0-7.5 |  | 0.5 | 6.5-7.0
Other professional services* |  | 1.3 | 1.1 | 2.4 |  | 2.4 | -
Staff support |  | 1.2 | 1.2 | 2.4 |  | 2.4 | -
Travel/Meetings** |  | 0.7 | 0.9 | 1.6 |  | 1.3 | 0.3
Language Services |  | 0.9 | 0.5-1.0 | 1.4-1.9 |  | 0.3 | 1.1-1.6
Admin |  | 0.1 | 0.2 | 0.3 |  | 0.0 | 0.3
*: includes education/engagement, government affairs, support (graphics/secretariat), other.
**: includes approximately $0.1m for the 1-day CCWG meeting in Marrakech during ICANN 55.
Notes: Do nothing

## Slide 8: FY16 USG Stewardship Transition – Legal costs
Financials
In million |  | FY16 Actuals Jul-Nov (6 mos) | FY16 Forecast Dec-Jun (6 mos) | FY16 Forecast Full year (12 mos) |  | FY16 Budget Envelope | Var. Fcst Vs Budget
 |  | (1) | (2) | (3)=(1)+(2) |  | (4) | (3)-(4)
External Legal costs |  | 4.4 | 2.6-3.1 | 7.0-7.5 |  | 0.5 | 6.5-7.0
By Client group: |  |  |  |  |  |  | 
CCWG |  | 4.1 | 1.8-2.3 | 5.9-6.4 |  | n/a | n/a
CWG |  | 0.3 | 0.8 | 1.1 |  | n/a | n/a
By legal firm (low end): |  |  |  |  |  |  | 
Sidley Austin |  | 1.7 | 0.8 | 2.5 |  | - | 2.5
Adler Colvin |  | 1.7 | 0.6 | 2.3 |  | - | 2.3
Jones Day |  | 1.0 | 1.2 | 2.2 |  | 0.5 | 1.7
Notes: Do nothing

## Slide 9: Question 2: Who is accountable?
Board & Officers Responsibilities:
The Board and the Officers have the fiduciary responsibility of ensuring that adequate financial controls are in place for THE PROJECT and that ICANN's financial stability is maintained at all times.
CCWG + CWG co-chairs Responsibilities:
The CCWG and CWG co-chairs are the managers of THE PROJECT. They have the responsibility for planning and scoping the work, directing external lawyers, consultants and staff, and deciding on the frequency of meetings and travel. Accordingly, they are accountable for the overall cost of THE PROJECT.
 Unless we have clarity on this, costs will not be controlled
Notes: This is a simpler agenda slide, the outline for your presentation.

## Slide 10: Question 3: What Control Mechanisms?
Although there have been some controls in place, these controls are not sufficient and effective for the purpose of managing the costs against the budget for a project of that magnitude.
As a result, the budget allocated to THE PROJECT has been overrun by a substantial amount.
For the remainder of FY16 (i.e. until end June 2016), therefore, new additional control mechanisms should be introduced to ensure that any approved additional expenditure is no exceeded.
Notes: This is a simpler agenda slide, the outline for your presentation.

## Slide 11: Question 3: Suggested New Control Mechanisms
Project Management Office (PMO): the co-chairs of the CCWG + CWG, the CEO, the CFO, one or two BFC reps.
  PMO will be responsible for developing a plan of activities, budget and timescales by activities.
  PMO meet monthly to review a project financial status report produced by the CFO.
  PMO will ensure no cost overrun until the end June 2016.
Approve the additional new expenditure in Tranches. The drawdown of each Tranche will require the approval of the PMO.
Exercise more control on the cost incurred by External Legal Advisors. Ask for proposals, hourly rates, estimates of work, timely invoices, etc.
Consider an annual cap on external legal cost for the remainder of FY16
Set deadlines for receiving input from the chartering organizations and explain that delays are costly.
Keep the community informed and publish minutes of the PMO meetings.
Notes: This is a simpler agenda slide, the outline for your presentation.

## Slide 12: Question 4: How will the additional expenditure be funded?
The Reserve Fund is the only readily available source for funding this additional new expenditure.
The Reserve Fund, however, has already been seriously depleted
  by end of June 2016, level will be US$60m
  This represents only 6-8 months of operating expenses instead of the historically set target of 12 months
  Further withdrawal from the Reserve Fund could jeopardize ICANN’s financial stability.
The replenishment of the Reserve Fund is unlikely to come from the ongoing ICANN Operations, which are not structured to generate an annual surplus.
The Board should initiate a community discussion on how the Reserve Fund will be replenished.
Notes: This is a simpler agenda slide, the outline for your presentation.

## Slide 13: Question 5: How WS2 work will be estimated and managed?
The BFC would like to request the CCWG to prepare a comprehensive cost proposal ( including external legal costs, travel, meetings, staff support, etc.) shortly after the CCWG face to face meeting in Marrakech where the scope of WS2 will be defined.
A cap on external legal costs should be considered.
In order to contain costs, the BFC recommends no further F2F meetings for WS2 after Marrakech.
A review of the estimates should be undertaken jointly between the CCWG, the CFO and the BFC.
The final estimates together with proposed financial control mechanisms should be approved by the Board before work on WS2 commences.
Notes: This is a simpler agenda slide, the outline for your presentation.