## Intro
WP1 Work Status Chart
Work Party 1: Community Empowerment / “Non-Triggered”
This document brings together information about the progress of WP1’s work on the specific powers and mechanisms developed in the “Scope, Powers and Mechanisms” paper [1] and harmonises these with the work item identifiers & list of volunteers developed in the “Work Plan and Work Methods” paper[2]. There are three tables: for powers, for mechanisms, and a third for work items assigned by WP2 to WP1 for further development.
[1] See document at https://docs.google.com/document/d/1-17DuxWJJuUk6QAelcz7X4L3KiyQ2XcEqapHVj9ir38/edit?usp=sharing
[2] See document at https://docs.google.com/document/d/1C7eMTu0k8KOTiRlhlt8vqAGwYc4vbl1EiiVGW6vuVXk/edit?usp=sharing
WP2 Work Status Chart
Work Party 2: Review and Redress
This document brings together information about the progress of WP2’s work on review and redress mechanisims.
WPST Work Status Chart
Work Party ST: Stress Tests
This document brings together information about the progress of WPST’s work on stress tests of the WP1 & WP2 mechanisims.

## WP1
WP1 Work Status Chart
Label | T / NT | WS | Title | Volunteer/s | Seen CCWG? | Target Date | Status | Comments / Pending Issues
(see Scope Powers Mechs for description)
Table 1: WP1 Powers
These were called “Powers” in our initial Scope Powers and Mechanisms paper.
WP1-1A | NT | 1 | Community approves Bylaws Change | Roelof | Y | 2015-03-20 | CCWG Hearing 1 | For Signoff WP1 #4
WP1-1B | NT | 1 | Community challenges actions against Bylaws | Roelof | Y | 2015-03-20 | CCWG Hearing 1 | For Signoff WP1 #4
WP1-1C | NT | 1 | Community approves Budget/Strat Plan | Roelof | Y | 2015-03-20 | CCWG Hearing 1 | For Signoff WP1 #4
WP1-2A | NT | 1 | AOC merged in to Bylaws | Steve, Matthew, Fiona, Kavouss | Y | 2015-03-20 | CCWG Hearing 1 | For Signoff WP1 #4; Draft reviewed WP1 18 March 2015
WP1-2B | NT | 2 | Community adds/sunsets AOC Reviews | Steve, Matthew, Fiona, Kavouss |  | 2015-03-20 | Draft | For Signoff WP1 #4
WP1-2C | NT | 2 | Community approves AOC Review Team members | Steve, Matthew, Fiona, Kavouss |  | 2015-03-20 | Draft | For Signoff WP1 #4
WP1-2D | NT | TBD | Community requires AOC Recommendation implementation | Matthew, Fiona |  | 2015-03-20 | Draft | For discussion WP1 #4
WP1-2E | NT | TBD | AOC review teams have access to all ICANN internal documents | Steve, Matthew, Fiona |  | 2015-03-20 | Draft | Discussed at WP1 #4; Discussed WP1 18 March 2015
WP1-3A | NT | 1 | Community can require implementation of all Accountability WG Work Stream 2 accountability improvements | Steve |  | 2015-03-20 | Draft | Discussed WP1 18 March 2015
WP1-4A | NT | TBD | Defining GAC Consensus for ICANN Board purposes | Jordan | Y | 2015-03-20 | On-Hold | On hold - Draft started; awaiting GAC feedback
WP1-5B-1 | NT | 1 | Prevent ICANN Imposing Obligations – Accountability Contract | Keith |  | 2015-03-20 | Draft | Discussed WP1 18 March 2015
WP1-5B-2 | NT | 1 | Prevent ICANN Imposing Obligations – Golden Bylaw | Keith, Kavouss |  | 2015-03-20 | Draft | Discussed WP1 18 March 2015
WP1-6A | NT | 2 | Community appoints ICANN Ombudsman | TBD |  | 2015-03-20 | On-Hold | Develop as part of WS2
WP1-6B | NT | 2 | NomCom appoints ICANN Ombudsman | TBD |  | 2015-03-20 | On-Hold | Develop as part of WS2
WP1-7A | NT | 1 | Community can remove ICANN Director/s | Jordan | Y | 2015-03-20 | Draft | CCWG to discuss who has standing to remove directors; v2.0 ciculated on 11 March; Discussed WP1 18 March 2015
Table 1A: WP1 Powers Transferred to WP2
These were called “Mechanisms” in our initial Scope Powers and Mechanisms paper.
Label | T / NT | WS | Title | Volunteer/s | Seen CCWG? | Target Date | Status | Comments / Pending Issues
(see Scope Powers Mechs for description)
WP1-5A | T |  | Clarify ICANN’s limited technical mission | Keith, Matthew |  |  | Transfer to WP2 | To WP2
WP1-6C | T | 2 | Ombudsman has standing for Independent Review Panel |  |  |  | Transfer to WP2 | Develop as part of WS2. To WP2
Table 2: WP1 Mechanisms
These were called “Mechanisms” in our initial Scope Powers and Mechanisms paper.
Label | T / NT | WS | Title | Volunteer/s | Seen CCWG? | Target Date | Status | Comments / Pending Issues
(see Scope Powers Mechs for description)
WP1-A | TBD | TBD | Existing SO/AC structures | TBD |  | 2015-03-20 | Draft
WP1-B | TBD | TBD | Permanent CCWG | Jordan |  | 2015-03-20 | Draft | Discussed on 18 Mar WP1 Call
WP1-C | TBD | TBD | Statutory Delegates | Roelof, Edward |  | 2015-03-20 | Draft | Discussed on 18 Mar WP1 Call
WP1-D | TBD | TBD | Statutory Members | Roelof, Edward |  | 2015-03-20 | Draft | Discussed on 18 Mar WP1 Call
WP1-E | TBD | TBD | Supervisory Board | Roelof |  | 2015-03-20 | Draft | Discussed at WP mtg #2
WP1-F | T | TBD | Community Veto | Robin |  | 2015-03-20 | Draft | Robin sent to WP1 list on 11 March and briefly reviewed on WP1 meeting
WP1-7G | NT | 1 | Community Council Mechanisim | Jordan |  | 2015-03-20 | Draft | Discussed WP1 18 March 2015
Table 3: Assigned to WP1 from WP2
This table is to record work items for WP1 that have been assigned to it by WP2 (i.e. they were initially within WP2’s “Review and Redress” focus but with the change to “triggered” v “non-triggered”, are now the domain of WP1).
Label | T / NT | WS | Title | Volunteer/s | Seen CCWG? | Target Date | Status | Comments / Pending Issues
(see Scope Powers Mechs for description)
WP2-11 | N/A | 1 | Changes to Bylaws and Articles of Incorporation | TBD | No | N/A | Transfer to WP1 | Absorbed into WP1-1A
WP2-12 | N/A | 1 | Permanent cross-community working group | TBD | No | N/A | Transfer to WP1 | Absorbed into WP1-B
WP2-13 | N/A | 1 | Recall mechanism for any board member | TBD | No | N/A | Transfer to WP1
WP2-14 | N/A | 1 | Community Veto | TBD | No | N/A | Transfer to WP1 | Moved to WP1-F

## WP2
WP2 Work Status Chart
Label | T / NT | WS | Title | Volunteer/s | Seen CCWG? | Target Date | Status | Comments / Pending Issues
Table 1: WP2
WP2-1 |  | 1 | Compact with Community | Robin Gross, Paul Rosenzweig, David Post, David Maher, Alain Bidron | No | 2015-03-20 | Discussed | This document will be submitted by 20 March 2015 for detailed discussion and refinement in Istanbul
WP2-2 |  | 1 | Office of an Ombudsman | Chris LaHatte, Robin Gross, Edward Morris | No | 2015-03-20 | Discussed | Discussions still preliminary, will be explored in detail in Istanbul pre-meeting F2F
WP2-3 |  | 1 | Request for Reconsideration | Chris LaHatte, David McAuley, Robin Gross, Carlos Gutierrez | No | 2015-03-20 | Discussed | Discussions still preliminary, will be explored in detail in Istanbul pre-meeting F2F
WP2-4 |  | 1 | Independent Review | Paul Rosenzweig, David McAuley, Jonathan Zuck, Robin Gross, Chris LaHatte, David Post, Greg Shatan, David Maher | No | 2015-03-20 | Discussed | We expect to have an outline for discussion in Istanbul
Table 2: WP2 Mechanisms
Label | T / NT | WS | Title | Volunteer/s | Seen CCWG? | Target Date | Status | Comments / Pending Issues
WP2-10 |  | 1 | Standards | Robin Gross, Paul Rosenzweig | No | 2015-03-20 | Discussed | This work has been combined with the Mission/Compact work
WP2-11 |  | 1 | Changes to Bylaws and Articles of Incorporation | TBD | No |  | Transfer to WP1
WP2-12 |  | 1 | Permanent cross-community working group | TBD | No |  | Transfer to WP1
WP2-13 |  | 1 | Recall mechanism for any board member | TBD | No |  | Transfer to WP1
WP2-14 |  | 1 | Community Veto | TBD | No |  | Transfer to WP1
Table 3: Assigned to WP2 from WP1
This table is to record work items for WP2 that have been assigned to it by WP1 (i.e. they were initially within WP1’s “triggered” v “non-triggered” focus but with the change to “Review and Redress”, are now the domain of WP2).
Label | T / NT | WS | Title | Volunteer/s | Seen CCWG? | Target Date | Status | Comments
WP1-5A | T |  | Clarify ICANN’s limited technical mission | Matthew Shears |  | 2015-03-20 | Transfer to WP2 | To WP2; Keith ack that docs had been sent and Mathew will take on in WP2 at WP1 Call 11 March.
WP1-6C | T | 2 | Ombudsman has standing for Independent Review Panel |  |  | 2015-03-20 | Transfer to WP2 | Develop as part of WS2. To WP2

## WPST
WPST Work Status Chart
Label | T / NT | WS | Title | Volunteer/s | Seen CCWG? | Target Date | Status | Comments / Pending Issues
Table 1: WPST
WPST-1a | N/A | 1,2 | 5. Domain industry financial crisis. | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Helpful
WPST-1b | N/A | 1,2 | 6. General financial crisis. | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Helpful
WPST-1c | N/A | 1,2 | 7. Litigation arising from private contract, e.g., Breach of Contract. | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Helpful
WPST-1d | N/A | 1,2 | 8. Technology competing with DNS. | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Helpful
WPST-2 | N/A | 1,2 | 9. Major corruption or fraud. | Steve, Cheryl | No | 2015-03-20 | Draft | Helpful
WPST-3a | N/A | 1,2 | 1. Change authority for the Root Zone ceases to function, in part or in whole. | Steve, Cheryl | No | 2015-03-20 | Draft | Await CWG
WPST-3b | N/A | 1,2 | 2. Delegation authority for the Root Zone ceases to function, in part or in whole. | Steve, Cheryl | No | 2015-03-20 | Draft | Await CWG
WPST-4 | N/A | 1,2 | 11. Compromise of credentials. | Steve, Cheryl | No | 2015-03-20 | Draft | Helpful (to be complemented ?); Mathieu provided input on 18 March
WPST-5 | N/A | 1,2 | 17. ICANN attempts to add a new top-level domain in spite of security and stability concerns expressed by technical community or other stakeholder groups. | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Enhance community powers
WPST-6 | N/A | 1,2 | 21. A government telecom minister instructs ICANN to revoke and re-delegate a country-code top-level domain (ccTLD), despite objections from many current registrants and user communities in the country concerned. | Steve, Cheryl | No | 2015-03-20 | Draft | Await CWG; Eberhard to send updated draft for #21
WPST-7a | N/A | 1,2 | 3. Litigation arising from existing public policy, e.g., Anti-Trust | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Might still be inadequate; Reviewed in WPST meeting 18 March; 3&4 proposed to be split apart and filled out separately
WPST-7b | N/A | 1,2 | 4. New regulations or legislation. | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Might still be inadequate; Reviewed in WPST meeting 18 March; 3&4 proposed to be split apart and filled out separately
WPST-8 | N/A | 1,2 | 19. ICANN attempts to re-delegate a gTLD because the registry operator is determined to be in breach of its contract, but the registry operator challenges the action and obtains an injunction from a national court. | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Await CWG; Sam to update #19 Problem Statement; Reviewed in WPST meeting 18 March; dependency to CWG defined "counter-party"
WPST-9 | N/A | 1,2 | 20. A court order is issued to block ICANN’s delegation of a new TLD, because of complaint by existing TLD operators or other aggrieved parties. | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Might still be inadequate; Reviewed in WPST meeting 18 March;
WPST-10a | N/A | 1,2 | 10. Chairman, CEO or major officer acting in a manner inconsistent with the organization’s mission. | Steve, Cheryl | No | 2015-03-20 | Draft | Adequate in combination; Reviewed in WPST meeting 18 March;
WPST-10b | N/A | 1,2 | 24. An incoming Chief Executive institutes a “strategic review” that arrives at a new, extended mission for ICANN. The Board, having just hired the new CEO, approves the new mission and strategy without community consensus. | Steve, Cheryl | No | 2015-03-20 | Draft | Adequate in combination; Reviewed in WPST meeting 18 March;
WPST-11 | N/A | 1,2 | 12. Capture by one or several groups of stakeholders. | Steve, Cheryl | No | 2015-03-20 | Draft | Adequate; Reviewed in WPST meeting 18 March; will update for underlying communities that they have trasparent process to avoid capture as well.
WPST-12 | N/A | 1,2 | 13. One or several stakeholders excessively rely on accountability mechanism to “paralyze” ICANN. | Steve, Cheryl | No | 2015-03-20 | Draft | May need to adjust individuals vs community powers; Reviewed in WPST meeting 18 March;
WPST-13 | N/A | 1,2 | 16. ICANN engages in programs not necessary to achieve its limited technical mission. For example, uses fee revenue or reserve funds to expand its scope beyond its technical mission, giving grants for external causes. | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Adequate in combination; Reviewed in WPST meeting 18 March;
WPST-14 | N/A | 1,2 | 18. Governments in ICANN’s Government Advisory Committee (GAC) amend their operating procedures to change from consensus decisions to majority voting for advice to ICANN’s board. | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Adequate - but GAC engagement needed; Reviewed in WPST meeting 18 March;
WPST-15 | N/A | 1,2 | 22. ICANN Board fails to comply with bylaws and/or refuses to accept the decision of a redress mechanism constituted under the bylaws. | Steve, Cheryl | Yes | 2015-03-20 | CCWG Hearing 1 | Adequate in combination; Reviewed in WPST meeting 18 March; No additional input
WPST-16 | N/A | 1,2 | 23. ICANN uses RAA or other agreements to impose requirements on third parties, outside scope of ICANN mission. Affected third parties, not being contracted to ICANN, have no effective recourse against ICANN. Contracted parties, not being implicated by the requirements themselves, do not avail themselves of mechanisms allowing them to challenge ICANN’s decision. | Steve, Cheryl | No | 2015-03-20 | Draft | ; Reviewed in WPST meeting 18 March; clarify language around policy...PDP vs. Registration policies for example; any suggestion to leverage market power is serious issue, does not affect only ICANN, but all contracted parties
WPST-17 | N/A | 1,2 | 14. ICANN or NTIA choose to terminate the Affirmation of Commitments. (AoC) | Steve, Cheryl | No | 2015-03-20 | Draft | Adequate; Reviewed in WPST meeting 18 March;
WPST-18 | N/A | 1,2 | 15. ICANN terminates its legal presence in a nation where Internet users or domain registrants are seeking legal remedies for ICANN’s failure to enforce contracts, or other actions. | Steve, Cheryl | No | 2015-03-20 | Draft | Improve and may be adequate (debate on US jurisdiction); Reviewed in WPST meeting 18 March;
WPST-19 | N/A | 1,2 | 25. ICANN delegates or subcontracts its obligations under a future IANA agreement to a third party. Would also include ICANN merging with or allowing itself to be acquired by another organization. | Steve, Cheryl | No | 2015-03-20 | Draft | Await CWG; Reviewed in WPST meeting 18 March;

## Lists
Status Options | WP1 Volunteers | WP2 Volunteers | WPST Volunteers
Not Started | Adebunmi Akinbo | Alain Bidron | Steve DelBianco
On-Hold | Alice Munyua | Alice Munyua | Cheryl Langdon-Orr
Discussed | Athina Fragkouki | Athina Fragkouli | James Bladel
Draft | Beran Gillen | Bruce Tonkin | Samantha Eisner
CCWG Hearing 1 | Camino Manjon-Sierra | Camino Manjon-Sierra | Jonathan Zuck
CCWG Hearing 2 | Claudia Selli | Carlos Raul Gutierrez | Alan Greenberg
Complete | Desiree Miloshevic | Claudia Selli | Leon Sanchez
Transfer to WP1 | Edward Morris | Cristofer Granillo | Eberhard Lisse
Transfer to WP2 | Fiona Asonga | David McAuley | Mathieu Weill
| Finn Petersen | David Maher | Thomas Rickert
| Gary Campbell | David Post | Carlos Raul Gutierrez
| Greg Shatan | Desiree Miloshevic | Camino Manjon-Sierra
| Guru Acharya | Edward Morris | Adebunmi Akinbo
| Izumi Okutani | Erika Mann | Claudia Selli
| Jonathan Zuck | Finn Petersen | Rudi Daniel
| Jorge Cancio | Gary Campbell | Fiona Asonga
| Julia Wolman | Greg Shatan | Jordan Carter
| Kavouss Arasteh | Guru Acharya | Edward Morris
| Konstantinos Komaitis | Izumi Okutani | Olga Cavalli
| Leon Sanchez | Jon Nevett | Thomas Schneider
| Malcolm Hutty | Jonathan Zuck | Alice Munyua
| Mark Carvell | Jordan Carter | Rafael Perez Galindo
| Markus Kummer | Jorge Cancio | Mark Carvell
| Mathieu Weill | Julia Wolman | Suzanne Radell
| Matthew Shears | Kavouss Arasteh | Pär Brumark
| Maura Gambassi | Konstantinos Komaitis | Pedro Ivo Ferrz Da Silva
| Olga Cavalli | Lars Erik Forsberg | Julia Wolman
| Olivier Muron | Leon Sanchez | Finn Petersen
| Pär Brumark | Malcolm Hutty | Jorge Cancio
| Pedro Ivo Ferraz De Silva | Mark Carvell | Izumi Okutani
| Phil Corwin | Markus Kummer | Maura Gambassi
| Rafael Perez Galindo | Mathieu Weill
| Robin Gross | Maura Gambassi
| Roelof Meijer | Olga Cavalli
| Samantha Eisner | Pär Brumark
| Steve DelBianco | Paul Rosenzweig
| Suzanne Radell | Pedro Ivo Ferraz Da Silva
| Thomas Rickert | Phil Corwin
| Thomas Schneider | Rafael Perez Galindo
| Tijani Ben Jemaa | Robin Gross
| Vrikson Acosta-Velasquez | Stephanie Duchesneau
| Young-Eum Lee | Suzanne Radell
Thomas Rickert
Thomas Schneider