## contract breakdown
# for Reference purposes | Section from IANA Naming Functions Contract | Title | Contract Section Text | Notes from IFRT - Legal meeting, 25-Feb-2020. PENDING REVIEW AND NOT FINAL | Applicable Notes from Plenary Meetings | Questions for the CSC | Reference Material | Team Members Reviewing | Suggested Methods of Evaluation *please initial your comments | IFRT Request for Materials Required for Evaluation *please initial your comments | Findings/Notes *please initial your comments | Possible Outreach Questions *please initial your comments | Conclusion *please initial your comments | SCOPE
1 |  | Contract Opening | This IANA Naming Function Contract (this “Contract”) is dated as of 30 September 2016 and is entered into by and between Internet Corporation for Assigned Names and Numbers, a California nonprofit public benefit corporation (“ICANN”) and Public Technical Identifiers, a California nonprofit public benefit corporation (the “Contractor”), and is effective as of the last date on which all of the conditions set out in ARTICLE II have been satisfied (the “Effective Date”). ICANN and Contractor may each be referred to herein individually as a “Party” and collectively as the “Parties.” WHEREAS, on 14 March 2014, the U.S. National Telecommunications and Information Administration (“NTIA”) announced the transition of NTIA’s stewardship role of key Internet domain name functions to the global multi-stakeholder community (the “Transition”); WHEREAS, following the Transition, ICANN will continue to serve as the Internet Assigned Numbers Authority (“IANA”) functions operator; and WHEREAS, ICANN and Contractor desire to enter into this Contract pursuant to which Contractor will serve as the operator for the IANA naming function after the Transition. NOW, THEREFORE, for good and valuable consideration, the sufficiency of which is hereby acknowledged, the Parties agree as follows: | The Cross Community Working Group (CGW) developed principles behind the contract during the IANA Stewardship Transition. CWG examined history and contracts with Department of Commerce and NTIA to ensure same level of IANA Functions performance were made. This is only 1 contract of several contracts with IANA Functions oversite. Opening identifies who this contract applies too |  |  | Cross Community Work Group (CWG) at https://community.icann.org/display/gnsocwgdtstwrdshp/CWG+to+Develop+an+IANA+Stewardship+Transition+Proposal+on+Naming+Related+Functions NTIA's involvement in the Stewardship Transition here: https://www.icann.org/resources/pages/transition-2014-03-23-en All PTI contracts found here: https://pti.icann.org/agreements
2 | Article I, all sections | Definitions | See Contract for Definitions Section at: https://pti.icann.org/agreements | Standard Definition section: provides clarity and keeps contract short by establishing common language |  |  |  | N/A
3 | Article II | Conditions Precedent | Condition Precedent. This Contract shall be effective as of the last date on which the following conditions have been satisfied: (a) the agreement between ICANN and the United States Department of Commerce (“DOC”), effective as of 01 October 2012 (including any extension thereof) has terminated or expired and (b) ICANN has accepted the responsibility to coordinate and administer the services that were previously provided thereunder. |  |  |  |  | N/A
4 | Article III, all sections | Representations and Warranties | Section 3.1 ICANN’s Warranties. ICANN represents and warrants that (a) it has all necessary rights and powers to enter into and perform its obligations under this Contract; (b) the execution, delivery and performance of this Contract by ICANN has been duly authorized by all necessary corporate action and does not violate any applicable law to which ICANN is subject; and (c) the execution, delivery and performance of this Contract by ICANN do not (i) require a consent or approval under, or (ii) conflict with, result in any violation or breach of, constitute a default under, or accelerate any rights in favor of a third party under, any agreement between ICANN and a third party. Section 3.2 Contractor Warranties. Contractor represents and warrants that (a) it has all necessary rights and powers to enter into and perform its obligations under this Contract; (b) the execution, delivery and performance of this Contract by Contractor has been duly 5 authorized by all necessary corporate action and does not violate any applicable law to which Contractor is subject; and (c) the execution, delivery and performance of this Contract by Contractor do not (i) require a consent or approval under, or (ii) conflict with, result in any violation or breach of, constitute a default under, or accelerate of any rights in favor of a third party under, any agreement between Contractor and a third party. | Common to contracts. Each entity in the contract states they have the ability to enter into the contract and are warranting that they're going to perform the contract to the best of their ability and without violations |  |  |  | N/A
5 | Article IV, Section 4.1 | Services and Requirements | Section 4.1 Designation. ICANN hereby designates Contractor as the operator of the IANA Naming Function, and authorizes Contractor to perform, the IANA Naming Function in accordance with the terms of this Contract (including the SOW). Without limiting the foregoing, ICANN hereby grants to Contractor, and Contractor hereby accepts, a worldwide, royalty-free, fully-paid right and license to the IANA Intellectual Property to the fullest extent permitted to be licensed to Contractor under the terms of the License Contract (including the right to further sublicense to the extent permitted in the License Contract). ICANN hereby authorizes Contractor to utilize any other rights and sublicensable licenses held by ICANN to the extent necessary or useful to perform the IANA Naming Function in accordance with the terms of this Contract (including the SOW). Contractor hereby accepts such designation, rights and licenses and agrees to perform the IANA Naming Function in accordance with the terms of this Contract (including the SOW). | Each entity states expectations. ICANN tells PGI that they are the entity that will perform this work. ICANN Bylaws obligate ICANN to set an entity to perform IANA Functions; have a contract with this entity.
6 | Article IV, Section 4.2 | US Presence | · U.S. Presence. (a) Contractor shall be a wholly U.S. owned and operated corporation operating in one of the 50 states of the United States or District of Columbia; (ii) incorporated within the state of California, United States of America; and (iii) organized under the nonprofit public benefit corporation laws of the state of California. (b) Contractor shall perform the IANA Naming Function in the United States and possess and maintain, throughout the performance of this Contract, a physical address within the United States. Contractor must be able to demonstrate that all primary operations and systems will remain within the United States (including the District of Columbia). ICANN reserves the right to inspect the premises, systems, and processes of all security and operational components used for the performance of the IANA Naming Function. | PTI is required to maintain existence in the US; ICANN can inspect PTI’s offices.
7 | Article IV, Section 4.3 (a) | Scope of the IANA Naming Function | Management of the DNS Root Zone (“Root Zone Management”) in accordance with the Statement of Work attached as Annex A to this Contract (“SOW”) | 4.3 Lays out main responsibilities in the subsections. PTI cannot change what services they want to perform. PTI must work with ICANN if PTI desires changes. This issue has yet to happen. PTI is a contractor to ICANN, not a decision maker on their own in relation to IANA Functions. | In IANA SERVICES OVERVIEW by Kim Davies, (https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC) PTI's root zone management is discussed 40 minutes into recording. |  | ‘Amendment No. 1 to IANA Naming Function Contract’ as of 07 May 2019 deleted Section 2, subsections (c) through (g) of the Annex A (=SOW) and replaced while also moving the Service Level Agreements (SLAs) to https://pti.icann.org/iana-naming-function-services-service-level-agreements
8 | Article IV, Section 4.3 (b) | Scope of the IANA Naming Function | Management of the .INT top-level domain |  | In IANA SERVICES OVERVIEW by Kim Davies, (https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC) .int is discussed 1:07 minutes into recording. |  | https://www.iana.org/domains/int | Tomslin | [Tomslin]Reach out to current registrants with questions regarding PTI's performance | List of current registrants
9 | Article IV, Section 4.3 (c) | Scope of the IANA Naming Function | Maintenance of a repository of internationalized domain name tables and label generation rulesets |  | In IANA SERVICES OVERVIEW by Kim Davies, (https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC) IDN Tables are discussed 1:09 minutes into recording. |  | https://www.iana.org/domains/idn-tables | Tomslin | [Tomslin]Review the IDN repository and the procedures for the IDN Repository | None | [Tomslin]A repository of IDN names is being maintained. | None | [Tomslin]PTI maintains a repository of IDN names. The repository can be found at https://www.iana.org/domains/idn-tables
10 | Article IV, Section 4.3 (d) | Scope of the IANA Naming Function | Provision of other services and implementation of modifications in performance of the IANA Naming Function, in each case upon ICANN’s request and in conformance with applicable policies and procedures. |  | IFRT#7 [Kim Davies]: Example is the established procedure for making formal changes to SLAs, and this process has been utilized and well documented. | 1. Does the CSC believe there are processes to address each area where performance of the IANA Naming functions might require changes? ANSWER: Yes. 2. For modification processes that do exist (relevant to the CSC is the SLA change procedure) are you satisfied with the procedure? Has the procedure been invoked and was it successful? ANSWER: When it was determined that SLAs needed to be modified, it took a long time to create the SLA Change Procedure. We reported about the process on our CSC monthly report. Now that there is a procedure, making the SLA changes have commenced. | The CSC, ICANN & PTI utilized the SLA Amendment Process (https://www.icann.org/en/system/files/files/iana-naming-function-sla-amendment-process-28mar19-en.pdf) to make three sets of SLA changes: 1. Technical Check SLA changes implemented 01 July 2019 2. new LGR SLAs implemented 01 January 2020 3. currently pending are new/changes to ccTLD creation/transfer SLAs PTI FY21 - FY24 Strategic Plan webinar, Service Delivery is discussed 18min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Suzanne | [5 empty] | 18.3.d, 18.3.i
11 | Article IV, Section 4.4 | Performance of IANA Naming Function | Contractor shall respect the diversity of customers of the IANA Naming Function and shall provide service to its customers in conformance with prevailing technical norms, and in support of the global security, stability and resilience of the DNS. If a customer’s receipt of services is based on a contract between such customer and ICANN, Contractor shall continue to provide services to such customer notwithstanding any on-going or anticipated contractual disputes between ICANN and such customer. | How PTI should do their work: that their work is done in a stable and secure manner in accrodance with statement of work they are meeting; following policies developed thru ICANN's PDPs; PTI's performance obligation. Naming function service should be equal with Number function. And next, customers of any IANA function perfromed by PTI will all be treated equally. No customer is entitled for more or different treatment from PTI & ICANN. Diversity to be respected (ICANN concerns over diversity is self imposed) | IFRT#7 [Kim Davies]: Statistical, machine readable data is available, but no "open transaction data" since most transactions are confidential. Also, there are different SLAs for different customer groups. The SLAs track measurements across all th ereserve management functions (see SLA Dashboard at ) and this dat is available for machine readable download without PTI needing to disclose anything. Part of analysis could be PTI describing approach to working with customers and overall work process. If IFRT wants more data, submit a request to PTI and staff will determine how to respond. |  | The CSC Reports: https://www.icann.org/en/csc/reports recommend watching this webinar: PTI FY21 - FY24 Strategic Plan webinar https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Patrik | Look at the result of the CSC review, ensure the SLA's are met, compare with the scope (Article IV, Section 4.3(d)). Ask PTI for post mortem for N latest issues that did fall outside of the SLA, why that happened and what has changed to make things better next time. [Tomslin] Something we could also consider is, to understand why PTI has different SLAs for different groups of customers, and if there is fairness in that difference. |  |  |  |  | 18.3.a
12 | Article IV, Section 4.5 | Separation of Policy Development and Operational Roles | Contractor shall ensure that its staff performing the IANA Naming Function do not publicly initiate, advance or advocate any policy development related to the IANA Naming Function. Notwithstanding the foregoing, Contractor’s staff may (i) respond to requests for information requested by Interested and Affected Parties, and, at Contractor’s volition, provide objective information to such customers, in each case, to inform ongoing policy discussions, (ii) request guidance or clarification as necessary for the performance of the IANA Naming Function, and (iii) publish, contribute to or comment on any document related to ongoing policy discussions, provided that, in the case of clause (iii), the primary purpose of such publication, contribution or commentary is to supply relevant IANA Naming Function experience and insight. | This section reflects an issue of importance to the US government in 2012: clear separation between policy development and operational roles. The US was bidding for an entity to take on the IANA Functions and the customers of IANA function asked for this to be maintained in post transition work. The people who perform the Naming Function are not to be the same people setting the policies. The Naming function team is to inform policy making, but not involved in setting that policy. ICANN leaves policy development to community and recommendations go to ICANN Board, and Board directs ICANN to direct PTI to follow that policy. | IFRT #7: [Peter] One approach would require a great level of detail in research but needs some clarification as to intent of the section. [Amy can assist with pulling research but team needs to determine level of effort] [Kim] Naming policies must start in ccNSO or GNSO, so you can consult with these groups about PTI's role in policy. [Peter]: who sets policy for .int though? Asking ccNSO/GNSO is one input, but still could dive into archives (go through PDP related emails to see how PTI interacted with PDP team). We should document our decision about our determined evaluation method...... [Steve C] contract section is separating PTI's participation vs. PTI's attempt to control policy....ask ccNSO/GNSO if PTI had "appropriate" level of interaction with PDP teams. TEAM DECIDED: to go back to ccNSO/GNSO for opinion |  | only ccNSO and GNSO can make policies applicable to Naming Functions In a PTI Budget & Strategic Plan webinar, this is discussed at different points, but a community question specifically about this is asked at 41mins in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Peter: will speak to ccNSO J.C.: will speak to GNSO James can give support to J.C. | consultation with GNSO and ccNSO. Ask ccNSO/GNSO if PTI attempted to influence policy decision making...did they appropriately collaborate/respond to PDP team or try to change the policy outcome? |  |  |  |  | 18.3.b
13 | Article IV, Section 4.6 | User Instructions | Contractor shall, in collaboration with all Interested and Affected Parties, maintain user instructions for the IANA Naming Function, including technical requirements. Contractor shall post such instructions at iana.org (“IANA Website”). | How PTI is expected to interact and take on responsiblities for our stakeholders. Some items in this section came from the legacy contracts previously mentioned, but some were from the 2014 Framework of Interpretation and Delegation of ccTLDs. This work on ccTLs changed a lot of nomenclautre used, and changed how we view the different roles in the managment of ccTLDs. This carried over to the governing of PTI which needs to respect the work of the Framework of Interpretation Working Group (FOIWG). This section says PTI is responsible for followng current registration policies. PTI also must be prepared for transfering the IANA Functions to another entity if required of PTI to do so. | IFRT#7 [Kim]: carry over language from NTA contract. Very early discussions about whether PTI was allowed to publish documentation at all, so this section allows PTI to publish. See URLs under "reference material" [Christian]: is there access to a test system [Kim]: no user facing test system. Some documentation is not published if it is too technical and for PTI side [Christian]: not a tld manager, so how would I evaluate it? [Kim]: very little documention on how to operate the system...since system is fairly straight forward. The documentation provides overview of IANA functions, policies and procedures. Does direct user as to what documentation is required for submitting to system. [Fred - Kim] discuss that clear policy stated on website is same from post-transition with no updates reflecting new proposals |  | Framework of Interpretation and Delegation of ccTLDs (FOIWG): https://ccnso.icann.org/en/workinggroups/foiwg.htm Root Zone Management: User Instructions and Guides at https://www.iana.org/domains/root/help IANA SERVICES OVERVIEW by Kim Davies, SOC2 audit of processes is discussed at 13min in https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Fred [has access to PTI systems] | Fred has direct expience with PTI systems. Option: Kim can give system demonstration if requested. |  |  |  |  | 18.3.a
14 | Article IV, Section 4.7 | Responsibility and Respect for Stakeholders | Contractor shall apply the policies for the Root Zone Management component of the IANA Naming Function that have been defined, or after the date of this Contract are further defined, by (a) the Generic Names Supporting Organization (“GNSO”), as appropriate under ICANN’s Bylaws, (b) the Country Code Names Supporting Organization (“ccNSO”), as appropriate under ICANN’s Bylaws, and (c) RFC 1591: /Domain Name System Structure and Delegation/ (“RFC 1591”) as interpreted by the Framework of Interpretation of Current Policies and Guidelines Pertaining to the Delegation and Redelegation of Country-Code Top Level Domain Names, dated October 2014 (“FOI”). In addition to these policies, Contractor shall, where applicable, consult the 2005 Governmental Advisory Committee Principles and Guidelines for the Delegation and Administration of Country Code Top Level Domains (“GAC 2005 ccTLD Principles”). Contractor shall publish documentation pertaining to the implementation of these policies and principles on the IANA Website. | see above | IFRT#7: TEAM DECISION: Can be bundled with Article IV, Section 4.5: Separation of Policy Development and Operational Roles |  | www.iana.org/domains/root | Peter: will speak to ccNSO J.C.: will speak to GNSO James can give support | [5 empty] | 18.3.a
15 | Article IV, Section 4.8 all | Management of the .INT TLD | (a) Contractor shall operate the .INT TLD within the current registration policies for the .INT TLD. (b) Upon designation of a successor registry by ICANN, if any, Contractor shall cooperate with ICANN to facilitate the smooth transition of operation of the .INT TLD. Such cooperation shall, at a minimum, include timely transfer to the successor registry of the then-current top-level domain registration data. | PTI is responsible for followng current registration policies in managing .int. PTI also must be pepared for transfering the .int registry services to another entity if required of PTI to do so. | IFRT#7 [Kim]: about 200-210 delegations. Strict eligibility criterial, only for inter-governmental treaty organizations. Low churn, if we remove ineligible requests, we have a dozen requests a year. Low transaction rate. [Fred]: is it managed through a separate registry system or RCM or email.... [Kim]: manual...we do use ticketing system to capture request but no automation. We will not be building a portal for 12 applications a year. There is a manual formal process with business system steps. Automated testing though, same system testing root zone. Unsigned zone goes through an automated signing process and is published. [Patrik]: Peter can look at peter.int |  | https://www.iana.org/domains/int | Peter & James | Option: Kim can hold webinar on this topic if requested |  |  |  |  | 18.3.b
16 | Article IV, Section 4.9 (a) | General Manager; Key Personnel. | (a) Contractor shall provide trained, knowledgeable technical personnel according to the requirements of this Contract, including the following key personnel: a General Manager, a Director of Security and a Conflict of Interest Officer (“Key Personnel”). All Contractor personnel who interface with ICANN must have excellent oral and written communication skills. "Excellent oral and written communication skills" is defined as the capability to converse fluently, communicate effectively, and write intelligibly in the English language. (b) The Conflict of Interest Officer shall be responsible for ensuring the Contractor is in compliance with Contractor’s internal and external conflict of interest rules and procedures. (c) The General Manager of Contractor shall organize, plan, direct, staff, and coordinate the overall performance of the IANA Naming Function; manage contract and subcontract activities as the authorized interface with ICANN and ensure compliance with applicable rules and regulations. The General Manager of Contractor shall be responsible for the overall performance of Contractor under this Contract and shall meet and confer with ICANN (including the Customer Standing Committee (“CSC”) and IANA Function Review teams (“IFRT”), as such terms are used in ICANN’s Bylaws) regarding the status of specific Contractor activities and problems, issues, or conflicts requiring resolution. The General Manager of Contractor must possess the following skills: (i) demonstrated communication skills with all levels of management; (ii) capability to negotiate and make binding decisions for Contractor (subject to any requirements of Contractor’s Bylaws and the authority delegated to such person by the Contractor’s Board of Directors (“PTI Board”)); (iii) extensive experience and proven expertise in managing similar multi-task agreements of this type and complexity; (iv) extensive experience supervising personnel; and (v) a thorough understanding and knowledge of the principles and methodologies associated with operations management and contract management. (d) Contractor shall obtain the approval of ICANN, after consultation with the PTI Board, prior to making Key Personnel substitutions. Replacements for Key Personnel must possess qualifications reasonably equal to or exceeding the qualifications of the personnel being replaced, unless an exception is approved by ICANN. | Dept of Commerce contract had specific roles specified: CWG wanted those roles to carry over, like: Conflict of Interest Officer, etc. |  |  | IANA SERVICES OVERVIEW by Kim Davies: 18 minutes in discusses team https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Kaili | [5 empty] | 18.3.b
17 | Article IV, Section 4.10 all | Inspection Of All Deliverables And Reports Before Publication. | (a) Prior to publication or posting of reports and other deliverables anticipated under this Contract on a template that has not been previously approved by ICANN, Contractor shall obtain approval from ICANN for such template, which will not be unreasonably withheld. Any deficiencies identified by ICANN shall be corrected by Contractor and resubmitted to ICANN within 10 business days after Contractor’s receipt of notice of such deficiency. (b) ICANN reserves the right to inspect the premises, systems and processes of all security and operational components used for the performance of all the requirements and obligations set forth in this Contract. | ICANN can inspect PTI's deliverables. SLA between ICANN and PTI for back-and-forth decision making, so each responds to the other in a timely manner. ICANN has to abide by these rules too. | IFRT#7: [Fred] to Kim, can you provide a report regarding this? [Kim] not sure what a report would entail but we could make an assertion. Private communications between ICANN & PTI. Maybe we have a representative of ICANN & PTI attest this is being met. TEAM DECISION that attestation from PTI & ICANN would fulfill this |  |  | Tomslin | get Attestation from PTI/ICANN |  | [Tomslin] Request for attestation sent to ICANN and PTI |  |  | 18.3.b
18 | Article V | Performance |  | Notes to apply to all sections of Article V: Performance below. High level statements of how ICANN expects PTI to do their work. Keep in mind that there are other contracts between ICANN and PTI, the IANA Services Agreement is a broad contract that obligates ICANN to provide PTI with the resources necessary to comply with all contracts, such as the Naming Functions contract. These other contracts are out-of-scope, but if the IFRT finds deficiencies which you believe are linked to other contracts, you can write a recommendation requesting to review those contracts
19 | Article V, Section 5.1 all | Constructive Working Relationship | Contractor shall use commercially reasonable efforts to maintain a constructive working relationship with ICANN, the root zone maintainer and all Interested and Affected Parties to ensure quality and satisfactory performance of the IANA Naming Function. | see above | IFRT#7: [James] involve Becky as the PTI finance part of this |  |  | Tomslin & Fred | Attestation from Amy, Becky (Finance), Kim | [Tomslin] Request for attestation sent to PTI and ICANN |  |  |  | 18.3.b
20 | Article V, Section 5.2 (a) | Continuity of Operations | Either ICANN or the Contractor shall provide, at a minimum, redundant sites in at least two geographically dispersed sites within the United States as well as multiple resilient communication paths to customers to ensure continuation of the IANA Naming Function in the event of cyber or physical attacks, emergencies, or natural disasters. | see above |  |  | IANA SERVICES OVERVIEW by Kim Davies, Security among other Audits discussed at 13min in https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Tomslin & James | [5 empty] | 18.3.b
21 | Article V, Section 5.2 (b) | Continuity of Operations | Contractor shall collaborate with ICANN to develop and implement a Contingency and Continuity of Operations Plan (“CCOP”) for the IANA Naming Function. Contractor in collaboration with ICANN shall from time to time update and annually test the CCOP as necessary to maintain the security and stability of the IANA Naming Function. The CCOP shall include details on plans for continuation of the IANA Naming Function in the event of cyber or physical attacks, emergencies, or natural disasters. Contractor shall submit the CCOP to ICANN after each update and publish on the IANA Website a report documenting the outcomes of the CCOP tests within 90 calendar days of the annual test. | ICANN requires PTI to have a business continuity plan. |  |  | CCOP created in 2016. Latest version is 6.0 as of January 2017. This is not a public document. IANA SERVICES OVERVIEW by Kim Davies, Security among other Audits discussed at 13min in https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC PTI FY21 - FY24 Strategic Plan webinar, Security is discussed 14min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Tomslin & James |  | Request to PTI for CCOP |  |  |  | 18.3.b
22 | Article V, Section 5.3 all | Performance Exclusions | (a) Contractor is not authorized to perform the services performed by the root zone maintainer, as such services are contemplated by the RZMA, unless authorized by ICANN. (b) Contractor shall not make changes in the policies and procedures developed by the relevant entities associated with the performance of the IANA Naming Function. (c) The performance of the IANA Naming Function shall not be, in any manner, predicated upon or conditioned by Contractor on the existence or entry into any contract, agreement or negotiation between Contractor and any TLD registry operator or any other third party. Compliance with this Section must be consistent with the SOW. | There are certain areas where PTI is not to perform. The RZMA Agreement - provisions for ICANN to perform, and not for the IANA Functions Operator. This is saying, just because this contract references responsibilities from other contracts, it does not mean PTI is responsible for the scope of that referenced contract. Contractor cannot make changes to process/procedures on their own. | IFRT#7: [Fred] for Root Zone operator would we request attestation from Verisign ? or? [Kim]: section is here to preserve the status quo in the transition when there was a separation of funcitons. Shows that this is at discretion of ICANN and not PTI. [Peter] related to lines 14/15 with PTI not being allowed to engage in policy making. New ideas about distributing the root zone, but it's not PTI engaging in this, it is ICANN as the root zone operator responsible. Believes section could be reworded. [Fred]: Root zone ceremonies do signatures...controlled by Verisign. What are the technical interfaces between ICANN & Verisign? [Kim]: 2 technical interfaces: (1) EPP for exchanging the deltas between unsigned root zone additions and (2) KSR-SKR Exchange where Verisign transmists to PTI via an API unsigned ZSSK and PTI sends back signatures. There are operational systems for interface and interaction. RZMA is detailed regarding this which has clear separation of roles documented. [Fred]: does the current architecture of the systems fulfill part of this section. |  | PTI FY21 - FY24 Strategic Plan webinar, Trust is discussed 7min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Christian Dawson | item a: attestation from Verisign and would architecture of systems fulfilll this |  |  |  |  | 18.3.b
23 | Article VI | Transparency of Decision-Making |  | Notes apply to all of Section VI: Transparencey of Decision-Making below. Section about levels of information that PTI must make public for sake of their customers and to show transparencey in decision making.
24 | Article VI, Section 6.1 (a) | Transparency | To enhance consistency, predictability and integrity in Contractor’s decision-making related to the IANA Naming Function, Contractor shall: (a) Publish reports pursuant to ARTICLE VII of this Contract and Section 3 of the SOW. | see above |  |  | Article VII Reporting is: 1. The monthly audit report on the root zone file which is published according to the contract at: www.iana.org/performance/root-audit 2. The CSC reports which are published according to the contract at: https://www.iana.org/performance/csc-reports SOW Section 3 Reporting is: 1. Above mentioned CSC reports 2. The online "dashboard" maintained and updated at: https://sle-dashboard.iana.org/ 3. Annual Customer Survey which is published at: Annual Customer Surveys 2019: https://www.iana.org/reports/2019/customer-survey-20191210.pdf 2018: https://www.iana.org/reports/2018/customer-survey-20181206.pdf 2017: https://www.iana.org/reports/2018/customer-survey-20180118.pdf 2016: https://www.iana.org/reports/2017/customer-survey-20170111.pdf 2015: https://www.iana.org/reports/2015/customer-survey-20151115.pdf 2014: https://www.iana.org/reports/2014/customer-survey-20141217.pdf 2013: https://www.iana.org/reports/2013/customer-survey-20131210.pdf IANA SERVICES OVERVIEW by Kim Davies, Performance Reporting: 27min https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC PTI FY21 - FY24 Strategic Plan webinar, Trust is discussed 7min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Kristian Ørmen | KØ: I'm looking at all the reference material and the text in the contract |  | KØ: In the contract section 7,1 it states: The relevant policies under which the changes are made shall be noted within each monthly report. I don't see this noted in the reports. KØ: i find it odd that the dashboard is in Beta. For me Beta means that it's not ready |  |  | 18.3.d
25 | Article VI, Section 6.1 (b) | Transparency | Make public all decisions of the PTI Board relating to the IANA Naming Function, unless, upon the determination of the PTI Board, such decision (i) relates to confidential personnel matters, (ii) is covered by attorney-client privilege, work product doctrine or other recognized legal privilege, (iii) is subject to a legal obligation that Contractor maintain its confidentiality or otherwise would result in the disclosure of confidential information of Contractor’s customers, (iv) would disclose trade secrets, or (v) would present a material risk of negative impact to the security, stability or resiliency of the IANA Naming Function or the Internet. | see above |  |  | PTI Board actions are found here: https://pti.icann.org/pti-board-meetings PTI FY21 - FY24 Strategic Plan webinar, Governance is discussed 30 min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Kristian Ørmen |  |  |  |  | PTI Board Actions are listed publically at: https://pti.icann.org/pti-board-meetings | 18.3.d
26 | Article VI, Section 6.1 (c) | Transparency | Agree not to redact any PTI Board minutes related to decisions concerning the IANA Naming Function, provided that the PTI Board may redact such minutes on the determination that such redacted information (i) relates to confidential personnel matters, (ii) is covered by attorney-client privilege, work product doctrine or other recognized legal privilege, (iii) is subject to a legal obligation that Contractor maintain its confidentiality or otherwise would result in the disclosure of confidential information of Contractor’s customers, (iv) would disclose trade secrets, or (v) would present a material risk of negative impact to the security, stability or resiliency of the IANA Naming Function or the Internet. | see above |  |  | https://www.icann.org/resources/board-material/briefing-materials-guidelines-2019-12-20-en | Kristian Ørmen |  |  |  |  | https://www.icann.org/resources/board-material/briefing-materials-guidelines-2019-12-20-en | 18.3.d
27 | Article VI, Section 6.1 (d) | Transparency | Have the General Manager of Contractor and chairperson of the PTI Board sign an annual attestation that Contractor has complied with the requirements of this Section 6.1. | see above |  |  | The PTI President signs an annual attestation which is currently not on-line PTI FY21 - FY24 Strategic Plan webinar, Governance is discussed 30 min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Kristian Ørmen |  | Request to ICANN/PTI: Annual Attestations |  |  |  | 18.3.d
28 | Article VI, Section 6.1 (e) | Transparency | Subject to the terms of this Contract, PTI shall operate to the maximum extent feasible in an open and transparent manner and consistent with procedures designed to ensure fairness, in each case, as such concepts are contemplated by ICANN’s Bylaws. | see above |  |  | PTI FY21 - FY24 Strategic Plan webinar https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Kristian Ørmen | [5 empty] | 18.3.d
29 | Article VII | AUDITS, MONITORING AND REVIEWS |  | Notes apply to all of Article VII: Audits, Monitoring & Reviews below. Types of audits/monitoring that contractor agrees to perform and what is published publically
30 | Article VII, Section 7.1 (a) | Audits | Contractor shall generate and publish via the IANA Website a monthly audit report identifying each root zone file and root zone “WHOIS” database change request and its status. The relevant policies under which the changes are made shall be noted within each monthly report. Such audit report shall be due to ICANN no later than 15 calendar days following the end of each month. | see above |  |  | www.iana.org/performance/root-audit IANA SERVICES OVERVIEW by Kim Davies, ROOT ZONE MANAGEMENT: 40mins https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Andreas Dlamini | [AD] Because the report is published publicly and it covers all the required aspects, I don't think there is a need for further evaluation |  | [AD] The PTI produces the monthly report as required and pubishes it on the website. For April 2020, the report has been published well before the 15 day timeline for submission to ICANN. It is my belief that the report is published on the website after submission to ICANN. |  | [AD] PTI carries out the function as required | 18.3.d
31 | Article VII, Section 7.1 (b) | Audits | Contractor shall annually perform a specialized compliance audit of Contractor’s security provisions relating to the IANA Naming Function against existing best practices and ARTICLE XI. This specialized compliance audit shall be performed by an external, independent auditor. | see above |  |  | An external auditor performs a specialized compliance audit of PTI’s security provisions relating to the IANA Naming Function against existing best practices. Description of audit: https://www.iana.org/about/audits IETF review of audit: https://iaoc.ietf.org/contracts.html IANA SERVICES OVERVIEW by Kim Davies, Auditing: 13mins https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC PTI FY21 - FY24 Strategic Plan webinar, Security is discussed 14min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Andreas Dlamini | [AD] Interview ICANN Org, CSC and IETF, TLD operators |  | [AD] The auditor, PwC together with PTI have posted security audit reports that are to do with the Root Zone KSK (service organization control, SOC 3 and not the other aspects of the naming function SOC 2. The SOC 3 reports are good but since I can't access the SOC 2 reports, the audit report produced therefore does not meet the criteria of Section 11. The other thing, it is not clear if the audit will forever be carried out by PwC only. | Possible question would be: 1) If there is a limit on PwC's contract on the IANA audit functions. 2) If the SOC 2 reports are produced at all and submitted to the relevant bodies. 3) If the TLD operators do receive notifications from the PTI when they are supposed to. |  | 18.3.d
32 | Article VII, Section 7.2 (a) | Performance Monitoring | So long as the CSC exists pursuant to ICANN’s Bylaws, Contractor acknowledges and agrees that the CSC is entitled to monitor Contractor’s performance under this Contract (including the SOW) in accordance with ICANN’s Bylaws. | see above |  | 5. Has PTI provided the CSC with reports that enable the CSC to fulfill it's remit and this section of the contract? ANSWER: Yes. But the CSC has also been discussing areas in the IANA contract that are not being monitored, and discussing if we need new metrics. | https://www.icann.org/csc/reports | Tomslin & James | Has PTI provided and continue to provide the CSC with reports reflecting the SOW? | [Tomslin] NONE | [Tomslin] Monthly reports continue to be provided | N/A | [Tomslin] PTI has provided monthly reports since October 2016 and continueing to work with CSC. This is acknowledgement that the CSC is entitled to monitor its performance. Reports are available publically at: https://www.iana.org/performance/csc-reports and the CSC's notification to their customers can be found at: https://www.icann.org/csc/reports | 18.3.d
33 | Article VII, Section 7.2 (b) | Performance Monitoring | Contractor shall provide reports to the CSC as contemplated by the SOW. | see above |  | 3. Does the CSC believe it receives reports covering all performance areas within the CSC's remit? ANSWER: Yes, and it is actually too much information with some metrics that are unnecessary for the CSC’s purpose. The CSC is concerned that tracking too many metrics could be a burden to PTI and not be providing any value [note - PTI now has an automated system that tracks and publishes these metrics]. The CSC is learning which metrics to skip in order to pay attention to the most important metrics. [note - Peter stated he preferred more metrics to less] 4. Does ICANN/PTI respond to any report changes that the CSC has ever requested in order to ensure the reports cover the IANA Naming function performance accurately. ANSWER: There has been little need to ask for changes, but on 2 occasions the CSC asked for information to be presented differently and PTI responded immediately. 6. Are the reports provided in a timely manner? ANSWER: Yes, and PTI works very hard to get us the reports before their due date when the CSC needs them early for a face-to-face meeting. The report has never been late. | https://www.iana.org/performance/csc-reports | Tomslin & James | Has PTI provided the CSC with reports reflecting the SOW? | NONE | Reports confirmed | N/A | PTI has provided a monthly report to the CSC since October 2016. Reports are available publically at: https://www.iana.org/performance/csc-reports and the CSC's notification to their customers can be found at: https://www.icann.org/csc/reports | 18.3.d
34 | Article VII, Section 7.2 (c) | Performance Monitoring | Contractor shall act in good faith to resolve issues identified by the CSC. | see above |  |  |  | Tomslin & James | Outreach question to CSC: whether PTI acted in good faith to resolve issue the CSC identified | [Tomslin] Question sent to CSC for a response |  | [Tomslin] Outreach question to CSC: In CSC's opinion, has PTI acted in good faith to resolve any performance issues the CSC has identified in the past? |  | 18.3.d
35 | Article VII, Section 7.2 (d) | Performance Monitoring | Contractor acknowledges that the CSC shall be empowered to escalate identified areas of concern as set forth in ARTICLE VIII. | see above |  | 7. Has the CSC needed to in-act the Remedial Action Procedure (called RAPs, this is the escalation process), and if so, how did PTI (& ICANN) react? ANSWER: There has been no cause to utilize the RAPs; no systemic issues. 8. Has the CSC found other issues not covered by the Remedial Action Procedure, that required PTI’s (& ICANN’s) response? If so, what are the details? ANSWER: The SLA changes are the only thing. | Via the Remedial Action Procedures : https://www.icann.org/en/system/files/files/csc-remedial-action-procedures-19feb19-en.pdf | Tomslin & James | Does a CSC escalation process exist. | NONE | YES | N/A | ICANN, PTI and the CSC developed and approved the Remidial Action Procedures which PTI adopted on February 2019. A copy can be found at: https://www.icann.org/en/system/files/files/csc-remedial-action-procedures-19feb19-en.pdf | 18.3.d
36 | Article VII, Section 7.3 all | IANA Naming Function Reviews | (a) Contractor acknowledges that ICANN’s Board of Directors (the “ICANN Board”) may cause a review by an IFRT, relating to the IANA Naming Function, this Contract and Contractor’s performance under this Contract (including the SOW), in accordance with ICANN’s Bylaws (an “IANA Function Review” or “IFR”). (b) Contractor shall cooperate with the conduct of any IFRT, including any site visit conducted by an IFRT that has been previously approved by ICANN in accordance with ICANN’s Bylaws. (c) Contractor agrees that ICANN may unilaterally amend or terminate this Contract (including the SOW) in accordance with an approved IFR Recommendation, an approved Special IFR Recommendation or an approved SCWG Recommendation (as such terms are defined in ICANN’s Bylaws), subject to the limitations set forth in ICANN’s Bylaws. Contractor agrees to abide by and implement any such amendments. | There was no IFR with the US Government before the IANA Stewardship Transition. This obligates PTI to cooperate with this review (IFR). This needed to be in contract becaue the bylaws obligate ICANN to do this review, but no obligation for IANA Functions Operator to cooperate, so we put that requirement here. | IFRT#7[Amy] suggest reviewing this section towards the end of the IFRT |  |  | IFR Team | [5 empty] | 18.3.b
37 | Article VIII | Escalation Mechanisms |  | Notes apply to all sections under Article VIII: Escalation Mechanisms listed below: Complaint Resoution proces is spelled out here along with customer naming mediation process. Came from the CWG stewardship which was not in place with US Government contract. Other customer resolution and escalation mechanisms exist (example: CSC's RAPs). Mechanisms to assist before you have to go to extreme of mediation. Putting this in the contract shows ICANNs and PTIs' commitment to resolving customer issues. We do have other mechanisms outside of this contract to maintain customer service levels and resolve issues....such as the CSC.
38 | Article VIII, Section 8.1 all | Complaint Resolution Process | (a) If Contractor receives a customer service complaint from a customer (a “Complaint”), Contractor will review the Complaint and attempt to resolve it to the reasonable satisfaction of the person or entity who brought the Complaint (the “Complainant”) as soon as reasonably practicable. If the Complaint is not so resolved, the Complainant may escalate the matter in writing to Contractor’s management team, in which case Contractor shall notify the CSC. If the Complaint is still not resolved, the Complainant or the President of Contractor may escalate the matter in writing to ICANN’s Ombudsman. (b) If (i) a Complainant is a customer and (ii) after completing the escalation process provided for in Section 8.1(a), the Complaint is still not resolved, then (A) the CSC may conduct a review to determine whether the Complaint is subject of a persistent performance issue of Contractor or an indication of a systemic problem with Contractor’s performance of the IANA Naming Function pursuant to the terms of this Contract (a “Performance Issue”) and (B) the Complainant may (x) request mediation, which shall be conducted in a manner consistent with the terms and process set forth below in Section 8.1(c) and (y) if the issue is not resolved following such mediation and the Complaint meets the requirements of the Independent Review Process, initiate an Independent Review Process (as defined in the ICANN’s Bylaws). If the CSC determines that a Performance Issue exists, the CSC may seek remediation of the Performance Issue through the IANA Problem Resolution Process described in Section 8.2. (c) Customer Mediation Process. (i) If a Complainant is a customer of Contractor, after completing the escalation process provided for in Section 8.1(a), the customer may initiate mediation by delivering a written notice to the President of Contractor and the Secretary of ICANN. (ii) There shall be a single mediator who shall be selected by the agreement of the customer and ICANN. ICANN shall propose a slate of at least five potential mediators, and the customer shall select a mediator from the slate or request a new slate until a mutually agreed mediator is selected. The customer may recommend potential mediators for inclusion on the slates selected by ICANN. ICANN shall not unreasonably decline to include mediators recommended by the customer on proposed slates and the customer shall not unreasonably withhold consent to the selection of a mediator on slates proposed by ICANN. (iii) The mediator shall be a licensed attorney with general knowledge of contract law and general knowledge of the DNS and ICANN. The mediator may not have any ongoing business relationship with ICANN, Contractor or the customer. The mediator must confirm in writing that he or she is not, directly or indirectly, and will not become during the term of the mediation, an employee, partner, executive officer, director, consultant or advisor of ICANN, Contractor or the customer. (iv) The mediator shall conduct the mediation in accordance with this Section 8.1(c), the laws of California and the rules and procedures of a well-respected international dispute resolution provider. (v) The mediation will be conducted in the English language and will occur in Los Angeles County, California, unless another location is mutually agreed between ICANN, Contractor and the customer. (vi) ICANN, Contractor and the customer shall discuss the dispute in good faith and attempt, with the mediator’s assistance, to reach an amicable resolution of the dispute. (vii) ICANN shall bear all costs of the mediator. (viii) If ICANN, Contractor and the customer have engaged in good faith participation in the mediation but have not resolved the dispute for any reason, ICANN, Contractor and the customer may terminate the mediation at any time by declaring an impasse. 12 (ix) If a resolution to the dispute is reached by ICANN, Contractor and the customer, ICANN, Contractor and the customer shall document such resolution. | see above | IFRT#7: [Fred] anyone used complaint procedure? [Amy] a few excalations that PTI notified the CSC of [Fred]: we could interview these parties to see if they were satisfied [Kim]: PTI could reach out to them and notify them of IFRT work and if open to it, PTI can introduce them to IFRT. [Fred]: we don't need to know subject of complaint; just if the process worked [Kim]: need to go back to team about this | 9. Have known customer complaints been resolved to the CSC's satisfaction? ANSWER: Individual customer complaints and escalations, go through PTI’s customer complaint process, not to the CSC. The CSC would only escalate using the RAPs if a systemic problem was noted within the customer escalations. The CSC is made aware of all customer escalations by PTI, so that the CSC can monitor for determining if there are systemic issues. To date, the CSC has never needed to utilize the RAPs. The CSC frequently gets customers coming directly to them and the CSC redirects them to PTI’s process. 10. What types of complaints has the CSC received? ANSWER: See answer to #9 11. Has the CSC uncovered any systemic problems with the IANA Naming Function services through these complaints? If so, did PTI fix this issue? ANSWER: see answer to #9 | https://www.iana.org/help/complaint-procedure and https://www.iana.org/form/complaint | Tomslin & Fred | Kim will look into past complaints and determine if reaching out to them on feedback regarding complaint process is feasible and useful | [Tomslin] Contact list of parties that have escalated to PTI before [Tomslin] Email requesting the contact list sent to PTI |  | [Tomslin] In your use of the customer service Complaint Resolution process to escalate unresolved complaints to PTI management/ICANN, would you consider the process effective? |  | 18.3.a
39 | Article VIII, Section 8.2 | IANA Problem Resolution Process | Following the Effective Date, Contractor shall work cooperatively with the CSC to develop “Remedial Action Procedures” for the purpose of addressing Performance Issues. If the CSC determines that a Performance Issue exists, the CSC may seek resolution of the Performance Issue with Contractor, in which case Contractor shall comply with such Remedial Action Procedures if and to the extent the CSC also complies with such procedures. | RAPs were completed by the CSC |  | see above, 8.1 | https://www.icann.org/en/system/files/files/csc-remedial-action-procedures-19feb19-en.pdf | Tomslin | [Tomslin] Was a Remedial Action Procedure developed? | [Tomslin] NONE | [Tomslin] YES | N/A | [Tomslin] The existing Remedial Action Process adopted by CSC on January 2019 and by PTI on Frebruary 2019, meets the contract's requirements. https://www.icann.org/en/system/files/files/csc-remedial-action-procedures-19feb19-en.pdf | 18.3.a
40 | Article VIII, Section 8.3 all | Notice and Mitigation Plan. | (a) Contractor shall promptly inform ICANN of any issue or dispute arising from its performance of the requirements and services contemplated by this Contract prior to the Complaint being escalated pursuant to Section 8.1(a), and shall agree with ICANN on a plan to resolve the Complaint. (b) If, for any reason, Contractor fails to meet any of the requirements of this Contract, Contractor shall (i) conduct an analysis of its operations to determine the root cause of such failure, (ii) develop a mitigation plan to avoid the root cause of such failure from occurring in the future, and (iii) deliver the report to ICANN upon its completion. Contractor shall modify and update any mitigation plan as directed by ICANN. | A mitigation plan: how PTI will figure out how to mitigate issues (handle issues and prevent them from repeating) | IFRT#7:[Fred] how is this done today? [Amy] PTI notifies CSC mail group which I'm on about the escalation. PTI will report out on it by the next CSC meeting. So far they have always resolved before escalation is needed. [Fred] attestation from ICANN that they've been notified of escalations by PTI would suffice? |  | PTI FY21 - FY24 Strategic Plan webinar, Trust is discussed 7min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true PTI FY21 - FY24 Strategic Plan webinar, Service Delivery is discussed 18min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true |  | Attestation letter from PTI & ICANN [Tomslin] The attestation will cover the fact that PTI has notified ICANN of all customer escalations but I think Incident reports also have to be examined for the existence any repeat incident. This would determine if there were instances where a mitigation plan was either not provided or it was, but was't followed to prevent repeat of an incident | Request Kim Davies to address escalations: those due to IANA service issues vs. disputes between 2 entities asking IANA to resolve |  |  |  | 18.3.a and 18.3.i
41 | Article IX | TERM; RENEWAL; TRANSITION AND TERMINATION |  | Notes apply to all of Article IX: Term, Renewal, Transition & Termination below. Standard to contracts, but written differently for ICANN/PTI. Perpetual renewal; Contract termination, in Bylaws, ICANN would only do so if a recommendation came from a Special IFR (and then PTI has to provide a plan to transition functions to a new operator and needs to ensure operational consistency with no interruptions in service during a transition to a new entity.
42 | Article IX, Section 9.1 | Initial Term | The initial term of this Contract will be five years from the Effective Date (the “Initial Term”). | see above | [9 empty] | 18.3.b
43 | Article IX, Section 9.2 all | Renewal; Termination | (a) This Contract will be automatically renewed for successive periods of five years (each, a “Renewal Term”) upon the expiration of the Initial Term and each successive Renewal Term, unless (i) ICANN terminates this Contract pursuant to an SCWG Recommendation arising from an IANA Naming Function Separation Process (as such terms are defined in ICANN’s Bylaws) approved in accordance with ICANN’s Bylaws or (ii) ICANN elects not to renew the Initial Term or any Renewal Term thereafter pursuant to an IFR Recommendation, Special IFR Recommendation, or SCWG Recommendation (as such terms are defined in ICANN’s Bylaws) approved in accordance with ICANN’s Bylaws by providing Contractor with not less than twelve months prior written notice. Any termination or election by ICANN to not renew this Contract under this Section 9.2 must be approved by the ICANN Board to be effective hereunder. (b) Subject to Section 9.2(a), the first Renewal Term shall commence immediately following the end of the Initial Term and each Renewal Term thereafter shall commence immediately following the end of the preceding Renewal Term. Each Renewal Term shall end on the fifth anniversary of the commencement of the Renewal Term. | see above | [9 empty] | 18.3.b
44 | Article IX, Section 9.3 (a), (b), (c) | Transition | (a) Contractor shall develop and maintain, with ICANN input, a plan in place for transitioning the IANA Naming Function to a successor provider to ensure an orderly transition while maintaining continuity and security of operations, including in connection with the nonrenewal of this Contract and/or divestiture or other reorganization of PTI by ICANN as contemplated by ICANN’s Bylaws. The transition plan shall be submitted to ICANN and posted to the IANA Website within 18 months after the Effective Date. The plan shall thereafter be reviewed annually and updated as appropriate. (b) Contractor shall provide support and cooperation to ICANN, and to any successor provider of the IANA Naming Function, in order to effect an orderly, stable, secure and efficient transition of the performance of the IANA Naming Function. (c) Contractor agrees to be engaged in the transition plan and to provide appropriate transition staff and expertise to facilitate a stable and secure transition of the IANA Naming Function to a successor provider. | see above |  | 12. Has the CSC reviewed PTI's Transition Plan, the plan to transition IANA services to another entity? No, as it is not mentioned in the CSC’s Charter. Partly because the CSC is clearly tasked, in their Charter, with continuing to monitor whichever entity performs the IANA Naming Functions...so if the Transition plan was invoked, the CSC would retain their same roll. However, it is a gap between the CSC Charter and the IANA Contract. Further discussion regarding the wording of “(d) ICANN, in conjunction with the CSC as necessary, shall review the transition plan at least every five years.” Kim Davies: PTI interprets this as that PTI must submit/update a Transition plan every five years, but the CSC’s role is “as necessary”, meaning they are not required to review it but only if necessary. However there is no definition of “necessary” so it may be worthwhile to understand what the community believes to be “necessary”. James: believes the community expects the Transition Plan to be published |  | Tentative: Suzanne | [5 empty] | 18.3.b
45 | Article IX, Section 9.3 (d) | Transition | (d) ICANN, in conjunction with the CSC as necessary, shall review the transition plan at least every five years. |  | A Transition plan was completed by PTI | [8 empty] | 18.3.b
46 | Article IX, Section 9.4 | Survival of Terms | Upon the expiration or termination of this Contract under this ARTICLE IX, this Contract shall become wholly void and of no further force and effect, and following such expiration or termination no Party shall have any liability under this Contract to the other Party, except that each Party hereto shall remain liable for any breaches of this Contract that occurred prior to its expiration or termination; provided, however, that the following provisions shall survive the expiration or termination of this Contract: ARTICLE I, ARTICLE III, Section 9.3, ARTICLE XII, ARTICLE XIII, Section 14.1 (but only with respect to obligations accruing prior to the expiration or termination of this Contract), Section 14.2 through Section 14.15, and this Section 9.4. | If any terms need to happen or kept in existence to allow the termination to happen, then ICANN/PTI has obligation to ensure that customers are not impacted | [9 empty] | 18.3.b
47 | Article X | Resources, Fees and Budget |  | Notes apply to all of Article X: Resources, Fees & Budget below. ICANN takes on obligations of resourcing the IANA Naming Functions appropriately. PTI is budgetted within the ICANN Budget, there is an approved IANA Budget, etc.
48 | Article X, Section 10.1 all | Fees | (a) ICANN shall provide or make available to Contractor the necessary personnel (including seconded employees), material, equipment, services and other resources and facilities to perform Contractor’s obligations under this Contract, including funding in accordance with the Approved IANA Budget. (b) Contractor may not charge or collect fees from third parties related to the performance of the IANA Naming Function without the prior written consent of ICANN. (c) Any fees approved by ICANN and charged by Contractor relating to the IANA Naming Function will be based on the actual costs incurred by Contractor to perform the IANA Naming Function. (d) ICANN acknowledges and agrees that the performance by Contractor of the IANA Naming Function is conditioned upon the full and complete performance of all of the services and obligations required of ICANN under the Services Contract between ICANN and Contractor. | Section 10.1 (b): Long standing clause, even in US Government contract. PTI can't collect it's own fees from customers, or base PTI's level of service on fees that customer pays. (Fees are based on costs, not on generating profit). PTI's ability to perform is dependent on resources ICANN gives to support it. ICANN recognizes that PTI can't provide the required level of service without resources provided by ICANN. | [9 empty] | 18.3.b
49 | Article X, Section 10.2 | Budget | Contractor shall comply with the requirements set forth in its Bylaws relating to preparing, submitting and monitoring an annual budget. ICANN will meet annually with the General Manager of Contractor to review the annual budget for the IANA Naming Function, which shall be approved in accordance with Contractor’s Bylaws and ICANN’s Bylaws (“Approved IANA Budget”). | see above | IFRT#7: Support for asking Becky to give IFRT a PTI budget overview |  | https://pti.icann.org/financial-information-for-public-technical-identifiers-pti |  | option to request Becky from Finance to give IFRT an overview |  |  |  |  | 18.3.d
50 | Article XI | Security Requirements |  | Notes apply to all of Article XI: Security Requirements below. Security Plan with requirements to ensure the authentication integrity and reliability of IANA Naming functions.
51 | Article XI, Sections 11.1 | Computing Systems, Notification Systems, Data | Section 11.1 Computing Systems. With respect to the performance of the IANA Naming Function, Contractor shall install and operate all computing and communications systems in accordance with best business and security practices. ICANN and Contractor shall implement a secure system for authenticated communications to Contractor’s customers when carrying out the IANA Naming Function pursuant to the terms of this Contract. ICANN and Contractor shall document practices and configuration of all systems. | see above | IFRT#7 [Fred] SOC2 may be reference material for this IANA SERVICES OVERVIEW by Kim Davies, Auditing involves operating systems: 13mins https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC |  |  | Wilhelm & Fred | [5 empty] | 18.3.b
52 | Article XI, Sections 11.2 | Computing Systems, Notification Systems, Data | Section 11.2 Notification Systems. Contractor shall implement and thereafter operate and maintain a secure notification system at a minimum, capable of notifying TLD registry operators, of such events as outages, planned maintenance, and new developments. In all cases, Contractor shall notify ICANN of any outages. | see above |  |  | PTI FY21 - FY24 Strategic Plan webinar, Security is discussed 14min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Wilhelm & Fred | [5 empty] | 18.3.b
53 | Article XI, Sections 11.3 | Computing Systems, Notification Systems, Data | Section 11.3 Data. Contractor shall ensure the authentication, integrity, and reliability of the service data in performing the IANA Naming Function. | see above |  |  | PTI FY21 - FY24 Strategic Plan webinar, Trust is discussed 7min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Wilhelm & Fred | [5 empty] | 18.3.b
54 | Article XI, Sections 11.4 | Security Plan, Director of Security | Section 11.4 Security Plan. ICANN shall coordinate with Contractor to develop and execute a security plan that meets the requirements of this Contract and this ARTICLE XI. ICANN and Contractor shall document in the security plan the process used to ensure information systems including hardware, software, applications, and general support systems have effective security safeguards, which have been implemented, planned for, and documented. Contractor shall, in coordination with ICANN, perform periodic reviews of the security plan and update the plan as necessary. | see above |  |  | PTI Information Security Plan V11, January 2017 is NOT a public document PTI FY21 - FY24 Strategic Plan webinar, Security is discussed 14min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Wilhelm & Fred | [5 empty] | 18.3.b
55 | Article XI, Sections 11.5 | Security Plan, Director of Security | Section 11.5 Director of Security. Contractor’s Director of Security shall be responsible for ensuring Contractor’s compliance with the technical and physical security measures and requirements of this Contract. | see above |  |  |  | Wilhelm & Fred | [5 empty] | 18.3.b
56 | Article XII | Confidentiality |  | Common in contracts. For things that should be non-public and confidential for the purpose of security issues or risk of PTI's ability to maintain integrity of the system, etc. PTI acknowledges it is required to cooperate with dispute resolution procedures, etc. Example for IFRT, review team can ask for these confidential materials. ICANN can determine how the review team should access or protect those materials; how it can be reflected in your report. This section acknowledges exception sto confidentiality requirements.
57 | Article XIII | Intellectual Property |  | Common in contracts: what will happen if new creations are developed by employees and who owns that
58 | Article XIV | Miscellaneous |  | Common in contracts: who pays for what in indemnification. ICANN'S responsibility to indemnify. Notice provisions specified since ICANN can treat performance issues at an arms length. Section says that you can waive one section of the contract (such as it becomes unenforceable because of local laws) without nullifying the entire contract. Establishes viability of this contract. PTI may NOT subcontract IANA Naming Functions out.
59 | Annex A | Statement of Work for Management of the DNS Root Zone |  | Statement of Work (SOW) moves from legal world to technical world . This is the day-to-day responsibilities of PTI. Flagging that we did Amendment No 1 that moved SLAs to outside of the contract to a webpage where a process can amend SLAs without needing a contract amendment. But the rest of this Annex A applies.
60 | Annex A, 1 (a) | Root Zone Management | a. The Root Zone Management component of the IANA Naming Function is the administration of certain responsibilities associated with the Internet DNS root zone management. |  | IFRT#7: [Kim] PTI can provide description of how this is implemented today with pertinent documentation. No single approach. |  | IANA SERVICES OVERVIEW by Kim Davies, ROOT ZONE MANAGEMENT: 40mins in https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Fred & Peter | [5 empty] | 18.3.b
61 | Annex A, 1 (b) | Root Zone Management | b. Contractor shall collaborate with Interested and Affected Parties to develop, maintain, enhance and post performance standards for Root Zone Management. Specifically, Contractor shall perform Root Zone Management in accordance with the service levels set forth in Section 2. |  |  |  | https://www.iana.org/domains/root IANA SERVICES OVERVIEW by Kim Davies, ROOT ZONE MANAGEMENT: 40mins in https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC IANA SERVICES OVERVIEW by Kim Davies, Performance Reporting: 27min https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Fred & Peter | [5 empty] | 18.3.a
62 | Annex A, 1 (c) | Root Zone Management | c. Contractor shall also implement DNSSEC in all zones for which ICANN has technical administration authority. |  |  |  |  | Fred & Peter | [5 empty] | 18.3.b
63 | Annex A, 1 (d) (i) | Root Zone Management | d. Contractor shall facilitate and coordinate the root zone of the domain name system, and maintain 24 hour-a-day/7 days-a-week operational coverage. Contractor shall work collaboratively with the Root Zone Maintainer, in the performance of this function. i. Contractor shall receive and process root zone file change requests for TLDs. These change requests include addition of new or updates to existing TLD name servers (“NS”) and delegation signer (“DS”) resource record (“RR”) information along with associated “glue” (A and AAAA RRs). A change request may also include new TLD entries to the root zone file. Contractor shall process root zone file changes as specified in Section 2 of this Annex A. |  |  |  | https://www.iana.org/domains/root/help IANA SERVICES OVERVIEW by Kim Davies, ROOT ZONE MANAGEMENT: 40mins in https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC PTI FY21 - FY24 Strategic Plan webinar, Service Delivery is discussed 18min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Fred & Peter | [5 empty] | 18.3.a
64 | Annex A, 1 (d) (ii) | Root Zone Management | ii. Contractor shall maintain, update, and make publicly accessible a Root Zone registration database with current and verified contact information for all TLD registry operators. The Root Zone registration database, at a minimum, shall consist of the following data fields: domain status and contact points for resolving issues relating to the operation of the domain (comprised of at least organizational name, postal address, email address and telephone number). Contractor shall receive and process root zone registration data change requests for TLDs. |  |  |  | https://www.iana.org/domains/root/db IANA SERVICES OVERVIEW by Kim Davies, ROOT ZONE MANAGEMENT: 40mins in https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Fred & Peter | [5 empty] | 18.3.a
65 | Annex A, 1 (d) (iii) | Root Zone Management | iii. Contractor shall apply existing policies in processing requests related to the Delegation, Revocation and Transfer of ccTLDs, including RFC 1591 as interpreted by the FOI and any further clarification of these policies developed by the ccNSO, as appropriate under ICANN’s Bylaws, and approved by the ICANN Board. In addition to these policies, Contractor shall, where applicable, consult the GAC 2005 ccTLD Principles. If an existing policy framework does not cover a specific situation, Contractor will use commercially reasonable efforts to consult with and provide opportunity for input from Significantly Interested Parties and, where necessary, may request the ccNSO to undertake policy development work to address such issues. |  |  |  | PTI FY21 - FY24 Strategic Plan webinar, Governance is discussed 30 min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Fred & Peter | [5 empty] | 18.3.a
66 | Annex A, 1 (d) (iv) | Root Zone Management | Contractor shall apply existing policy frameworks in processing requests related to retirement of a ccTLD, including RFC 1591 as interpreted by the FOI and any further clarification of these policies developed by the ccNSO, as appropriate under ICANN’s Bylaws, and approved by the ICANN Board. If an existing policy does not cover a specific situation, Contractor will use commercially reasonable efforts to consult with and provide opportunity for input from Significantly Interested Parties and, where necessary, may request the ccNSO to undertake policy development work to address such issues. |  |  |  | PTI FY21 - FY24 Strategic Plan webinar, Governance is discussed 30 min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Fred & Peter | [5 empty] | 18.3.a
67 | Annex A, 1 (d) (v) | Root Zone Management | Contractor shall verify that all requests related to the delegation and redelegation of generic TLDs are consistent with the procedures developed by ICANN. |  |  |  | PTI FY21 - FY24 Strategic Plan webinar, Service Delivery is discussed 18min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true IANA SERVICES OVERVIEW by Kim Davies, Auditing involves operating systems: 13mins https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Fred & Peter | [5 empty] | 18.3.a
68 | Annex A, 1 (d) (vi) | Root Zone Management | Contractor shall maintain an automated root zone management system that, at a minimum, includes (A) a secure (encrypted) system for customer communications; (B) an automated provisioning protocol allowing customers to manage their interactions with the root zone management system; (C) an online database of change requests and subsequent actions whereby each customer can see a record of their historic requests and maintain visibility into the progress of their current requests; (D) a test system, which customers can use to meet the technical requirements for a change request; and (E) an internal interface for secure communications between the Contractor and the Root Zone Maintainer. |  |  |  | https://www.iana.org/domains/root PTI FY21 - FY24 Strategic Plan webinar, Service Delivery is discussed 18min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true IANA SERVICES OVERVIEW by Kim Davies, Auditing involves operating systems: 13mins https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC IANA SERVICES OVERVIEW by Kim Davies, ROOT ZONE MANAGEMENT: 40mins in https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Fred & Peter | [5 empty] | 18.3.a
69 | Annex A, 2 (a) | Service Levels | Contractor shall perform the Services in accordance with the following “Service Levels”. The expectation is that Contractor will normally perform within the threshold. The thresholds will be modified over time as part of periodic reviews of the service level expectation. A subset of the following measures relate to measurement of non-routine changes where it is not applicable to set a specific threshold for performance. It is expected for measurements of non-routine process steps these will only be reported with no applicable service level expectation. |  |  |  | PTI publishes a SLA report referred to as the CSC Report (https://www.iana.org/performance/csc-reports). (PTI's Report: and the CSC's analysis: https://www.icann.org/csc/reports). The CSC meets on a monthly basis to review this report, and determine if there are any recurring issues that need to be addressed. Should such an issue arise, the CSC would trigger the Remedial Action Procedures {RAPs). The CSC and PTI may determine that the SLA metric is not accurately reflecting the purpose of the SLA. The CSC, PTI or ICANN would trigger the Process for Amending the IANA Naming Service Level Agreements. (the RAPs and SLA Change process can be found on: https://www.icann.org/en/csc/other-procedures). Also review the CSC's homepage, from which all of these pdfs can be found: https://www.icann.org/csc IANA SERVICES OVERVIEW by Kim Davies, Performance Reporting: 27min https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC |  | Review PTI/CSC reports to determine if SLAs are met within expected range. See "PTI-CSC REPORTS" Sheet in THIS spreadsheet for the % of metrics met by PTI from 2016 to tody. There will be an IFRT-CSC meeting to discuss this | NONE | Since 2016, PTI has consistently met between 95.0 to 100% of SLAs. Metric thresholds have been adjusted twice, utilizing the SLA Change Process (See "PTI-CSC REPORTS" Sheet in THIS spreadsheet) |  |  | 18.3.a
70 | Annex A, 2 (b) | Service Levels | Services Definitions i. Category I (Routine updates impacting Root Zone File). Routine change requests that alter the technical data published in the DNS root zone (e.g. changes to NS records, DS records and glue records). A third party may be engaged to compile, publish and distribute the root zone. ii. Category II (Routine updates not impacting Root Zone File). Routine change requests that do not alter the DNS root zone (e.g., contact data and metadata). These changes do not require changes to the root zone. iii. Category III (Creating or Transferring a gTLD). Requests to create (“delegate”) or transfer (“redelegate” or “assign”) a generic TLD. These changes require additional processing by Contractor to ensure policy and contractual requirements associated with a change of control for the TLD are met. iv. Category IV (Creating or Transferring a ccTLD). Requests to create or transfer a country-code TLD. These changes require additional processing by Contractor to ensure policy requirements are met. This processing includes additional analysis on the change request, production of a report, and review of the report (including verification that all existing registration data has been successfully transferred from the old to new registry operator). v. Category V (Other change requests). Other non-routine change requests. Contractor is required to process change requests that may have special handling requirements, or require additional documentary evidence or clarifications from the customer or third parties, that prevent automating the handling of the request. These requests include, but are not limited to: 1. Customers that require requests to be handled outside the online self-service platform, such as those lodging change requests through the exchange of postal mail; 2. Customers that have placed special handling instructions on file with Contractor, or have otherwise asked for special handling for a request that deviates from the normal process, resulting in the request being executed manually; 3. Unique legal or regulatory encumbrances that must be satisfied that require additional processing; 4. Removing a TLD from service (i.e. retirement or revocation); and 5. Changes that relate to the operation of the root zone itself, including changing the Root Key Signing Key, altering the set of authoritative name servers for the root zone (i.e. the “root servers”), and changes to the “root hints”. | [10 empty] | 18.3.a
71 | Annex A, 2 (c through g) | Service Levels | Annex A (= SOW), Section 2, subsections (c) through (g) are “deleted” and replaced with ‘Amendment No.1 to IANA NaminAmendment No. 1 to IANA Naming Function Contract’ as of 07 May 2019 deleted Section 2, subsections (c) through (g) of the Annex A (=SOW) and replaced while also moving the Service Level Agreements (SLAs) to https://pti.icann.org/iana-naming-function-services-service-level-agreementsg Function Contract’
72 | Annex A, 3 | Performance Metric Requirements
73 | Annex A, 3 (a) | Program Reviews and Site Visits | i. Contract acknowledges that the CSC is entitled to conduct reviews in accordance with ICANN’s Bylaws and the CSC Charter. ii. Contractor acknowledges that an IFRT is entitled to conduct site visits in accordance with ICANN’s Bylaws.
74 | Annex A, 3 (b) | Monthly Performance Progress Report. | Contractor shall prepare and submit reports as mutually agreed between Contractor and the CSC. |  |  | 3. Does the CSC believe it receives reports covering all performance areas within the CSC's remit? ANSWER: Yes, and it is actually too much information with some metrics that are unnecessary for the CSC’s purpose. The CSC is concerned that tracking too many metrics could be a burden to PTI and not be providing any value [note - PTI now has an automated system that tracks and publishes these metrics]. The CSC is learning which metrics to skip in order to pay attention to the most important metrics. [note - Peter stated he preferred more metrics to less] 4. Does ICANN/PTI respond to any report changes that the CSC has ever requested in order to ensure the reports cover the IANA Naming function performance accurately. ANSWER: There has been little need to ask for changes, but on 2 occasions the CSC asked for information to be presented differently and PTI responded immediately. 5. Has PTI provided the CSC with reports that enable the CSC to fulfill it's remit and this section of the contract? ANSWER: Yes. But the CSC has also been discussing areas in the IANA contract that are not being monitored, and discussing if we need new metrics. 6. Are the reports provided in a timely manner? ANSWER: Yes, and PTI works very hard to get us the reports before their due date when the CSC needs them early for a face-to-face meeting. The report has never been late. 7. Has the CSC needed to in-act the Remedial Action Procedure (called RAPs, this is the escalation process), and if so, how did PTI (& ICANN) react? ANSWER: There has been no cause to utilize the RAPs; no systemic issues. 8. Has the CSC found other issues not covered by the Remedial Action Procedure, that required PTI’s (& ICANN’s) response? If so, what are the details? ANSWER: The SLA changes are the only thing. | https://www.iana.org/performance/csc-reports, (and indirectly, but not due to a contractual requirement, the CSC reports at https://www.icann.org/en/csc/reports). b refers to same reports as d below, but this specifies the report’s creation |  | Ask CSC this question: Has PTI provided the CSC with reports as agreed upon between PTI and the CSC? (A summary for the PTI/CSC reports is in this spreadsheet on tab "PTI-CSC REPORTS") | CSC Interview required |  |  |  | 18.3.d
75 | Annex A, 3 (c) | Root Zone Management Dashboard. | Root Zone Management Dashboard. Contractor shall work collaboratively with ICANN and Interested and Affected Parties to produce the dashboard to report Service Level Expectations for Root Zone Management, which will be used for real-time reporting of Contractor’s performance. |  |  |  | online dashboard at: https://sle-dashboard.iana.org/ | [6 empty] | 18.3.d
76 | Annex A, 3 (d) | Performance Standards Reports | Performance Standards Reports. Contractor shall develop and publish performance standard metric reports for the IANA Naming Function in consultation with the CSC. The performance standards metric reports will be published via a website every month (no later than 15 calendar days following the end of each month). |  |  |  | refers to same reports as b.: https://www.iana.org/performance/csc-reports, but specifies that they must be published. IANA SERVICES OVERVIEW by Kim Davies, Performance Reporting: 27min https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | [6 empty] | 18.3.d
77 | Annex A, 3 (e) | Customer Service Survey | In accordance with ICANN’s Bylaws, Contractor shall collaborate with the CSC and ICANN to maintain and enhance the annual customer service survey consistent with the performance standards for Root Zone Management. The survey shall, at a minimum, include a feedback section for the IANA Naming Function. No later than 60 calendar days after completing a customer service survey, Contractor shall prepare a report (the “CSS Report”), submit the CSS Report to ICANN and publicly post the CSS Report to the IANA Website. |  |  |  | Annual Customer Surveys 2019: https://www.iana.org/reports/2019/customer-survey-20191210.pdf 2018: https://www.iana.org/reports/2018/customer-survey-20181206.pdf 2017: https://www.iana.org/reports/2018/customer-survey-20180118.pdf 2016: https://www.iana.org/reports/2017/customer-survey-20170111.pdf 2015: https://www.iana.org/reports/2015/customer-survey-20151115.pdf 2014: https://www.iana.org/reports/2014/customer-survey-20141217.pdf 2013: https://www.iana.org/reports/2013/customer-survey-20131210.pdf | [6 empty] | 18.3.a
78 | Annex A, 3 (f) | Final Report. | Contractor shall prepare and submit a final report on the performance of the IANA Naming Function that documents standard operating procedures, including a description of the techniques, methods, software, and tools employed in the performance of the IANA Naming Function. Contractor shall submit the report to the CSC and ICANN no later than 30 days after the expiration or termination of the Contract. | [10 empty] | 18.3.b
79 | Annex A, 3 (g) | Inspection and acceptance. | ICANN will perform final inspection and acceptance of all deliverables and reports articulated in this Section 3, as set forth in Section 4.10(a) of the Contract. Any deficiencies identified by ICANN shall be corrected by Contractor and resubmitted to ICANN within 10 business days after Contractor’s receipt of notice of such deficiency. | [10 empty] | 18.3.b
80 | Annex A, 4 | BASELINE REQUIREMENTS FOR DNSSEC IN THE AUTHORITATIVE ROOT ZONE
81 | Annex A, 4 (a) | DNSSEC at the authoritative Root Zone | DNSSEC at the authoritative Root Zone requires cooperation and collaboration between the Contractor and the Root Zone Maintainer. The baseline requirements encompass the responsibilities and requirements for Contractor and these responsibilities and requirements must be implemented in cooperation with similar responsibilities and requirements defined within ICANN’s relationship with the Root Zone Maintainer. |  |  |  | IANA SERVICES OVERVIEW by Kim Davies, ROOT ZONE MANAGEMENT: 40mins https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC PTI FY21 - FY24 Strategic Plan webinar, Security is discussed 14min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Wilhelm | [5 empty] | 18.3.b
82 | Annex A, 4(b) (i) | General Requirements | The Root Zone system needs an overall security lifecycle, such as that described in ISO 27001, NIST SP 800-53, etc., and any security policy for DNSSEC implementation must be validated against existing standards for security controls. |  |  |  | The SOC 3 audit is described and can be read at: https://www.iana.org/about/audits. The SOC 2 audit covers the same topics but at a more detailed level and is distributed to the oversight bodies: IETF and the five (5) Regional Internet Registries (RiRs) | Wilhelm | [5 empty] | 18.3.b
83 | Annex A, 4 (b) (ii) | General Requirements | The remainder of this section highlights security requirements that must be considered in developing any solution. ISO 27002:2005 (formerly ISO 17799:2005) and NIST SP 800-53 are recognized sources for specific controls. Note that reference to SP 800-53 is used as a convenient means of specifying a set of technical security requirements. The systems referenced in this document are assumed to meet all the SP 800-53 technical security controls or equivalent required by a HIGH IMPACT system. |  |  |  | PTI FY21 - FY24 Strategic Plan webinar, Security is discussed 14min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true IANA SERVICES OVERVIEW by Kim Davies, Auditing involves security: 13mins https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Wilhelm | [5 empty] | 18.3.b
84 | Annex A, 4 (b) (iii) | General Requirements | Whenever possible, references to NIST publications are given as a source for further information. These Special Publications (“SP”) are not intended as auditing checklists, but as non-binding guidelines and recommendations to establish a viable IT security policy. Comparable security standards can be substituted where available and appropriate. All of the NIST document references can be found on the NIST Computer Security Research Center webpage (http://www.csrc.nist.gov/). |  |  |  |  | Tomslin | [5 empty] | 18.3.b
85 | Annex A, 4 c | Security Authorization and Management Policy | Security Authorization and Management Policy i. Contractor shall have its own security policy in place; each security policy must be periodically reviewed and updated, as appropriate. 1. Supplemental guidance on generating a Security Authorization Policy may be found in NIST SP 800-37. ii. The policy shall have a contingency plan component to account for disaster recovery (both man-made and natural disasters). 1. Supplemental guidance on contingency planning may be found in SP 800-34 iii. The policy shall address Incident Response detection, handling and reporting (see 4 below). 1. Supplemental guidance on incident response handling may be found in NIST SP 800- 61. |  |  |  | PTI FY21 - FY24 Strategic Plan webinar, Security is discussed 14min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true IANA SERVICES OVERVIEW by Kim Davies, Auditing involves security: 13mins https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Wilhelm & Tomslin | [Tomslin] Verify that PTI has a Security Policy and verify that: a) the policy is frequently reviewed andupdated b) It includes a DR plan c) It includes incident detection and response plan | [Tomslin] PTI security policy document | [Tomslin] Question for PTI: If and when the security policy is reviewed and updated, how does PTI keep records of these reviews and updates? |  |  | 18.3.b
86 | Annex A, 4 (d) | IT Access Control | There shall be an IT access control policy in place and enforced for the key management functions 1. This includes both access to hardware/software components and storage media as well as ability to perform process operations. 2. Supplemental guidance on access control policies may be found in NIST SP 800-12. ii. Users without authentication shall not perform any action in key management. iii. In the absence of a compelling operational requirement, remote access to any cryptographic component in the system (such as hardware security modules) is not permitted. |  |  |  | PTI FY21 - FY24 Strategic Plan webinar, Security is discussed 14min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true IANA SERVICES OVERVIEW by Kim Davies, Auditing involves security: 13mins https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC | Wilhelm & Tomslin | [Tomslin] Verify that PTI has an access Policy and verify that: a) It includes policies on hardware and software access b) it includes policies to keep out unauthenticated users from key management c)it includes a policy to prevent remote access to cryptographic components | [Tomslin] PTI Access policy document |  |  |  | 18.3.b
87 | Annex A, 4 (e) | Security Training | i. All personnel participating in the Root Zone Signing process shall have adequate IT security training. ii. Supplemental guidance on establishing a security awareness training program may be found in NIST SP 800-50. |  |  |  |  | Wilhelm | [5 empty] | 18.3.b
88 | Annex A, 4 (f) | Audit and Accountability Procedures | i. Contractor shall periodically review/update: (1) its formal, documented, audit and accountability policy that addresses purpose, scope, roles, responsibilities, management commitment, coordination among organizational entities, and compliance; and (2) the formal, documented procedures to facilitate the implementation of the audit and accountability policy and associated audit and accountability controls. 1. Supplemental guidance on auditing and accountability policies may be found in NIST SP 800-12. 2. Specific auditing events include the following: a. Generation of keys. b. Generation of signatures c. Exporting of public key material d. Receipt and validation of public key material (i.e., from the ZSK holder or from TLDs) e. System configuration changes f. Maintenance and/or system updates g. Incident response handling h. Other events as appropriate ii. Incident handling for physical and exceptional cyber-attacks shall include reporting to ICANN in a timeframe and format as mutually agreed by ICANN and Contractor. iii. The auditing system shall be capable of producing reports on an ad-hoc basis for ICANN or the CSC. iv. A version of the reports provided to ICANN or the CSC must be made publically available. |  |  |  |  | Wilhelm | [5 empty] | 18.3.b
89 | Annex A, 4 (g) | Physical Protection Requirements | i. There shall be physical access controls in place to only allow access to hardware components and media to authorized personnel. 1. Supplemental guidance on token based access may be found in NIST SP 800-73. 2. Supplemental guidance on token based access biometric controls may be found in NIST SP 800-76. ii. Physical access shall be monitored, logged, and registered for all users and visitors. iii. All hardware components used to store keying material or generate signatures shall have short-term backup emergency power connections in case of site power outage. (See NIST SP 800-53r3). iv. Appropriate protection measures shall be in place to prevent physical damage to facilities as appropriate. |  |  |  |  | Wilhelm & Tomslin |  | [Tomslin] PTI Physical Access policy document |  |  |  | 18.3.b
90 | Annex A, 4 (h) | All Components | i. All hardware and software components must have an established maintenance and update procedure in place. 1. Supplemental guidance on establishing an upgrading policy for an organization may be found in NIST SP 800-40 ii. All hardware and software components provide a means to detect and protect against unauthorized modifications/updates/patching. |  |  |  |  | Wilhelm
91 | Annex A, 4 (i) | Interface Basic Functionality | i. Contractor’s interface shall have the ability to accept and process TLD DS records, including: 1. Accept TLD DS RRs a. Being able to retrieve TLD DNSKEY record from the TLD, and perform parameter checking for the TLD keys, including verifying that the DS RR has been correctly generated using the specified hash algorithm. 2. Having procedures for: a. Scheduled roll over for TLD key material; b. Supporting emergency key roll over for TLD key material; and c. Moving TLD from signed to unsigned in the root zone. ii. Ability to submit TLD DS record updates to the Root Zone Maintainer for inclusion into the root zone. iii. Ability to submit RZ keyset to the Root Zone Maintainer for inclusion into the root zone. |  |  |  | IANA SERVICES OVERVIEW by Kim Davies, Auditing involves operating systems: 13mins https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC PTI FY21 - FY24 Strategic Plan webinar, Service Delivery is discussed 18min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true | Wilhelm
92 | Amendment 1 |  | The Parties hereby agree that subsections (c) through (g) of Section 2 of the SOW (Annex A of the Agreement) are deleted and replaced with the following:
93 | Amendment 1: 1 c | Service Levels | Contractor will perform all services relating to Root Zone Management in accordance with the requirements and “Service Levels” specified at https://pti.icann.org/iana-naming-function-services-service-level- agreements#definitions (the “SLAs”), as such services and SLAs may be amended from time to time in accordance with the procedures specified at https://www.icann.org/en/system/files/files/iana-naming-function-sla-amendment- process-28mar19-en.pdf. |  | PTI FY21 - FY24 Strategic Plan webinar, Service Delivery is discussed 18min in https://icann.zoom.us/rec/play/7pUuJe-sqzk3G4DBsASDVvR6W9W9Kfqs0ykd-KFcnU-2U3AFMFr0ZuFBNuVfCHlhqY88Tlio0WeNEuXf?continueMode=true IANA SERVICES OVERVIEW by Kim Davies, ROOT ZONE MANAGEMENT: 40mins in https://community.icann.org/display/ifr/Webinar%3A+IANA+Overview+for+IFRT+-+24+January+2020+@17%3A00+UTC
94 | Amendment 1: c (II) through 4 | Service Levels | ii. The fields for the SLAs are as follows: 1. Process. The business process that Contractor is requested to perform. 2. Metric.Theindividualmetricthatwillbemeasuredaspartofthe completion of the business process. 3. Threshold. The specified target for each individual change request. 4. Type. Whether the threshold specified is a minimum target (compliance must not be less than the target) or a maximum target (compliance must not be more than the target). 5. Compliance. The percentage that the target goal in aggregate must be met or exceeded within the specified time period for all requests in the specified category. 6. Period. The time over which compliance is measured. (The period of collecting measurements to meet the Service Level Agreement (SLA)). 1 d. Process Performance. Total Contractor transaction time for emergency changes should be completed within a target of 12 hours until reviewed by the CSC with Contractor. e. These elements reflect activity areas that should be instrumented by Contractor, and reported pursuant to ARTICLE VII of the Contract and Section 3 of this SOW.” 2. The Parties agree that, except as set forth in this Amendment, the current terms and conditions of the Contract will remain unchanged and in full force and effect and, to the extent applicable, such and conditions terms shall apply to this Amendment as if it formed part of the Contract. 3. This Amendment may be executed in one or more counterparts, each of which will be deemed to be an original copy of this Amendment and all of which, when taken together, will be deemed to constitute one and the same agreement. 4. Any signature page delivered pursuant to this Amendment via facsimile, email or other electronic means shall be binding to the same extent as an original signature. Any Party who delivers such a signature page agrees to later deliver an original counterpart to any party that requests it.

## Questions for CSC
row # from main page | Section from IANA Naming Functions Contract | Contract Section Text | Questions for the CSC | Applicable Notes | Team Members Reviewing | Conclusion *please initial your comments
10 | Article IV, Section 4.3 (d) | Scope of the IANA Naming Function Provision of other services and implementation of modifications in performance of the IANA Naming Function, in each case upon ICANN’s request and in conformance with applicable policies and procedures. | 1. Does the CSC believe there are processes to address each area where performance of the IANA Naming functions might require changes? ANSWER: Yes. 2. For modification processes that do exist (relevant to the CSC is the SLA change procedure) are you satisfied with the procedure? Has the procedure been invoked and was it successful? ANSWER: When it was determined that SLAs needed to be modified, it took a long time to create the SLA Change Procedure. We reported about the process on our CSC monthly report. Now that there is a procedure, making the SLA changes have commenced. | IFRT#7 [Kim Davies]: Example is the established procedure for making formal changes to SLAs, and this process has been utilized and well documented. [Reference Materials] The CSC, ICANN & PTI utilized the SLA Amendment Process (https://www.icann.org/en/system/files/files/iana-naming-function-sla-amendment-process-28mar19-en.pdf) to make three sets of SLA changes: 1. Technical Check SLA changes implemented 01 July 2019 2. new LGR SLAs implemented 01 January 2020 3. currently pending are new/changes to ccTLD creation/transfer SLAs | Suzanne
32 | Article VII, Section 7.2 (a) | Performance Monitoring So long as the CSC exists pursuant to ICANN’s Bylaws, Contractor acknowledges and agrees that the CSC is entitled to monitor Contractor’s performance under this Contract (including the SOW) in accordance with ICANN’s Bylaws. | 3. Does the CSC believe it receives reports covering all performance areas within the CSC's remit? ANSWER: Yes, and it is actually too much information with some metrics that are unnecessary for the CSC’s purpose. The CSC is concerned that tracking too many metrics could be a burden to PTI and not be providing any value [note - PTI now has an automated system that tracks and publishes these metrics]. The CSC is learning which metrics to skip in order to pay attention to the most important metrics. [note - Peter stated he preferred more metrics to less] 4. Does ICANN/PTI respond to any report changes that the CSC has ever requested in order to ensure the reports cover the IANA Naming function performance accurately. ANSWER: There has been little need to ask for changes, but on 2 occasions the CSC asked for information to be presented differently and PTI responded immediately. 5. Has PTI provided the CSC with reports that enable the CSC to fulfill it's remit and this section of the contract? ANSWER: Yes. But the CSC has also been discussing areas in the IANA contract that are not being monitored, and discussing if we need new metrics. 6. Are the reports provided in a timely manner? ANSWER: Yes, and PTI works very hard to get us the reports before their due date when the CSC needs them early for a face-to-face meeting. The report has never been late. | [Reference Materials]: https://www.icann.org/csc/reports | Tomslin & James | [Tomslin] PTI has provided monthly reports since October 2016 and continueing to work with CSC. This is acknowledgement that the CSC is entitled to monitor its performance. Reports are available publically at: https://www.iana.org/performance/csc-reports and the CSC's notification to their customers can be found at: https://www.icann.org/csc/reports
33 | Article VII, Section 7.2 (b) | Performance Monitoring Contractor shall provide reports to the CSC as contemplated by the SOW. | answers covered by above questions | [Reference Materials] https://www.iana.org/performance/csc-reports | Tomslin & James | PTI has provided a monthly report to the CSC since October 2016. Reports are available publically at: https://www.iana.org/performance/csc-reports and the CSC's notification to their customers can be found at: https://www.icann.org/csc/reports
34 | Article VII, Section 7.2 (c) | Performance Monitoring Contractor shall act in good faith to resolve issues identified by the CSC. | 7. Has the CSC needed to in-act the Remedial Action Procedure (called RAPs, this is the escalation process), and if so, how did PTI (& ICANN) react? ANSWER: There has been no cause to utilize the RAPs; no systemic issues. 8. Has the CSC found other issues not covered by the Remedial Action Procedure, that required PTI’s (& ICANN’s) response? If so, what are the details? ANSWER: The SLA changes are the only thing. | [Reference Materials] | Tomslin & James
35 | Article VII, Section 7.2 (d) | Performance Monitoring Contractor acknowledges that the CSC shall be empowered to escalate identified areas of concern as set forth in ARTICLE VIII. | answers covered by above questions | [Reference Materials] Via the Remedial Action Procedures : https://www.icann.org/en/system/files/files/csc-remedial-action-procedures-19feb19-en.pdf | Tomslin & James | ICANN, PTI and the CSC developed and approved the Remidial Action Procedures which PTI adopted on February 2019. A copy can be found at: https://www.icann.org/en/system/files/files/csc-remedial-action-procedures-19feb19-en.pdf
38 | Article VIII, Section 8.1 all | Complaint Resolution Process (a) If Contractor receives a customer service complaint from a customer (a “Complaint”), Contractor will review the Complaint and attempt to resolve it to the reasonable satisfaction of the person or entity who brought the Complaint (the “Complainant”) as soon as reasonably practicable. If the Complaint is not so resolved, the Complainant may escalate the matter in writing to Contractor’s management team, in which case Contractor shall notify the CSC. If the Complaint is still not resolved, the Complainant or the President of Contractor may escalate the matter in writing to ICANN’s Ombudsman. (b) If (i) a Complainant is a customer and (ii) after completing the escalation process provided for in Section 8.1(a), the Complaint is still not resolved, then (A) the CSC may conduct a review to determine whether the Complaint is subject of a persistent performance issue of Contractor or an indication of a systemic problem with Contractor’s performance of the IANA Naming Function pursuant to the terms of this Contract (a “Performance Issue”) and (B) the Complainant may (x) request mediation, which shall be conducted in a manner consistent with the terms and process set forth below in Section 8.1(c) and (y) if the issue is not resolved following such mediation and the Complaint meets the requirements of the Independent Review Process, initiate an Independent Review Process (as defined in the ICANN’s Bylaws). If the CSC determines that a Performance Issue exists, the CSC may seek remediation of the Performance Issue through the IANA Problem Resolution Process described in Section 8.2. (c) Customer Mediation Process. (i) If a Complainant is a customer of Contractor, after completing the escalation process provided for in Section 8.1(a), the customer may initiate mediation by delivering a written notice to the President of Contractor and the Secretary of ICANN. (ii) There shall be a single mediator who shall be selected by the agreement of the customer and ICANN. ICANN shall propose a slate of at least five potential mediators, and the customer shall select a mediator from the slate or request a new slate until a mutually agreed mediator is selected. The customer may recommend potential mediators for inclusion on the slates selected by ICANN. ICANN shall not unreasonably decline to include mediators recommended by the customer on proposed slates and the customer shall not unreasonably withhold consent to the selection of a mediator on slates proposed by ICANN. (iii) The mediator shall be a licensed attorney with general knowledge of contract law and general knowledge of the DNS and ICANN. The mediator may not have any ongoing business relationship with ICANN, Contractor or the customer. The mediator must confirm in writing that he or she is not, directly or indirectly, and will not become during the term of the mediation, an employee, partner, executive officer, director, consultant or advisor of ICANN, Contractor or the customer. (iv) The mediator shall conduct the mediation in accordance with this Section 8.1(c), the laws of California and the rules and procedures of a well-respected international dispute resolution provider. (v) The mediation will be conducted in the English language and will occur in Los Angeles County, California, unless another location is mutually agreed between ICANN, Contractor and the customer. (vi) ICANN, Contractor and the customer shall discuss the dispute in good faith and attempt, with the mediator’s assistance, to reach an amicable resolution of the dispute. (vii) ICANN shall bear all costs of the mediator. (viii) If ICANN, Contractor and the customer have engaged in good faith participation in the mediation but have not resolved the dispute for any reason, ICANN, Contractor and the customer may terminate the mediation at any time by declaring an impasse. 12 (ix) If a resolution to the dispute is reached by ICANN, Contractor and the customer, ICANN, Contractor and the customer shall document such resolution. | 9. Have known customer complaints been resolved to the CSC's satisfaction? ANSWER: Individual customer complaints and escalations, go through PTI’s customer complaint process, not to the CSC. The CSC would only escalate using the RAPs if a systemic problem was noted within the customer escalations. The CSC is made aware of all customer escalations by PTI, so that the CSC can monitor for determining if there are systemic issues. To date, the CSC has never needed to utilize the RAPs. The CSC frequently gets customers coming directly to them and the CSC redirects them to PTI’s process. 10. What types of complaints has the CSC received? ANSWER: See answer to #9 11. Has the CSC uncovered any systemic problems with the IANA Naming Function services through these complaints? If so, did PTI fix this issue? ANSWER: see answer to #9 | IFRT#7: [Fred] anyone used complaint procedure? [Amy] a few excalations that PTI notified the CSC of [Fred]: we could interview these parties to see if they were satisfied [Kim]: PTI could reach out to them and notify them of IFRT work and if open to it, PTI can introduce them to IFRT. [Fred]: we don't need to know subject of complaint; just if the process worked [Kim]: need to go back to team about this [Reference Materials] https://www.iana.org/help/complaint-procedure and https://www.iana.org/form/complaint | Tomslin & Fred
39 | Article VIII, Section 8.2 | IANA Problem Resolution Process Following the Effective Date, Contractor shall work cooperatively with the CSC to develop “Remedial Action Procedures” for the purpose of addressing Performance Issues. If the CSC determines that a Performance Issue exists, the CSC may seek resolution of the Performance Issue with Contractor, in which case Contractor shall comply with such Remedial Action Procedures if and to the extent the CSC also complies with such procedures. | answers covered by above questions | RAPs were completed by the CSC [Reference Materials] https://www.icann.org/en/system/files/files/csc-remedial-action-procedures-19feb19-en.pdf | Tomslin | [Tomslin] The existing Remedial Action Process adopted by CSC on January 2019 and by PTI on Frebruary 2019, meets the contract's requirements. https://www.icann.org/en/system/files/files/csc-remedial-action-procedures-19feb19-en.pdf
40 | Article VIII, Section 8.3 all | Notice and Mitigation Plan (a) Contractor shall promptly inform ICANN of any issue or dispute arising from its performance of the requirements and services contemplated by this Contract prior to the Complaint being escalated pursuant to Section 8.1(a), and shall agree with ICANN on a plan to resolve the Complaint. (b) If, for any reason, Contractor fails to meet any of the requirements of this Contract, Contractor shall (i) conduct an analysis of its operations to determine the root cause of such failure, (ii) develop a mitigation plan to avoid the root cause of such failure from occurring in the future, and (iii) deliver the report to ICANN upon its completion. Contractor shall modify and update any mitigation plan as directed by ICANN. | CSC's answer to above questions feeds into this contract section Attestation letter from PTI & ICANN [Tomslin] Has the CSC ever been notified of any escalation? and did PTI follow that notification up with a mitigation plan to prevent re-ocurence? | A mitigation plan: how PTI will figure out how to mitigate issues (handle issues and prevent them from repeating) IFRT#7:[Fred] how is this done today? [Amy] PTI notifies CSC mail group which I'm on about the escalation. PTI will report out on it by the next CSC meeting. So far they have always resolved before escalation is needed. [Fred] attestation from ICANN that they've been notified of escalations by PTI would suffice?
74 | Annex A, 3 (b) | Monthly Performance Progress Report Contractor shall prepare and submit reports as mutually agreed between Contractor and the CSC. | 1. Has PTI provided the CSC with reports that enable the CSC to fulfill it's remit and this section of the contract? 2. Are the reports provided in a timely manner? | [Reference Materials] https://www.iana.org/performance/csc-reports, (and indirectly, but not due to a contractual requirement, the CSC reports at https://www.icann.org/en/csc/reports). b refers to same reports as d below, but this specifies the report’s creation (A summary for the PTI/CSC reports is in this spreadsheet on tab "PTI-CSC REPORTS")
76 | Annex A, 3 (d) | Performance Standards Reports Contractor shall develop and publish performance standard metric reports for the IANA Naming Function in consultation with the CSC. The performance standards metric reports will be published via a website every month (no later than 15 calendar days following the end of each month). | answers covered by above questions | [Reference Materials] refers to same reports as b.: https://www.iana.org/performance/csc-reports, but specifies that they must be published.
69 | Annex A, 2 (a) | Service Levels Contractor shall perform the Services in accordance with the following “Service Levels”. The expectation is that Contractor will normally perform within the threshold. The thresholds will be modified over time as part of periodic reviews of the service level expectation. A subset of the following measures relate to measurement of non-routine changes where it is not applicable to set a specific threshold for performance. It is expected for measurements of non-routine process steps these will only be reported with no applicable service level expectation. | Review PTI/CSC reports to determine if SLAs are met within expected range. See "PTI-CSC REPORTS" Sheet in THIS spreadsheet for the % of metrics met by PTI from 2016 to tody. Answers are covered by above questions | [Reference Materials] PTI publishes a SLA report referred to as the CSC Report (https://www.iana.org/performance/csc-reports). (PTI's Report: and the CSC's analysis: https://www.icann.org/csc/reports). The CSC meets on a monthly basis to review this report, and determine if there are any recurring issues that need to be addressed. Should such an issue arise, the CSC would trigger the Remedial Action Procedures {RAPs). The CSC and PTI may determine that the SLA metric is not accurately reflecting the purpose of the SLA. The CSC, PTI or ICANN would trigger the Process for Amending the IANA Naming Service Level Agreements. (the RAPs and SLA Change process can be found on: https://www.icann.org/en/csc/other-procedures). Also review the CSC's homepage, from which all of these pdfs can be found: https://www.icann.org/csc
44 | Article IX, Section 9.3 (a), (b), (c) | Transition (a) Contractor shall develop and maintain, with ICANN input, a plan in place for transitioning the IANA Naming Function to a successor provider to ensure an orderly transition while maintaining continuity and security of operations, including in connection with the nonrenewal of this Contract and/or divestiture or other reorganization of PTI by ICANN as contemplated by ICANN’s Bylaws. The transition plan shall be submitted to ICANN and posted to the IANA Website within 18 months after the Effective Date. The plan shall thereafter be reviewed annually and updated as appropriate. (b) Contractor shall provide support and cooperation to ICANN, and to any successor provider of the IANA Naming Function, in order to effect an orderly, stable, secure and efficient transition of the performance of the IANA Naming Function. (c) Contractor agrees to be engaged in the transition plan and to provide appropriate transition staff and expertise to facilitate a stable and secure transition of the IANA Naming Function to a successor provider. | 12. Has the CSC reviewed PTI's Transition Plan, the plan to transition IANA services to another entity? No, as it is not mentioned in the CSC’s Charter. Partly because the CSC is clearly tasked, in their Charter, with continuing to monitor whichever entity performs the IANA Naming Functions...so if the Transition plan was invoked, the CSC would retain their same roll. However, it is a gap between the CSC Charter and the IANA Contract. Further discussion regarding the wording of “(d) ICANN, in conjunction with the CSC as necessary, shall review the transition plan at least every five years.” Kim Davies: PTI interprets this as that PTI must submit/update a Transition plan every five years, but the CSC’s role is “as necessary”, meaning they are not required to review it but only if necessary. However there is no definition of “necessary” so it may be worthwhile to understand what the community believes to be “necessary”. James: believes the community expects the Transition Plan to be published |  | Tentative: Suzanne
45 | Article IX, Section 9.3 (d) | Transition (d) ICANN, in conjunction with the CSC as necessary, shall review the transition plan at least every five years. |  | A Transition plan was completed by PTI

## IFR Scope breakdown
|  | SCOPE PER THE BYLAWS | RESOURCES | SCOPE CATEGORY
| 1 | Review and evaluate the performance of PTI against the requirements set forth in the IANA Naming Function Contract and IANA Naming Function Sow. (18.3.b*) | All Contracts found on: https://pti.icann.org/agreements | Review PTI Performance | Article IV, Section 4.5 | Article IV, Section 4.10 all | Article V, Section 5.2 (b) | Article IV, Section 4.8 all | Article VII, Section 7.2 (a) | Article VII, Section 7.2 (c) | Article VII, Section 7.3 all | Article IX, Section 9.2 all | Article IX, Section 9.3 (d) | Article X, Section 10.1 all | Article XI, Sections 11.2 | Article XI, Sections 11.4 | Article VII, Section 7.1 (a) | Annex A, 1 (a) | Annex A, 3 (f) | Annex A, 4 (a) | Annex A, 4 (b) (ii) | Annex A, 4 c | Annex A, 4 (e) | Annex A, 4 (g) | Annex A, 4 (i)
18.3.b |  |  | Amy can provide a compilation of all performance metrics on a separate spreadsheet |  | Article IV, Section 4.9 (a) | Article V, Section 5.2 (a) | Article V, Section 5.3 all | Article V, Section 5.1 all | Article VII, Section 7.2 (b) | Article VII, Section 7.2 (d) | Article IX, Section 9.1 | Article IX, Section 9.3 (a), (b), (c) | Article IX, Section 9.4 | Article XI, Sections 11.1 | Article XI, Sections 11.3 | Article XI, Sections 11.5 | Article VII, Section 7.1 (b) | Annex A, 1 (c) | Annex A, 3 (g) | Annex A, 4(b) (i) | Annex A, 4 (b) (iii) | Annex A, 4 (d) | Annex A, 4 (f) | Annex A, 4 (h)
18.3.a | 2 | Interpret the IANA Naming Function Contract’s requirements in relation to the needs of its direct customers and the expectations of the broader ICANN community (18.3.a*) | About IANA Naming Services: | Review PTI Performance | Article IV, Section 4.4 | Article IV, Section 4.7 | Article VIII, Section 8.3 all | Annex A, 1 (d) (i) | Annex A, 1 (d) (iii) | Annex A, 1 (d) (v) | Annex A, 2 (a) | Annex A, 3 (e)
|  |  | Suggest discussion with the CSC, and read their monthly reports. |  | Article IV, Section 4.6 | Article VIII, Section 8.2 | Annex A, 1 (b) | Annex A, 1 (d) (ii) | Annex A, 1 (d) (iv) | Annex A, 1 (d) (vi) | Annex A, 2 (b)
18.3.d | 3 | Review and evaluate the openness and transparency procedures of PTI and any oversight structures for PTI's performance, including reporting requirements and budget transparency (18.3.d*) | https://pti.icann.org/ | Review PTI Oversight | Article IV, Section 4.3 (d) | Article VI, Section 6.1 (c) | Article VII, Section 7.1 (a) | Annex A, 3 (b)
|  |  | PTI Finances |  | Article VI, Section 6.1 (a) | Article VI, Section 6.1 (d) | Article VII, Section 7.1 (b) | Annex A, 3 (c)
|  |  | Audit Committee Charter |  | Article VI, Section 6.1 (b) | Article VI, Section 6.1 (e) | Article X, Section 10.2 | Annex A, 3 (d)
PTI Board Meetings
Director's list
PTI Board of Directors' Code of Conduct
Conflicts of Interest Policy
Expected Standards of Behavior
18.3.e | 4 | Review and evaluate the performance and effectiveness of the Empowered Community (EC) if applicable actions have been taken by the EC (18.3.e*) | The Empowered Community has approved all PTI Operational Plans and Budgets to date. All activities for EC. | Review PTI Oversight
18.3.f | 5 | Review the IANA naming function SLAs for performance period corresponding with the period being reviewed by this Periodic IFR as compared to the performance period prior (will not be applicable to “First Periodic Review”). (18.3.f*) | NOT APPLICABLE TO FIRST IFR
18.3.g | 6 | Review and evaluate systemic issues impacting PTI’s performance (18.3.g*) | This is monitored by the CSC, and to date, no systemic issues have been identified. However, it was determined that during the IANA Stewardship Transition, three sets of SLAs did not correctly reflect the monitored process, and these SLAs have been or are to be changed: | Review PTI Performance
COMPLETED: Change to Technical Checks (did not require Public Comment) went into effect 01 July 2019
APPROVED, PENDING IMPLEMENTATION: Publishing LGRs Public Comment at
IN PUBLIC COMMENT NOW: Changes to ccTLD Creation & Transfer:
18.3.h | 7 | Consider input from the CSC and the community (through a Public Comment session) regarding PTI’s performance as laid out in the IANA Naming Function Contract & SOW (18.3.h & i*) | Review Team's Draft Report and later, Initial Report to go to Public Comment | Review PTI Oversight
|  |  | Two Reviews have recently completed regarding the CSC: |  | Article VIII, Section 8.3 all
1. Review of the CSC's Charter Wiki:
Final Report
2. CSC Effectiveness Review Wiki
Final Report
18.3.i | 8 | Identify processes/areas for improvement in (18.3.j*): | Review Team Deliverable | Review PTI Processes | Article IV, Section 4.3 (d)

## PTI-CSC Reports
Monthly PTI performance report (by the 12th or next business day to ICANN/CSC)
IANA Naming Function Contract found at https://www.icann.org/iana_pti_docs/151-iana-naming-function-contract-v-30sep16, Section 7.2.b
PTI's versions are at: https://www.iana.org/performance/csc-reports
The CSC's versions are at: https://www.icann.org/csc/reports
DATE | SLAs Met | Missed SLAs Explanation | Escalations | SLA Changes via the SLA Change Process: https://www.icann.org/en/system/files/files/iana-naming-function-sla-amendment-process-28mar19-en.pdf
October 2016 | 95.9% | Missed service level agreements were satisfactorily explained and the CSC has determined that these exceptions were no cause for concern. No persistent problems were identified and no further action is needed. Missed service level agreements that were satisfactorily explained and are not an indication of a persistent issue: a) Technical Checks (Retest and Supplemental) b) ccTLD Delegation c) Manual Lodgement
November 2016 | 99% | Missed service level agreements were satisfactorily explained and the CSC has determined that these exceptions were no cause for concern. No persistent problems were identified and no further action is needed. Missed service level agreements that were satisfactorily explained and are not an indication of a persistent issue: a) Technical checks b) Manual lodgment
December 2016 | 99.4% | Missed service level agreements that were satisfactorily explained and are not an indication of a persistent issue: a) Technical check (first) b) Technical check (re-test)
January 2017 | 99.5% | Missed service level agreements were satisfactorily explained and the CSC has determined that these exceptions were no cause for concern. No persistent problems were identified and no further action is needed. Missed service level agreements that were satisfactorily explained and are not an indication of a persistent issue: a) Manual lodgment time b) Technical check (supplemental)
February 2017 | 99.5% | Missed service level agreements were satisfactorily explained and the CSC has determined that these exceptions were no cause for concern. No persistent problems were identified and no further action is needed. Missed service level agreements that were satisfactorily explained and are not an indication of a persistent issue: a) Manual lodgment time (routine/non-technical and ccTLD creation/transfer) b) Validation and reviews (ccTLD creation/transfer) Please refer to the Exceptions and Narrative for Reporting Period section of the February 2017 PTI performance report for more detailed explanations of these missed SLAs
March 2017 | 98.6% | The single missed service level is subject to a CSC recommendation that would recategorize this month's performance for this metric as 'met'. The CSC notes that PTI will be investigating this issue further and reporting back to the CSC on their findings. On the evidence so far, the CSC does not regard this as a persistent problem or a cause for concern. Missed service level agreement was: a) Technical Check (Retest) Please refer to the Exceptions and Narrative for Reporting Period section of the March 2017 PTI performance report for a more detailed explanation of this missed SLA. In addition, PTI reported that it discovered two change types (revocations and root server changes) that had been underreported in previous monthly reports. The CSC found the explanation to be satisfactory and thanked PTI for bringing this information forward. The CSC notes that these change types are infrequent manual work items (category v in terms of the agreed SLE) and for which performance metrics have not been established. The CSC discussed how to deal with this on a going forward basis, including whether to include the issue in the next review of the SLE’s. Please see the addendum to the March 2017 PTI performance report for more details.
April 2017 | 98.6% | The single missed service level is subject to a CSC recommendation that would recategorize this month's performance for this metric as 'met'. On the evidence so far, the CSC does not regard this as a persistent problem or a cause for concern. Missed service level agreement was: a) Technical Check (Retest)
May 2017 | 100%
June 2017 | 100% |  | To-date, PTI has notified the CSC of 2 escalations. The CSC took note of the escalations and has asked that PTI keep the CSC informed with respect to their resolution.
July 2017 | 100% |  | Escalations from June 2017 resolved
August 2017 | 100%
September 2017 | 100%
October 2017 | 96.9% | ) Technical Check (First) b) Technical Check (Retest) Regarding the Technical Check (First) missed service level, PTI has previously informed the CSC that this SLA is missed due to an historic design decision to process these checks in series and while the active performance of the technical test itself does not exceed the SLA, the SLA is exceeded because some requests were queued waiting to be performed. The next revision of RZMS will have the technical check portion substantially rewritten and will allow greater parallelization of the testing being performed. Regarding the Technical Check (Retest) missed service level is subject to a CSC recommendation that would re-categorize this month’s performance for this metric as ‘met’ as well. On the evidence so far, the CSC does not regard this as a cause for concern.
November 2017 | 96.9% | a) Technical Check (Retest) b) Technical Check (Supplemental) Both the Technical Check (Retest) and the Technical Check (Supplemental) missed service levels are subject to a CSC recommendation that would re-categorize this month’s performance for these metrics as ‘met’ as well. On the evidence so far, the CSC does not regard this as a cause for concern. | During this reporting period, PTI has notified the CSC of two escalations. The CSC has discussed the escalation and determined that it is not a persistent performance issue or systemic problem associated with the provision of the IANA naming services.
December 2017 | 100% |  | Escalations from June 2017 resolved
Jan 2018 Performance | 100%
Feb 2018 Performance | 96.9% | a) Technical Check (Retest) b) Technical Check (Supplemental) Both the Technical Check (Retest) and Technical Check (Supplemental) missed service levels are subject to a CSC recommendation that would re-categorize this month’s performance for these metrics as ‘met’. On the evidence so far, the CSC does not regard this as a cause for concern.
Mar 2018 Performance | 95.3% | Technical Check (Retest) b) Technical Check (Supplemental) c) Validation and Reviews (ccTLD Creation/Transfer) The first two missed service levels are subject to a CSC recommendation that would re-categorize this month’s performance for these metrics as ‘met’. The third metric would require a year’s worth of data under the recommended change, which is not yet available. On the evidence so far, the CSC does not regard this as a cause for concern. | At its 16 April meeting the CSC has adopted and agreed with PTI on the Remedial Action Procedures (RAP) as foreseen under the CSC charter. The RAP are available at: https://www.icann.org/en/system/files/files/csc-remedial-action-procedures03mar18-en.pdf
Apr 2018 Performance | 95.3% | a) Technical Check (First) b) Technical Check (Retest: Routine) c) Technical Check (Retest: ccTLD Creation/Transfer) Regarding the Technical Check (First) missed service level, PTI has previously informed the CSC that this SLA is missed due to the sequential performance of technical checks where the active performance of the technical test itself does not exceed the SLA but rather the SLA is exceeded because the requests were sequentially queued waiting for the technical check to be performed. The next revision of RZMS will have the technical check portion substantially rewritten that will allow greater parallelization of the testing being performed, which would re-categorize this month’s performance for this metric as ‘met’. PTI expects to deliver the RZMS revision of the technical check module for Q1 2019. The remaining missed service levels, b) Technical Check Retest: Routine and c) Technical Check: ccTLD Creation/Transfer, are subject to a CSC recommendation that would recategorize this month’s performance for these metrics as ‘met’. Please refer to the Exceptions and Narrative for Reporting Period section of the April 2018 PTI performance report for a more detailed explanation of the missed SLAs. On the evidence so far, the CSC does not regard the missed service levels as a cause for concern. | Escalations from June 2017 resolved
May 2018 Performance | 100%
Jun 2018 Performance | 98.4% | Technical Check (First) - Routine
Jul 2018 Performance | 98.4% | Technical Check (Retest) – ccTLD Creation/Transfer
Aug 2018 Performance | 98.4% | Technical Check (Retest) – Routine
Sep 2018 Performance | 100%
Oct 2018 Performance | 100%
Nov 2018 Performance | 98.4% | Technical Check (Supplemental) – Routine (Technical)
Dec 2018 Performance | 100%
Jan 2019 Performance | 98.4% | a) Validation and Reviews (ccTLD Creation/Transfer)
Feb 2019 Performance | 100%
Mar 2019 Performance | 98.4% | The single missed service level is subject to a CSC recommendation that would recategorize this month's performance for this metric as 'met'. On the evidence so far, the CSC does not regard this as a persistent problem or a cause for concern. Technical Check (Retest)
Apr 2019 Performance | 100%
May 2019 Performance | 100%
Jun 2019 Performance | 100%
july 2019 | 100% |  |  | Technical Check – Retest and Supplemental: Amended SLAs became effective 01 July 2019.
august 2019 | 98.4% | • Technical Check (Retest)
September 2019 | 100%
October 2019 | 98.4% | Technical Check (Retest) – Routine This metric failure is related to time spent waiting for responses from name servers that were ultimately unreachable for each of the technical check runs. PTI will explore how to further refine how the technical checks are performed to reduce the end-to-end processing time for unresponsive name servers, by improving algorithms to quickly identify servers as unreachable and then not retrying them later in an individual tech check test run.
November 2019 | 100%
December 2019 | 100% |  |  | LGR Metrics applied 01 January 2020
January 2020