## ATRT1
Questions from ATRT2 regarding implementation of recommendations of ATRT1
ATRT1 Recommendations | Implementation Assignments |  | A. What was the baseline? | B. What did s/he understand the recommendation to be? | C. What did s/he understand the underlying issue to be that led to the recommendation? | D. What did s/he understand the desired outcome to be from the recommendation? | E. How did s/he implement the recommendation? What options were considered and how was the actual option chosen for implementation? | F. Percentage/portion that is complete? | G. Does s/he believe ICANN fully implemented the recommendation? If not, why not? If not, what parts were not implemented, and why not? | H. Did s/he run into any new or unforeseen problems or issues while implementing the recommendation? (i.e. scope increase, costs, legal, resources, timing) | I. Did s/he identify additional opportunities for improvement by virtue of the implementation of these recommendations? | J. What has been the outcome and effect both inside ICANN and external to ICANN as a result of the implementation of the recommendation? | K. What has been the feedback both inside ICANN and external to ICANN as a result of the implementation of the recommendation? | L. How does s/he feel that ICANN has improved as a result of the implementation of the recommendation? | M. What were the dependencies as seen from each group involved in implementation? | N. In view of ATRT1 what changes in workflows and/or organization where undertaken? | Additional Information
Board Operations, Composition & Review of Decisions
1. a-d Mechanisms for identifying collective Board skillset; benchmarking Board/BGC skillsets; tailoring & consulting on skills; reviewing for each NomCom; publishing outcomes & requirements with NomCom’s notice. | Board/BGC | Bruce Tonkin
| NomCom | Adam Peake (2011 Chair); Vanda Scartezini (2012 Chair) | VS - The baseline was to guarantee the following points: a) Candidate’s access to very clear information about the position requirements b) Give to all ACs and SOs and its constituencies the opportunity to define which will be the better board candidate from their particular point of view c) Board’s opportunity to analyze each year what is lacking (or will be with the termination of some members terms) as necessary knowledge among its members that a new member could contribute. d) Orientation to NOMCOM analysis of each candidate to guarantee the choice among all candidates will fulfill the best as possible the requirements for such position that year. AP – NomComs for some years (probably since 2005 or 2006), developed a "leadership positions" document describing the positions and candidate profile for each. The document (see <http://nomcom.icann.org/positions-2011.htm> for 2011 version) was updated based on discussions with various constituencies, and as a general practice a draft (or the previous year's version) was sent to the entities receiving NomCom appointees for comment. NomCom procedures <http://nomcom.icann.org/procedures-2011.htm> updated each year also contain similar information. This document covers all positions, ATRT 1 recommendations addressed Directors. | VS - The recommendation is asking to NOMCOM to create adequate actions to guarantee the points above will be implemented, used giving the expected results for the community, candidate and the Board itself. AP - As it says: identify the candidate profile, ensure that profile was informed by the relevant parties (the ICANN community and Board), and there was some degree of accountability in how the selections met the profile. | VS - I believe there was several occasions when the selected board members brought not what is needed inside the Board, neither responded to the community expectation for being there. Analyzing the historical reality of not adequate members seating inside the Board I believe led the WG to propose this task to NOMCOM, since it is NOMCOM task to select independent Board members, without the particular focus of each constituency. AP - That selected candidates better met ICANN's needs, through process better understood, better managed, etc | VS - The desired outcome I believe was to have a Board member with the adequate profile demanded by the community and the Board among those applied, as well as, to give candidates the opportunity to apply for a more matching position regarding their own profiles. AP - Accountability and transparency, with an emphasis on transparency. | VS - In 2012 we implemented the following actions: a) Formal consultations during all ICANN meetings with all ACs (GAC declined to have such conversation in 2012) and SOs and its constituencies during the general assembly the previous year ( 2011) to identify all the characteristics and publish it. b) Formal meeting with Board chair and CEO to collect their own opinion about Board member profile needed for the next selection. c) Meeting with General Counsel to guarantee all members inside NOMCOM will understand the requirements for a Board position and other legal issues. d) Meeting with the BGC to demand and receive the specific characteristics already existed inside the Board, which will be missing that next year and which are lacking and important for the Board. e) Publishing the Identified and checked profile characteristics, as a guideline for candidate application information. f) Publishing and up to date the TIMELINE for NOMCOM activities during the whole cycle of NOMCOM to guaranty transparency and facility to community and the candidates to follow. g) Meeting with the company selected to help NOMCOM in a professional analysis for pre selected board candidates, related to their personal and professional characteristics in order to debate with them on the main characteristics we were looking for and how their analysis will help the members to select the best candidates. h) Similar meeting as in a) to recheck with the AC+SOs + constituencies during the first meeting of the year (2012) to orient NOMCOM’s members on the selection process. i) After the selection process, a Report was made and published matching matrix with the information asked by the community and Board and what the selected persons’ profiles for the Board member accomplished such requirements. j) At the general Assembly in 2012 meeting again with each AC, SOs and its constituencies in order to give them feedback about the NOMCOM activities and how we respected their requirements for the Board positions (and for their own positions) The report was published and announced during the Public Forum at the General Assembly on Toronto 2012 meeting. AP - Workshops with the community (i.e. workshops on the ICANN meeting schedule, and meetings with GNSO constituencies, SO and AC, including GAC) and with the Board and Board Governance Committee seeking input on the candidate profile, on anticipated challenges ICANN would face and likely skills useful in addressing those challenges. Meetings with Board and Board Governance Committee also discussed internal board processes (example, board committees), experience gaps, etc. | VS - 100% - NOMCOM has implemented all. (see response to E.) AP - Initially behind schedule, NomCom on 2011 implemented some improvements ahead of schedule and recommendations. Seems most of the recommendations were met by the time the 2012 committee began work. | VS - From this specific recommendation NOMCOM has implemented all, BGC have done its part, all SO and its constituencies had sent their contributions regarding the profile requirements they believe would be good for ICANN. The only missing recommendation was from GAC. AP - Reviewing the selections, particularly against the ideal candidate profile, experience gaps etc, thankfully hasn't been carried out to the extent I think the ATRT intended. The original recommendation was too ambitious, example: without knowing the candidate pool the NomCom selected from, it would be impossible to review/justify selections. | VS - No, just the opposite, the implementation of such recommendations brought more facilities for NOMCOM analysis on candidates profile to matching specific requirements, the participation of the AC and SOs and its constituencies in suggesting specific profile characteristics for board members they believe was missing and clarity and transparency to candidates to follow the process and matching their profiles with the required ones. AP - No. But the CFO was positive about funds being made available for expenses necessary to meet ATRT recommendations, felt this was a positive by ICANN. | VS - Yes, I believe this is a constant improvement process and for instance, to have a more standard matrix to identify profile characteristics and do matching making after the process is done , may help the community to easily identify which is the expectations from new board members, and help the Board to analyze their performance. AP - Process of understanding candidate profiles now taken more seriously by the Board/GNSO/ccNSO/ALAC. Example, in the past, each had been asked to comment on the "leadership" document, given an early opportunity to edit, etc. They tended not to be very diligent in their response. New processes, mainly ATRT inspired, have largely fixed that. General feeling that the NomCom needn't be so obsessed by secrecy was positive. Some of core ATRT recommendations were already NomCom practice, but the ATRT gave impetuous to take improvements seriously. | VS - Inside ICANN was a clearer vision about the NOMCOM process, the implementation of review performance of Board members and the needs required for fulfill the knowledge inside the Board. From outside, a clear view of the selecting process, also a clearer view on what was the expectation for someone to become a Board member and the sense of a improvement regarding transparency in ICANN relationship with the community and the external world. AP - Candidates have a better understanding of what's required. A better knowledge of what the board needs (both the skills of a candidates and the "gaps" in the board's collective skillset) should mean the NomCom can make better judgment. Indirect benefit has been that the improved information about the desired candidate profile has been very useful in helping a professional recruitment company help NomCom identify potential candidates. Used in 2011, and more effectively being used now in 2013 (learnt from 2011, basically, but the candidate profiles, skillset/skill-gap etc very useful.) | VS - One very positive feedback about the easiest way to an outsider see if they match or not the requirements to seat at ICANN Board, and also the members of AC and SO recognized they were listened about their concerns and requirements regarding new board members. AP - Positive, both from the ICANN community and candidates (to the extent one can tell.) | VS – Yes, some interesting improvements can be recognized: a) Improvement on BGC organization inside the Board b) Board improving its internal management performance, individually and collectively; c) More participation from AC & SOs related to the choice of new board members. | VS - NOMCOM had the support of the entire staff involved on such implementation including the BGC, the AC, SOs and its constituencies. I believe was a cooperative task, as such, with good results. | VS - Related to NOMCOM some: a) Build a new process of publish and update the TIMELINE during the activities of NOMCOM, be involved with AC and SOs and its constituencies in formal meetings; b) Report back to the AC and SOs and its constituencies in formal meetings c) Become more transparent regarding community. d) Report and publish the Matching Matrix with the requirements and each selected profile for Board member AP - Little, most was almost standard practice, more a matter of rethinking and improving (significantly improving) what was being done rather than major change. The outcome is major, however.
| Staff: Board Support (Legal); NomCom Support | Amy Stathos; Samantha Eisner; Diane Schroeder; Olof Nording | Informal meetings between the Board Chair and the NomCom Chair periodically took place to discuss skillsets for the Board. Board training and induction programs were in place, although not necessarily regularized or embedded in the Board’s Standard Operating Procedures. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. Regarding the NomCom, it was generally understood that underlying this recommendation were concerns of undue secrecy in the NomCom process and requests for more expansive explanations of NomCom selections. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. Regarding the NomCom, it was generally understood that improved community confidence in the NomCom process was a desired outcome. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. Given the independence of the NomCom, implementation was driven by the Committee and the Board. NomCom Chairs and members took the lead in implementing the recommendations in practice as well as manifesting changes in core NomCom documents. The implementation actions are presented in an annex (document linked from the NomCom front page), to which should be added recent initiatives by the 2013 NomCom, notably a public report card issued after each meeting and holding public NomCom meetings at ICANN meetings. Regarding implementation options, a case in point was whether any changes of the ICANN Bylaws were called for - the Board found it preferable to issue guidelines on transparency rather than modifying or adding any Bylaws provision. | Please see 2012 Implementation Summary re: ATRT Rec. Nos. 1 and 2 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). In addition, each independent, annual NomCom may consider further improvements, as is the case with NomCom 2013. | ICANN addressed all portions of these recommendations in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) In addition, each independent, annual NomCom may build upon this implementation to consider further improvements, as is the case with NomCom 2013. | ICANN has not identified any material unforeseen issues during implementation of these recommendations. Regarding NomCom work, well-known particular aspects of the NomCom called for consideration, such as the limited continuity from one Committee to the next and the strict timeline for appointments, but these were clearly not unforeseen issues. | ICANN has not identified any additional material opportunities during implementation of these recommendations. Regarding the NomCom process, it is observed that advice on skillsets from the entities receiving NCAs is often provided late. Additional prompting of these entities well in advance about the need to provide such advice already at the launch of each NomCom may improve that. | The Board now regularly considers both existing and desired skillsets for new members and has developed a more open dialogue with the NomCom. Training continues to be a focus for the Board. Increased visibility into the NomCom's activities has been a positive effect. | Increased visibility into the NomCom's activities has been a positive effect. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | The Board and the NomCom generally were dependent upon each other for implementation, as well as on support from staff. | Standard Operating Procedures for annually identifying Board member skillsets, and providing guidance to the NomCom, are now in place. See annex, core documents and timeline on the NomCom web site, http://nomcom.icann.org/ | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
2. Regularly reinforce/review training & skills building. | Board/BGC | Bruce Tonkin
| Staff: Board Support (Legal); NomCom Support | Amy Stathos; Samantha Eisner; Diane Schroeder | Informal meetings between the Board Chair and the NomCom Chair periodically took place to discuss skillsets for the Board. Board training and induction programs were in place, although not necessarily regularized or embedded in the Board’s Standard Operating Procedures. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. Regarding the NomCom, it was generally understood that underlying this recommendation were concerns of undue secrecy in the NomCom process and requests for more expansive explanations of NomCom selections. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. Regarding the NomCom, it was generally understood that improved community confidence in the NomCom process was a desired outcome. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. Given the independence of the NomCom, implementation was driven by the Committee and the Board. NomCom Chairs and members took the lead in implementing the recommendations in practice as well as manifesting changes in core NomCom documents. The implementation actions are presented in an annex (document linked from the NomCom front page), to which should be added recent initiatives by the 2013 NomCom, notably a public report card issued after each meeting and holding public NomCom meetings at ICANN meetings. Regarding implementation options, a case in point was whether any changes of the ICANN Bylaws were called for - the Board found it preferable to issue guidelines on transparency rather than modifying or adding any Bylaws provision. | Please see 2012 Implementation Summary re: ATRT Rec. Nos. 1 and 2 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). In addition, each independent, annual NomCom may consider further improvements, as is the case with NomCom 2013. | ICANN addressed all portions of these recommendations in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) In addition, each independent, annual NomCom may build upon this implementation to consider further improvements, as is the case with NomCom 2013. | ICANN has not identified any material unforeseen issues during implementation of these recommendations. Regarding NomCom work, well-known particular aspects of the NomCom called for consideration, such as the limited continuity from one Committee to the next and the strict timeline for appointments, but these were clearly not unforeseen issues. | ICANN has not identified any additional material opportunities during implementation of these recommendations. Regarding the NomCom process, it is observed that advice on skillsets from the entities receiving NCAs is often provided late. Additional prompting of these entities well in advance about the need to provide such advice already at the launch of each NomCom may improve that. | The Board now regularly considers both existing and desired skillsets for new members and has developed a more open dialogue with the NomCom. Training continues to be a focus for the Board. Increased visibility into the NomCom's activities has been a positive effect. | Increased visibility into the NomCom's activities has been a positive effect. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | The Board and the NomCom generally were dependent upon each other for implementation, as well as on support from staff. | Standard Operating Procedures for annually identifying Board member skillsets, and providing guidance to the NomCom, are now in place. See annex, core documents and timeline on the NomCom web site, http://nomcom.icann.org/ | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
3. Increase transparency of NomCom’s deliberations & decision-making process. ASAP but starting no later than next NomCom. | Board/BGC | Bruce Tonkin
| NomCom | Adam Peake (2011 Chair); Vanda Scartezini (2012 Chair) | VS - The base line was to bring the transparency demand from ATRT1 to the NOMCOM too. AP - Standard practice, NomCom would meet with each GNSO constituency (they send delegates to the NomCom), SO and AC, and usually the Board (or some members of) and GAC to explain the process for the year, ask for comment. (this was a useful exercise, but became so common place I don't think it was taken seriously.) | VS - Find ways to improve the transparency without compromise the privacy of candidates information. AP - To better inform community (and potential candidates) about NomCom's work, about what it was seeking in candidates and why. | VS - NOMCOM was secluded from the community till 2010 and with ATRT starts to open in 2011. Since NOMCOM responsibilities are so relevant bring so many leadership positions to ICANN looked for the WG as necessary to have a more clear vision about how the NOMCOM worked, are their members independent? Community wants to know. AP - NomCom considered a "black-box", overly concerned with confidentiality. Needed to be fixed. | VS - The desire was to have the most open conditions as possible for NOMCOM AP - ICANN community to have a better understanding of how the NomCom went about its work. Sense that the NomCom would then be more accountable for its selections (which I think difficult to do.) Make NomCom more professional. | VS – the following implementations were done during 2012 term. a) Publishing and up to date the TIMELINE for NOMCOM activities during the whole cycle of NOMCOM to guaranty transparency and facility to community and the candidates to follow b) Formal consultations during all ICANN meetings with all ACs and SOs and its constituencies during the general assembly the previous year to identify all the profiles needed for the Board and their own leadership positions. Publish it. c) Publishing all the presentations to ACs and SOs, d) Have a public meeting regarding ATRT and all other relevant aspects of NOMCOM process during ICANN formal meeting during 2012. e) Formal meeting with Board chair and CEO and the BGC to collect their own opinion about Board member profile needed for the next selection. f) Meeting with General Counsel to guarantee all members inside NOMCOM will understand the requirements regarding privacy of candidate’s information and what we could be open to the community. g) Publishing the Identified and checked profile characteristics, for all leadership positions as a guideline for candidate application information. h) Similar meeting as in a) to recheck with the AC+SOs + constituencies during the first meeting of the year (2012) to orient NOMCOM’s members on the selection process. i) After the selection process, a FINAL REPORT was written and published before the General Assembly on Toronto, October 2012. http://nomcom.icann.org/nomcom-final-report-08oct12-en.pdf j) At the FINAL REPORT item 6 is possible to find all STATISTCS related to NOMCOM 2012 – number of the candidates, gender, geographic distributions in clear graphics. k) Inside the FINAL REPORT on item 11 MATCHING MATRIX with the information asked by the community and Board and what the selected persons’ profiles for the Board. l) At the general Assembly in 2012, formal meetings again with each AC, SOs and its constituencies in order to give them feedback about the NOMCOM activities and how we respected their requirements for the Board positions, and for their own positions m) On item 12 NOMCOM 2012 have suggested some PROCEDURES RECOMMENDATIONS where there is suggestions for General rules of participation at NOMCOM; Ethics; NOMCOM work and Selecting Process and Logistics. n) At the end of the process I, as chair, personally wrote a Thank you email to all candidates also encouraging them to reapply since the requirements change each year and their chances can be better next time. The report was published and announced during the Public Forum at the General Assembly on Toronto 2012 meeting. AP - 2011: Workshops with the community. Quite successful. Attempt to improve communication throughout the process with the community (more email to lists, a blog), and with candidates (more information about the process, some communication to tell them what stage the process was at. In 2011 these communications efforts were mostly not realized (ideas that were not put into practice.) Note: transparency is time consuming for volunteers. Writing to people, publishing, etc. And these are additional to an already busy (later in the process, selection period of weekly calls) process. But it has been worthwhile as improvements in 2013 are showing. | VS - 100% - We did all we have proposed to do during our Term (see response to E. ) AP - Now, 100%. | VS - The new Recommendation we posted in our FINAL REPORT and sent it also to BGC; annexed to this document is the full recommendations for the NOMCOM 2012. Some of them not yet analyzed and/or implemented, and could be analyzed now by the ATRT2 (see http://nomcom.icann.org/nomcom-final-report-08oct12-en.pdf). AP - Yes. And it improves to this day (example of the monthly report cards from the NomCom.) | VS - No, transparency brings more quality to the process, not problems. We did not break any candidate privacy and could finalize the whole election process timely, in time to have the selected new member participating on the BOARD retreat in September 2012. | VS - I believe there is always room to improve transparency. For instance: since my participation on NOMCOM in 2011 I started, personally to send a report to my community (SSAC) each month relating what we were doing, but respecting all data related to any candidate. As a Chair, had no community to respond back, but some members also did report to their community monthly. NOMCOM 2013 one of our colleagues offered to write a standard report and send to us members to delivery to our communities (my community I respond this year is LACRALO, and since there are several members not proficient in English I also translated to Spanish for them to make sure they can follow the process). | VS - The rethinking about the selection of the chair elect was a positive thing from inside ICANN and the community also recognized that. Externally was more difficult to see, it will be reflected on the number of new candidates from external community that can be informed about the transparency of NOMCOM etc. AP - Yes. Feel there is improved confidence in the NomCom. And the NomCom has learnt that so long as it protects candidate information, almost everything else can be shared / should be shared. Transparency become a NomCom goal, this was something I wanted in 2011, and it's being implemented I think quite successfully by the 2013 committee (it does need work, and the incoming chairs should be reminded that they should seek to make improvements. And that as volunteers, the outcomes only as good as the time/energy people willing to put in.) | VS - For inside ICANN was a positive feedback coming from BGC< BOARD and AC and SOs and its constituencies related to some improvements we had made for transparency , but from other side and even with the movement to be much more transparent in process, the needs to have more transparency was there as always happens when people identify they can have more information about something, people also complained that could be done more about transparency! And they are right! What is very good as a feedback, I believe, encouraging next group to make more improvements. From outside ICANN I heard positive things from selected board members about the process and its transparency and information as well as from several candidates not selected. AP - Positive | VS - Accepting feedback from the community, changing internal processes to help NOMCOM to become more transparent. | VS - This is a very collaborative process and the participation of all staff, Board and NOMCOM was quite important to allow these steps forward to be taken. | VS - During 2012, we, as a whole participants in the NOMCOM realized several issues needed to be clearer to members and process must be improved related to them; as commented in response to other questions, NOMCOM had published in its FINAL REPORT (http://nomcom.icann.org/nomcom-final-report-08oct12-en.pdf) | http://nomcom.icann.org/nomcom-final-report-08oct12-en.pdf
| Staff: Board Support (Legal) NomCom Support | Amy Stathos; Samantha Eisner; Olof Nording | Prior to publication of the ATRT1 Final Report, the NomCom regularly maintained a web page where it posted documents related to its processes (http://nomcom.icann.org). Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. No. 3 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN addressed all portions of this recommendation in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | ICANN has not identified any material unforeseen issues during implementation of this recommendation. | ICANN has not identified any additional material opportunities during implementation of this recommendation. | People have recognized and appreciated the added transparency of the NomCom processes while recognizing the need for confidentiality of the specific candidates. | Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | The Board and the NomCom generally were dependent upon each other for implementation, as well as on support from staff. | The NomCom has adopted some standard practices and the Board has imposed some transparency guidelines that all NomComs are required to follow. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
4. Continue to enhance Board performance & work practices. | Board/BGC | Bruce Tonkin
| Staff: Board Support (Legal) | Amy Stathos; Samantha Eisner; Diane Schroeder | ICANN has not identified any baseline in place from which this recommendation could be measured. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. No. 4 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN addressed all portions of this recommendation in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) |  | All opportunities to continue to enhance Board performance will be implemented as feasible, whether identified in the implementation plans or not. | The Board has a renewed focus on formalizing and documenting standard processes. | Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No specific dependencies were identified. | In part due to the recommendations of the ATRT1, the Board has adopted changes to its work practices that include development of a procedural manual, use of informational calls, designation of Board topic leads and other mechanisms to enhance the efficiency and effectiveness of the Board. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
5. Implement compensation scheme for voting Board Directors. | Board/BGC | Bruce Tonkin
| Staff: Board Support (Legal) | Amy Stathos; Samantha Eisner | The Board had begun considering compensation for its members in response to the Board Review Report by the Boston Consulting Group. In August 2010, after public comment, the Board approved compensation for the Board Chair only and deferred consideration of compensation for other Board members. (See http://www.icann.org/en/groups/board/documents/resolutions-05aug10-en.htm#5.) | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. No. 5 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) | ICANN addressed all portions of this recommendation in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | There were significant legal and procedural hurdles that needed to be overcome involving money, time and resources, in order to ensure this was dealt with properly and in accordance with non-profit requirements. | ICANN has not identified any additional material opportunities during implementation of this recommendation. | Board members now have the opportunity to elect compensation. This has increased the annual Board budget by a material amount. |  | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | This implementation was dependent upon following all proper procedural and legal requirements. | A standard process has been put in place to allow Board members to elect to receive compensation; the Board member election is regularly published. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
6. Clarify distinction between PDP & executive function issues. | Board/BGC | Bruce Tonkin
| Staff: Board Support (Legal) | Amy Stathos; Samantha Eisner | ICANN has not identified any baseline in place from which this recommendation could be measured. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. No. 6 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). While not required for the completion of this recommendation, the discussion about the distinction between policy and implementation issues is still ongoing. | ICANN addressed all portions of this recommendation in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) Completion of this implementation project inspired further discussion about the distinction between policy and implementation issues that is still ongoing within the community, most recently in a public session in Beijing. |  | Because of the work undertaken for Recommendation 6, ICANN also published a paper on the Community Input and Advice Function (http://www.icann.org/en/news/in-focus/accountability/input-advice-function-24sep12-en.pdf), which has led to an ongoing dialogue in the community. There were sessions in both Toronto and Beijing on this topic, and ICANN staff has since produced a paper for public comment on Policy v. Implementation (http://www.icann.org/en/news/public-comment/policy-implementation-31jan13-en.htm) to help frame and move the discussion forward. | Community now has a defined set of terms to use when discussing and categorizing Board actions. The follow-on work has reinitiated a challenging debate within the community regarding policy vs. implementation roles and how the community provides advice to the Board. | Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No specific dependencies were identified. | Every substantive action taken by the Board is now accompanied by an identification of the type of action and the consultation expected or conducted prior to Board decision. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
7.1 Promptly publish all appropriate Board materials related to decision-making processes. | Board/BGC | Bruce Tonkin
| Staff: Board Support (Legal) | Amy Stathos; Samantha Eisner | As of the 22 April 2010 Board Meeting, all board briefing materials have been posted contemporaneously with approval of minutes, subject to appropriate redactions. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. No. 7.1 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN addressed all portions of this recommendation in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Additional resources are required to review all Board briefing materials for confidential information before posting, but they were anticipated in the implementation plans (see www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf). | ICANN has not identified any additional material opportunities during implementation of this recommendation. | People have greater transparency into Board materials. Further, see response to question H. | Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. | No specific dependencies were identified. | Board materials are now posted along with approved minutes for each meeting of the Board and the New gTLD Program Committee as a standard operating procedure. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
7.2 Publish rationale for Board decisions and for accepting or rejecting public & community input. | Board/BGC | Bruce Tonkin
| Staff: Board Support (Legal) | Amy Stathos; Samantha Eisner | Prior to January 2011, the Board had not regularly adopted formal rationale statements for its decisions. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. No. 7.2 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN addressed all portions of this recommendation in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | The development of rationales has, at times, increased the time needed for Board consideration of items. For major Board decisions, there has been significant costs incurred in both money and resources to develop the rationales. | ICANN has not identified any additional material opportunities during implementation of this recommendation. | People have more information as to the bases for Board decisions. Sometimes the complexity of the resolutions has decreased because background information can now be provided through the rationale. Further, see response to question H. | Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No specific dependencies were identified. | Rationales are now posted for every substantive decision of the Board and the New gTLD Program Committee as a standard operating procedure. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
8. Publish redaction conditions. | Board/BGC | Bruce Tonkin
| Staff: Board Support (Legal) | Amy Stathos; Samantha Eisner | Redaction conditions specifically relating to Board briefing materials were not posted prior to publication of the ATRT1 Final Report. However ICANN's Documentary Information Disclosure Policy redaction conditions were available. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. No. 8 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN addressed all portions of this recommendation in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | ICANN has not identified any material unforeseen issues during implementation of this recommendation. | ICANN has not identified any additional material opportunities during implementation of this recommendation. | Publishing the redaction conditions for Board briefing materials is meant to provide the community with a better understanding as to why certain information is held as confidential. | Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No specific dependencies were identified. | Redaction conditions are adhered to with every posting of Board briefing materials as a standard operating procedure. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
19. Publish translated Board material within 21 days | Board/BGC | Bruce Tonkin
| Staff: Board Support (Legal); Communications | Amy Stathos; Samantha Eisner; Christina Rodriguez | Translations of Board Resolutions and Minutes were not being published before the ATRT1 Final Report was published. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. No. 19 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN addressed all portions of this recommendation in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | There is now ongoing additional cost for the additional translations, but those were anticipated in developing the implementation plans (see www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf). Further the increasing volume of translation of materials across the organization has at times jeopardized meeting the specific timeframe for Board materials set forth in this recommendation. | ICANN has not identified any additional material opportunities during implementation of this recommendation. The Language Services Department has continued to improve its methodologies. | Publishing translations in all six United Nations languages provides greater access to the decisions and deliberations of the Board. Further, see response to question H. | Anecdotally, Staff has received positive feedback from community and staff members. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Dependencies included the availability and quality of outside translation services. | A specific process/workflow was created to publish these materials, as required. Posting of translations of resolutions and minutes of Board meetings and New gTLD Program Committee meetings within 21 days is now standard operating procedure. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
20. Ensure/certify that inputs in policymaking processes are considered by the Board | Board/BGC | Bruce Tonkin
| Staff: Board Support (Legal) | Amy Stathos; Samantha Eisner | Policy inputs were regularly considered by the Board before the ATRT1 Final Report was published. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. No. 20 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN addressed all portions of this recommendation in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | ICANN has not identified any material unforeseen issues during implementation of this recommendation. | ICANN has not identified any additional material opportunities during implementation of these recommendations. | The decisional checklists provide high level summaries and additional transparency into inputs the Board considers when making policy-related decisions. | Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Dependencies included input from each of the affected Supporting Organizations regarding the sufficiency of the checklists for their policy-making processes. | Decisional checklists have been developed and are used when policy recommendations arising out of the Supporting Organizations and are now part of the standard materials required. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
23. Get input from committee of independent experts on restructuring review mechanisms | Board/BGC | Bruce Tonkin
25. Clarify standard for Reconsideration requests | Staff: Board Support (Legal) | Amy Stathos | An established standard for reconsideration requests was in place before the ATRT1 Final Report was published. Prior recommendations relating to accountability mechanisms had been posted for public comment and challenged by the community to the extent they were not implemented. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of these recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. Nos. 23 and 25 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN addressed all portions of these recommendations in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Significant expenses were incurred engaging the expert group and significant staff resources were expended to support the expert group, but those were anticipated in developing the implementation plans (see www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf). Identifying a group of individuals with requisite diversity and expertise presented unforeseen challenges, resulting in the need for additional time and resources to complete implementation. | ICANN has not identified any additional material opportunities during implementation of these recommendations. | The revised mechanisms will bring easier access to the Reconsideration and Independent Review processes, enhance the ability of the community to seek to hold the Board accountable for its decisions, add more predictability into the processes, and add certainty into ICANN's decision making. | Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Dependencies included finding a group of individuals with the requisite diversity and expertise, the work of that group once comprised, community input into recommendations and coordinating with existing providers. | Bylaws and forms have been revised and are now part of the required processes. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
24. Assess Ombudsman relationship and confirm framework is consistent with international standards | Board/BGC | Bruce Tonkin
| Staff: Board Support (Legal); Ombudsman | Amy Stathos | ICANN has not identified any baseline in place from which this recommendation could be measured. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. No. 24 and 25 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN addressed all portions of this recommendation in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | ICANN has not identified any material unforeseen issues during implementation of this recommendation. | ICANN has not identified any additional material opportunities during implementation of this recommendation. | The Ombudsman has a more structured reporting relationship with the Board and a renewed focus on ensuring that he operates under the highest possible standards. |  | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No specific dependencies were identified. | A formal and regular reporting structure has been established between the Ombudsman and two Board committees. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
26. Adopt standard timeline & format for Reconsideration Requests | Board/BGC | Bruce Tonkin
| Staff: Board Support (Legal) | Amy Stathos; Samantha Eisner | There was a standard timeline and format for Reconsideration Requests in place at the time the ATRT1 Final Report was published, but no template was yet available. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Please see 2012 Implementation Summary re: ATRT Rec. No. 26 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN addressed all portions of this recommendation in implementation. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | ICANN has not identified any material unforeseen issues during implementation of this recommendation. | ICANN has not identified any additional material opportunities during implementation of this recommendation. | The implementation provided a standard tool for requestors to use which enhanced clarity and ease of access to the process. | Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See response to question J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No specific dependencies were identified. | A timeline and template remain available and have been updated to reflect revisions to process. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
Governmental Advisory Committee Operations, Engagement, Interaction with Board
9. Clarify what constitutes GAC public policy “advice” under the Bylaws. | Board/Board-GAC WG | Heather Dryden; Manal Ismail; Bill Graham | The baseline is described in the following excerpt from the JWG Final Report (June 2011): "GAC members have worked on the basis that any explicit advice, in any written form, constitutes the kind of advice foreseen in the Bylaws. In practice, the GAC produces various kinds of written advice for communication to the Board, including: 1) letters signed by the GAC Chair on behalf of the GAC. 2) communiqués endorsed by the GAC at the conclusion of each GAC face-to-face meeting. 3) overarching “principles” documents, typically developed over successive face-to-face GAC meetings. 4) “issues” documents, including interim issues documents. As reflected in the Bylaws, the focus of the GAC is on public policy advice. Such advice constitutes the majority of advice that is issued by the GAC. There are also instances where the GAC generates advice on matters related to the effectiveness of ICANN’s procedures for facilitating interactions between the ICANN constituencies in support of policy development. For example, the comments formulated by the GAC on the frequency of ICANN meetings. The Bylaws instead reference GAC advice that has a public policy aspect to it. The JWG does not consider it worthwhile to pursue efforts to distinguish between “informal” and “formal” GAC advice. As per Principle 47 of the GAC Operating Principles, the GAC first seeks consensus. In practice, the vast majority of GAC advice to the Board has been consensus advice. The GAC’s Operating Principles also note that if it is not possible to reach consensus then a full range of views can be presented to the Board. An appropriate balance in approach therefore would be for the GAC to identify consensus where it exists, record where it doesn't exist (and describe the various positions) and provide advice to the Board in a timely manner. Recommendation 4. That the GAC amends its Operating Principles to include a description of the process it follows to develop consensus-based GAC advice (e.g. by incorporating the UN definition of consensus into Principle 47). (Objective 1)" | The need for a clear definition, commonly agreed by the GAC and the Board, of what constitutes GAC advice that would imply an expected response either affirmatively or seeking further information or triggering the consultation mandated as per the Bylaws. See also https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf. | Perceived lack of clarity as to what constitutes GAC advice, and would hence need a Board response and would trigger the Bylaws if not followed, and how the GAC develops consensus advice. See also ATRT1 Final Report for discussion of the basis for the ATRT's recommendation. | For this recommendation, the focus was on developing a common understanding between the Board and the GAC as to what constitutes GAC advice under the Bylaws and how the GAC develops consensus advice. | The Board and GAC issued a joint communication to the ICANN community articulating a shared view of what constitutes public policy "advice" under the bylaws (March 2012). The communication reiterated the views expressed in the JWG Final Report. It indicated that written, explicit advice from the GAC constitutes "advice" as used in the bylaws. The Board and GAC also discussed whether and how to distinguish between consensus advice and other advice and their significance under the ICANN bylaws. The GAC amended its Operating Principles to include a description of the process it follows to develop consensus-based GAC advice (i.e., by incorporating the UN definition of consensus into Principle 47). The GAC restructured its communique to clearly highlight GAC advice to the Board and distinguish it from other informational sections; aiming at a process that is straight forward for: the Board to respond, the staff to enter to the Online Register and the GAC to follow-up. Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Complete. Please see 2012 Implementation Summary re: ATRT Rec. No. 9 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | Yes. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | It was not possible to meet the Recommendation's deadline for implementation by March 2011. Before any work could begin on any of the GAC-related recommendations, the previously-established Board-GAC Joint Working Group (JWG) needed to finalize its recommendations and report. The JWG Final Report was issued in June 2011, almost six months following the posting of the ATRT1 Final Recommendations, and posted for public comment. The JWG then dissolved and, following comment summary and analysis, the Board adopted a resolution in Sept. 2011 creating the BGRI-WG (approximately half the ICANN Board and the entire GAC). Additional factors contributed to the length of time it took to finalize implementation of the GAC-related recommendations including the difficulty of finalizing implementation outside of ICANN Public meetings where the BGRI-WG could meet face-to-face, and the difficulty the BGRI-WG had in meeting internal deadlines between ICANN public meetings. First face-to-face meeting of BGRI-WG was held at Costa Rica Meeting (March 2012). | No, not for this specific recommendation. | Significantly greater understanding among Board, staff and community as to what is and is not GAC advice, and embedded process for Board to seek clarification of the meaning of GAC advice (per Rec. 10). | Positive feedback from Board and GAC regarding implementation of this recommendation. | As a result of implementation of recommendations 9 and 10, it seems that among the Board, GAC, Staff and community there is a greater understanding of what is and isn't GAC advice which has led to improvements in the effectiveness and quality of work of the Board, the GAC and the multistakeholder community. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Dependencies for BGRI-WG, Board, GAC: finalization and adoption of the JWG report; constitution of the BGRI-WG; BGRI-WG deliberation and agreement on implementation plans. | None directly but indirectly was condition precedent for implementation of recs. 10, 11. | Publication of what constitutes GAC advice: http://www.icann.org/en/news/announcements/announcement-07jul11-en.htm Revised GAC Operating Principles: https://gacweb.icann.org/display/gacweb/Core+Principles JWG Final Report & Public Comment Forum: http://www.icann.org/en/news/announcements/announcement-07jul11-en.htm
| Staff: Global Stakeholder Engagement; GAC Liaison; Board Support (Legal) | Jamie Hedlund; Jeannie Ellers; Samantha Eisner
10. Create formal, documented process for requesting, tracking GAC advice.* | Board/Board-GAC WG | Heather Dryden; Manal Ismail; Bill Graham | Prior to implementation of this recommendation, there was no formalized process for tracking GAC advice or requests for GAC advice, nor was there a central repository for this information. | The need for an agreed formal, documented process through which the Board proactively seeks GAC advice on matters that affect public policy concerns. In addition, the need for an on-line tool that would be used to archive and track advice request, provided advice, Board response while maintaining an agreed timeline. The tool would ultimately be used to check old advice, know status of current advice and facilitate follow-up, tracking and handshaking.Board and GAC should establish formal, documented process by which it notifies the GAC of matters that affect public policy concerns. See also https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | No formalized process for tracking GAC advice or requests for GAC advice, nor was there a central repository for this information. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | The focus of this work was creation of online register of GAC Advice (and requests for GAC Advice) that tracks all phases in lifecycle of advice, from issuance through implementation (or rejection). BGRI-WG and staff understood recommendation to establish formal documented process for notifying the GAC of public policy concerns to be addressed in work on Recommendations 12&13. | Online register tracks advice, information and briefing requests from GAC to Board; board response, proposed and actual implementation, along with intervening communications and checks along the way to ensure alignment of Board and GAC; also tracks requests or notifications from Board regarding matters of public policy advice; process manual and flow diagrams developed. still open for iteration GAC Advice Register, written Board requests embedded in SOP: https://gacweb.icann.org/display/GACADV/GAC+Register+of+Advice Revised format of GAC Communiqué adopted which sets out much more clearly the GAC’s advice or requests of the Board. Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Complete (not including portion deferred to 12&13). Please see 2012 Implementation Summary re: ATRT Rec. No. 10 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | Yes, although BGRI-WG, Board and staff recognize that further iterations of the register and improvements in online performance will be made. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Not possible to meet March 2011 deadline established in Recommendation 10; see cell above for explanation. | Yes, as noted, further improvements will be made to the online register. | Greater visibility into what advice or information requests the GAC has issued to the Board and whether and to what extent ICANN has addressed these; same true with respect to Board requests of the GAC. | General satisfaction with the initial implementation of the GAC Advice Register; some suggestions for further improvement. | Greater transparency and accountability with respect to handling of GAC Advice/requests for information and Board requests. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Dependencies for BGRI-WG, Board, GAC: finalization and adoption of the JWG report; constitution of the BGRI-WG; BGRI-WG deliberation and agreement on implementation plans. | Creation and ongoing operation of GAC Advice Register; enabling tool for implementation of Rec. 11; enhances efficient and effective communication between GAC and Board on progress in addressing GAC advice. | GAC Advice Register: https://gacweb.icann.org/display/GACADV/GAC+Register+of+Advice
| Staff: Global Stakeholder Engagement; GAC Liaison; Board Support (Legal) | Jamie Hedlund; Jeannie Ellers; Samantha Eisner
11. Ensure timely provision & consideration of GAC advice and mechanisms for Board follow-up.* | Board/Board-GAC WG | Heather Dryden; Manal Ismail; Bill Graham | Prior to the ATRT Final Report, while the GAC would provide advice to the Board and the Board would consider that advice, there was no formalized or documented process for how the Board would consider that advice. Further, in the event that the Board anticipated taking action in contravention to the GAC advice, there was not a formalized process in place for how the Board and the GAC were to engage in the Bylaws-required consultations. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for what ATRT1 stated as the baseline. | The need for a formal, documented process agreed by the GAC and the Board, illustrating the details and timeline of seeking and responding to GAC advice. The process should further include agreed procedures for the consultation process to be followed, should the Board decide not to follow GAC advice. See also https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Main issues included instances where there was no or delayed Board response as well as overlooked follow-up from the GAC side. The recommendation called for a defined process for Board consideration of GAC advice. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | The desired outcomes were predictability, timeliness, accountability and transparency in how the Board considers GAC advice. ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN in its manner of implementation for each of the recommendations. | Through the Board/GAC Recommendations Implementation Working Group, guidelines were developed to impose predictability in the timing of the Board's consideration of GAC advice. The GAC advice register is one of the keys to this work, as well as the inclusion of steps that allow for clarifications to be sought. In addition, the historical process and draft documentation on Board/GAC consultations was considered and revised. Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Although identified tasks have been implemented, work continues as the GAC addresses ongoing improvements and evolving goals in this area. The timeline in how the Board receives advice and responds to advice is fully operationalized. The consultation process has been completely designed, though Bylaws changes are likely necessary to "hardcode" new recommended voting thresholds regarding the Board's rejection of GAC advice. However, GAC suggested that ICANN Bylaws amendment be addressed holistically with consideration of potential impact to other parts of the Bylaws and hence proposed postponing the process until after new gTLDs discussions. In the interim, the Board suggested to have all agreed changes reflected in the Board procedures manual, which does not have the same status as a formal resolution or the bylaws, but serves as a guide to the way the Board does things. Hence the consultation mechanism can/will be implemented prior to formal Bylaws modifications. Please see 2012 Implementation Summary re: ATRT Rec. No. 11 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN and the GAC have addressed all portions of Recommendation 11 through the implementation work. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | ICANN has not identified any material unforeseen issues during the implementation of this recommendation. | ICANN has not identified any additional material opportunities during implementation of this recommendation. | The implementation provides a clearer, more predictable path for the Board to receive and clarify the advice it receives from the GAC. This clarification may result in reduction of situations where the Board determines it is necessary to act in contravention to GAC advice. In addition, the development of the formal Consultation procedure will bring more predictability in situations where the Board determines its needs to act in contravention to GAC advice. While the new process has not yet been used, the consultation process can be expected to take a maximum duration of 6 months. While this sets a default maximum duration, it may also, in some cases, which could introduce delay into decisions that will impact third parties. |  | See J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | N/A | The procedures set out for the timing in the receipt and response to GAC advice are becoming standard operating procedures. The consultation process, upon initiation, will also become standard operating procedure. | Process for Consultations between the ICANN Board of Directors (“Board”) and the Governmental Advisory Committee (“GAC”), including those required pursuant to Article XI Section 2.1.j of the ICANN Bylaws. Proposed Timeline for Board-GAC Consultation Process Register Consultation Process Flow Chart (still needs to be posted online).
| Staff: Global Stakeholder Engagement; GAC Liaison; Board Support (Legal) | Jamie Hedlund; Jeannie Ellers; Samantha Eisner
12. & 13. Board, acting through the JWG, should develop & implement a process to engage the GAC earlier in the policy development process; ensure GAC is fully informed of policy agenda & policy staff is aware of GAC concerns.* | Board/Board-GAC WG | Heather Dryden; Manal Ismail; Bill Graham | Prior to the ATRT Recommendations, there were no set mechanisms to facilitate early engagement by the GAC in the policy development process, or targeted communication channels to ensure the GAC's awareness of the policy agenda or, the policy staff's awareness of GAC concerns. | The need for an agreed ongoing mechanism for GAC-Board timely exchange on policy agendas. This should eventually help, rather than advising the Board at a very late stage, engaging the GAC earlier in the policy development process, which would ultimately help tackling and maybe resolving any conflicts early within the PDP and consequently facilitating later Board decisions. See also ATRT1 Final Report at https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf. | The need to avoid situations where the GAC provides advice at a very late stage that conflicts with a policy recommendation before the Board for its consideration which has already been approved by the GNSO Council; the need to facilitate the availability/awareness of any GAC advice early enough so that it can be considered during the policy development process before it's completed. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | Overall, to facilitate and encourage earlier engagement by the GAC in the policy development process and to ensure more effective communication and coordination between ICANN staff, the Board and the GAC related to the policy development process; and in taking into account GAC concerns while policy is still being developed. | #12 – ICANN policy staff consulted and coordinated with the Board/GAC JWG in developing a Pilot Project to notify the GAC of upcoming and pending policy issues, as well as opportunities to participate in the policy development process. Policy staff met with the Board/GAC JWG in Toronto to present the Pilot Project and solicit feedback. Pilot Project initiated in November 2012, and involves the following: • Monthly reports posted on the GAC website, highlighting early engagement opportunities in policy development process for GNSO, ccNSO & ASO policy issues • Translated in 6 UN languages plus Portuguese • Current monthly Policy Update also provided to GAC with monthly reports: also highlights SO issues open for public comment • Policy Director assigned to coordinate pilot project and process #13 – Measures implemented to establish more effective communication and understanding between the GAC and ICANN for policy issues and concerns: • Face to Face Board/GAC meetings and discussion of policy issues at each ICANN meeting now part of SOP • GAC website redesigned and the Advice Registry launched • Increased staff coordination support for GAC processes and involvement with ICANN Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | 70% complete (as discussion with GNSO on GAC early engagement is still ongoing). | With respect to the original ATRT Recommendations, they were all fully implemented but please also see previous entry (F). Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Coordination of schedules is always a challenge for the SO-AC groups, including the GAC, at ICANN meetings. | Possible additional measures for future consideration: #12 - • GAC Chair designates small GAC WG • Reviews Monthly Reports for possible public policy interest • Post any comments on website • Submit comments to relevant SO • Specially-tailored Webinar prior to Public Meetings • Specifically designed for the GAC to focus on emerging or significant policy issues under development for discussion at public meetings that may raise public policy issues or concerns • Utilize Monthly Report to engage Supporting Organizations • Identify issues that may have public policy interest • Engage with relevant SOs prior to and during ICANN Public Meeting #13 - Assisting the GAC to organize/formalize regular consultation at ICANN meetings with the GNSO, ccNSO, ASO, and Advisory Committees on policy issues and matters of concern to the GAC. | Mechanisms to ensure GAC awareness of ICANN policy issues/agenda at an early stage in the policy development process, as well as ICANN Board/Staff awareness of GAC concerns are now in place. There is also a better awareness of the need for communication between the GAC and SO-AC groups on policy matters and an exchange of views. | The feedback from the GAC on the Pilot Project has generally been positive, as has been the feedback from both the GAC and the Board on the implementation of face-to-face meetings at ICANN international meetings. | Generally speaking, the implementation of these recommendations has established a better understanding of ICANN policy issues and policy development process by the GAC, as well as opportunities for closer collaboration and coordination between the ICANN Board, Staff and the GAC. These measures have resulted in earlier engagement by the GAC in the policy development process, and has helped to ensure that GAC concerns are taken into account in a more effective manner - i.e, while policy is still being developed (rather than after the policy has been developed and awaiting final consideration by the Board). Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | N/A | #12 - Policy Director specifically assigned to coordinate pilot project which includes distribution of monthly one-page reports on current policy development issues to GAC membership, and process to facilitate GAC's early engagement in policy development process. #13 – Face to Face Board/GAC meetings and discussion of policy issues at each ICANN meeting are now part of SOP. There is increased staff coordination support for GAC processes and involvement with ICANN. | Although the recommendations have been fully implemented, the next step is to make the actual engagement process more effectively utilized. In the GAC's view, further improvements in actual engagement and coordination between the GAC and policy supporting organizations can be made.
| Staff: Office of the CEO; Policy; Global Stakeholder Engagement; GAC Liaison | David Olive; Jamie Hedlund; Jeannie Ellers
14. Increase support & commitment of governments to the GAC process.* | Board/Board-GAC WG | Heather Dryden; Manal Ismail; Bill Graham | While more than 100 governments were officially members of the GAC at the time the ATRT Final Report was issued, it was clear that not all were or could be heavily engaged or committed to ICANN or the multi-stakeholder model. | The need to increase the level of support and commitment of governments to the GAC process by: - outreach to non-members - facilitating attendance and participation of members by increasing funds, providing translated documents, providing interpretation, supporting secretarial work; - engaging senior government officials to ensure commitment of GAC member countries and that their representatives will be spared the necessary time, provided the needed resources and empowered by the authority to actively participate and provide timely input See also https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Increasing GAC membership and making it easier for GAC members to participate in ICANN is important for the future success and legitimacy of the organization. While most of this recommendation calls for Board action, it cannot be implemented without the cooperation and support of the GAC. Progress will require joint dialog, planning and execution by the Board and GAC. Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | Greater support for GAC members, particularly those from the developing world; better translation and interpretation; hosting of a High Level Meeting; enhance "onboarding" of new GAC members with more and better educational materials. | Key actions include: - Creation of GAC Capacity Building WG; Non-GAC governments invited to meetings and GAC introductions added; - Increased resources for interpretation of GAC sessions and for translation of GAC documents; - Increased resources for members travel support with a focus on those GAC members from developing economies; - In coordination with GAC, staff members raising awareness in regions about role of GAC and ICANN; - GAC membership also promoted through Fellowship program; - Increased support to GAC processes and involvement in ICANN; - Tarek Kamel appointed to focus on government engagement for ICANN; - Continued operation of BGRI-WG; - Use of the measurement of current GAC membership and resource allocations to create a baseline for future, annual metrics; - Launch of myICANN increases governments’ access to key information; - Joint hosting of the HLM by Canadian Government/GAC as pilot; - GAC communiqué and Board resolution recognizing GAC HLM efforts on increasing awareness/government engagement in ICANN and noting long-term efforts. Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. | Complete. Please see 2012 Implementation Summary re: ATRT Rec. No. 14 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | Yes. Yet experience with the HLM needs to be studied to guide future decisions whether further such meetings should be held, how frequent and what are the lessons learnt. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Some difficulty in identifying level, date and venue for HLM. | More could be done to provide new GAC members with sufficient informational resources. MyICANN was, in part, intended to contribute to this objective and the planned Online Education Platform (working title) also is expected to help address GAC member's information needs. | GAC appears to have benefitted from increased travel, language, staff, translated documents, real-time interpretation and informational resources; successful HLM in Toronto. | Anecdotal, positive feedback. | ICANN gains credibility with increased governmental engagement, particularly from the developing world. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Identification by GAC of additional resource needs, ICANN budget process to approve same, HLM planning and coordination. |  | Increased language resources approved: http://www.icann.org/en/financials/adopted-opplan-budget-fy12-09sep11-en.pdf HLM Meeting: http://toronto45.icann.org/gac-hlm Increased travel support approved: http://www.icann.org/en/financials/adopted-opplan-budget-fy12-09sep11-en.pdf
| Staff: Office of the CEO; Global Stakeholder Engagement; GAC Liaison | Tarek Kamel; Jamie Hedlund; Jeannie Ellers
Public Input & Multilingual Access
15. Implement stratified, prioritized public Notice & Comment processes. | Board/PPC | Sébastien Bachollet/Chris Disspain
| Staff: Policy | David Olive/Sally Costerton/Chris Gift | Public Comments solicitations were not previously categorized or prioritized in any standard or systematic manner. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) I.e. Incorporate Prioritization and Stratification based on community input and consultation with Staff. | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. In particular, due to the proliferation of Public Comments topics, at certain times, community members must read each solicitation in order to determine whether or not to participate. Adding Stratification and Prioritization information to each solicitation were thought to enable community members to make participation decisions more quickly and efficaciously. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN Staff in its manner of implementation for each of the recommendations. The focus was on improving the participation, usability, flexibility, efficiency, and overall effectiveness of the ICANN Public Comments process. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. A two-phase project plan was developed including forming a community Focus Group (Jul-Aug 2011); Phase I (Aug 2011) involved improvements to the existing Public Comments website. Rec #15 was implemented as part of Phase II (Dec 2011). For Stratification, a list of possible subjects was proposed by Staff and submitted for community comment as part of a formal Public Comment forum. Several changes were incorporated based upon community feedback resulting in 16 final categories. The Focus Group and community generally were not in favor of assigning priority because of its subjectivity among various organizations. Instead, several new fields were added to assist community members understand context and next steps. | Please see 2012 Implementation Summary re: ATRT Rec. No. 15 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). 100% (1 Jan 2012) as proposed by Staff and amended based upon Focus Group and Public Comment community feedback. | Yes - all parts were implemented as planned. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | The implementation of this recommendation was straightforward and involved redesigning the ICANN.org web pages, developing a standard template for Open Topics, finalizing the 16 subject categories (including incorporating community feedback), and publishing Staff Guidelines to document roles/responsibilities as well as flowcharts and tools. | No additional opportunities for improvement were identified relative to this specific recommendation; however, now that it has been implemented for a full year, Staff suggests that the community be asked, perhaps via a survey instrument, whether the Stratification and Prioritization enhancements have provided value and whether any additional improvements are advisable. | Each Public Comments solicitation is now categorized (16 subject areas) to help the community with participation decisions; additional fields are also available to help explain context and relative importance. There are no formal metrics to gauge the effect or outcome of stratifying Public Comments. Now that this enhancement has been in place for over a year, Staff recommends that the community be asked (e.g., via survey instrument) to assess the value of the stratification enhancement and the supplemental prioritization information. | There has not yet been any formal mechanism to collect internal or external feedback concerning the Stratification and Prioritization of Public Comments solicitations. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | With respect to Rec #15, data has not yet been collected concerning the extent to which these enhancements have improved ICANN's process for Public Comments. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No special dependencies were noted pertaining to this particular recommendation other than Staff strongly urging that it not be placed in a position of assigning priority values to Public Comment solicitations (not implemented). | New Staff Guidelines were published including standard templates to capture the appropriate category(ies), status, next steps, et al., pertaining to this recommendation. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
16. & 17. Provide “Comment” cycle & a “Reply Comment” comment cycles; review and adjust fixed timelines for Notice & Comment | Board/PPC | Sébastien Bachollet/Chis Disspain
| Staff: Policy | David Olive/Sally Costerton/Chris Gift | Perception that timeframes were inconsistently administered and that adding a separate Reply Cycle would enhance the community's participation experience. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) I.e. #16 - Create distinct Comment and Reply cycles that allow community respondents to address and rebut arguments raised; #17 – Establish fixed duration Timelines to provide adequate opportunity for considered and timely comments and replies. | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. I.e. adding a formal opportunity to submit replies to original comments, simulating a dialogue, was designed in the hope of stimulating participation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN Staff in its manner of implementation for each of the recommendations. The focus was on improving the participation, usability, flexibility, efficiency, and overall effectiveness of the ICANN Public Comments process. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. A two-phase project plan was developed including forming a community Focus Group (Jul-Aug 2011); Phase I (Aug 2011) involved improvements to the existing Public Comments website. Recs #16-17 were implemented as part of Phase II (Dec 2011). Various alternatives were considered; however, Staff settled upon a minimum 21-day Comment & Reply cycle which was then submitted for community input as part of a formal Public Comments forum. Community feedback generally supported the Reply Cycle; however, several respondents thought that the timeframes should be increased. In the published guidelines, Staff members were encouraged to extend the timeframes based upon topic complexity or other needs of the community. | Please see 2012 Implementation Summary re: ATRT Rec. Nos. 16 and 17 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). 100% (1 Jan 2012) as proposed by Staff and amended based upon Focus Group and Public Comment community feedback. | Yes - all parts were implemented as planned. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | One continuing challenge, although anticipated from the outset, has been community members submitting original Comments during the Reply cycle. At this stage, there is no automated method that would inhibit a respondent from using the 2nd period as an extension of the initial Comment cycle. | Staff identified and tested a potential replacement technical solution (Confluence Wiki) for Public Comments that would permit dynamic threading (comments and replies) vs. static email submissions. That project was not formally evaluated for implementation due to other important organizational priorities at the time (2012); however, it remains a viable alternative for future consideration. | A formal study of the Public Comments experience from 2010-2012 has recently been completed including supported inferences concerning the effectiveness of the Reply Cycle implementation. It is clear from the data analysis that a majority (over 70%) of Reply submissions were not related to any prior Comment; rather, were forwarded after the initial period ended. One hypothesis to be further evaluated is whether some community members may be utilizing the Reply Cycle as a virtual extension of the initial Comment period. | Since its adoption, there has not been any formal mechanism to collect internal or external feedback concerning the Comment/Reply Cycle implementation. Informal input has been received that the Comment and Reply cycles (each minimum 21 days) are not sufficiently long for certain communities due to internal drafting and review processes. Both Staff members and the community have been advised that the 21 day periods are minimums, not maximums. Staff members have been encouraged to utilize longer periods, especially when a topic is complicated or expected to require a more extensive analysis period by the community. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | An analysis of the Public Comments experience from 2010-2012 has recently been completed including supported inferences concerning the effectiveness of the Reply Cycle implementation. The data analysis shows that a majority (over 70%) of Reply submissions were not related to any prior Comment; rather, were forwarded after the initial period ended. The Comment/Reply Cycle enhancement appears to require further study to improve its effectiveness within the overall Public Comments process. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No special dependencies were noted pertaining to this particular recommendation other than certain groups expressing concern about extending the timeframes for Comment/Reply Cycles. | New Staff Guidelines were published including standard templates/flowcharts to simply presentation and formally document roles/responsibilities. The Guidelines encourage Staff members to extend the timeframes for Comment/Reply Cycles based upon perceived topic complexity and/or to accommodate community needs. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
18. Ensure multilingual access in PDP to maximum extent feasible | Board/PPC | Sébastien Bachollet | [9 empty] | ·
| Staff: Communications | Christina Rodriquez | No formal, adopted organizational guidelines for publication of translated material. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) In general, that we had to make information about ICANN and its work more accessible to those who speak languages other than English in ways that enhance participation in and the effectiveness of the multistakeholder model. | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN Staff in its manner of implementation for each of the recommendations. Overall, the outcome was focused on the enhancement of community participation to live up to ICANN's multistakeholder model. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. ICANN Language Services Policy and Procedures was created, put through a Public Comment Period, approved by the ICANN Board, implemented, and incorporated in the Standard Operating Procedure. | Please see 2012 Implementation Summary re: ATRT Rec. No. 18 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). The implementation plan for this recommendation is 100% complete. Follow-up work to fully implement the LSPP throughout the organization is ongoing. | Yes. One of the first accomplishments was the creation and approval by the Board of the Language Services Policy and Procedures document. The ATRT1 recommendation to “Enhance Multilingual Strategy” also added significant improvements (more interpretation support, transcription support, teleconference interpretation). Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Yes; allowing for translation time when planning a project at times continues to be challenging for the community, Board and staff. | Yes, one of them being the provision of teleconference interpretation support by our own team of interpreters | One outcome was a substantial increase in work and resulted in the need to create better processes. Also, it has demonstrated a clear need to switch from a translation function to a translation department to attend to all of the needs, external and internal. | Informal feedback from the community and ICANN followers has been positive. From an ICANN perspective education is needed to provide the Board, community and staff with a better understanding of processes. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | The provision of translated material is more organized, and ICANN attends to the needs and requests from the community. ICANN also has laid the path toward more effective engagement with global stakeholders. | Board approval, advice from the Legal department, financial support. | Many changes and new processes and workflows were created to provide better language support. | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
21. Create annual public comment forecast | Board/PPC | Sébastien Bachollet/Chris Disspain
| Staff: Policy | David Olive/Sally Costerton/Chris Gift | Community had no visibility into future Public Comments topics which, if available, could be used effectively for planning upcoming participation. | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) I.e. #21 - Introduce forecasts of upcoming Public Comment topics to facilitate community planning and participation. | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. I.e. establishing visibility into potential Public Comments topics would improve the community's ability to plan (staffing) and participate on future solicitations. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN Staff in its manner of implementation for each of the recommendations. The focus was on improving the participation, usability, flexibility, efficiency, and overall effectiveness of the ICANN Public Comments process. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. A two-phase project plan was developed including forming a community Focus Group (Jul-Aug 2011); Phase I (Aug 2011) involved improvements to the existing Public Comments website and implementation of Rec #21. In June 2011, a request was forwarded to Staff and SO-AC leaders soliciting upcoming topics (one year horizon), which were then consolidated and published on ICANN.org under the new heading "Public Comments-Upcoming." An annual process was also developed to refresh this information periodically. | Please see 2012 Implementation Summary re: ATRT Rec. No. 21 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). 100% (1 July 2011) as originally developed by Staff including guidelines, procedures, and flowcharts for ongoing administration. [Note: the annual update process was not completed in Dec 2012 per the guidelines. Staff is currently simplifying the process and templates and expects to launch another formal refresh cycle shortly.] | Yes - all parts were implemented as originally proposed. [Note: the annual update process was not completed in Dec 2012 per the guidelines. Staff is currently simplifying the process and templates and expects to launch another formal refresh cycle shortly.] Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | The initial collection of Upcoming Topics went smoothly and was implemented on schedule. [Note: the annual update process was not completed in Dec 2012 per the guidelines. Staff is currently simplifying the process and templates and expects to launch another formal refresh cycle shortly.] | As a result of a missed opportunity (Dec 2012) to refresh the annual Upcoming Topics data, Staff is currently revising the process and template to operate on a trimester schedule. A refresh cycle is expected to commence shortly once the process has been put in place. Staff also recommends that, after another six months experience, the community be asked for its feedback on the value of publishing Upcoming Topics. | There are no formal metrics to gauge the effect or outcome of publishing Upcoming Public Comments topics. There is anecdotal evidence that some community members perceive value in consulting the Upcoming topics list; however, a formal study should be undertaken approximately six months after the information has been refreshed. | Since its adoption, there has not been any formal mechanism to collect internal or external input concerning the Upcoming Topics implementation. Anecdotal feedback suggests that certain communities appreciate and value having the list of Upcoming Topics to consult. Some anecdotal information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | With respect to Rec #21, data has not yet been collected concerning the extent to which this enhancement has improved the overall Public Comments process. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No special dependencies were noted pertaining to this particular recommendation. | New Staff Guidelines were published including standard templates/flowcharts to collect and update Upcoming Topics on an annual basis. [Note: Staff is currently revising the process and template to operate on a trimester basis. A new data refresh cycle will be launched once the modified process has put in place.] | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
22. Ensure senior staffing arrangements are appropriately multilingual | Staff: HR | Steve Antonoff | Unknown | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) I.e. increase the multilingual skills of senior staff. | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation, i.e. increasing global community support and involvement by speaking languages besides English. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN Staff in its manner of implementation for each of the recommendations, and for this recommendation led to a focus on increasing the multilingual skills of senior staff. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. Key elements include: 1) All posted jobs indicate the desire for multilingual skills; 2) Language skill training made available to staff; 3) Interview review forms require interviewers to indicate multilingual skills of candidates. | Complete. Please see 2012 Implementation Summary re: ATRT Rec. No. 22 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | Yes Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No | No | Senior staff is significantly more multilingual. It is hard to measure the external effect. | No feedback received. | We have demonstrated an ongoing commitment to transforming ICANN into a more global organization. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | None | Job postings modified, interview process modified | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.
Measuring Success
27. Evaluate and report on progress on recommendations and accountability & transparency commitments in the AoC. | Board/Exec | Steve Crocker
| Staff: Office of the CEO | Denise Michel | NA | ICANN understood the recommendation to be as stated in the ATRT1 Final Report. (See https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf and proposed implementation plans, at www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf.) | Please see ATRT1 Final Report (https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf) for discussion of the basis for the ATRT's recommendation. I.e. evaluate and publicly report on implementation of the ATRT1 Report to track progress and advance ICANN's accountability and transparency. | ICANN's understanding of the desired outcomes of the recommendations of the ATRT1 Final Report was to enhance overall accountability and transparency. These desired outcomes guided ICANN Staff in its manner of implementation for each of the recommendations. The outcome for this recommendation was focused on enabling the public visibility into implementation of the ATRT1 Report. | Please see Proposed Implementation Plans October 2011 for how ICANN originally planned to implement the recommendation (www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf) and the 2012 Summary Report (http://www.icann.org/en/news/in-focus/accountability) for how ICANN implemented the recommendations. ICANN used established mechanisms to implement the recommendation, including: • An "Accountability & Transparency" webpage that kept the public apprised of progress on ATRT1 and other AoC reviews • The posting of 2012 Annual Report on ATRT Implementation • The posting of frequent status updates and reports on implementation, including “ATRT Implementation Summary” and “ATRT at-a-glance;” • Reports from the Board at the March 2011 and June 2011 ICANN meetings detailing which recommendations have been fully implemented, and the status and schedule for implementing the remaining recommendations; • An overview in ICANN’s Annual Reports for FY2011 and FY2012 of achievements and progress made on the ATRT recommendations and AoC commitments; • Public forums on ATRT activities at ICANN’s October 2011 and June 2012 meetings • A public webinar and numerous presentations to ICANN constituency groups • Regular highlights of completed ATRT tasks publicly posted • Ongoing Metrics for ATRT-specific projects. In addition, internal mechanisms were used to monitor and advance implementation of the recommendations, including monthly tracking reports on for the Board Chair and (under CEO Fadi Chehade) detailed work plans and weekly progress meetings. | Please see 2012 Implementation Summary re: ATRT Rec. No. 27 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) The implementation plan, as amended, was fully implemented. The Board & Staff regularly evaluated progress against the ATRT1 recommendations, and the accountability and transparency commitments in the AoC, and in general considered the accountability and transparency performance of the whole organization. Regular reports were publicly issued on ATRT1 implementation and the public was kept apprised of ICANN activities on a myriad of efforts broadly aimed at improving accountability and transparency. | No. | Additional opportunities include: agreeing on a definition of "public interest," "accountability" and "transparency;" developing and reporting on additional metrics and benchmarks related to ATRT1 recommendations; expanding a public "dashboard "reporting on accountability and transparency-related activities; conducting an organization-wide assessment of ICANN's performance against accountability and transparency commitments. | Public reporting reinforced Board and Staff attention to ATRT1 implementation. Presumably public confidence on ATRT1 implementation was increased, but this was not quantified. | Anecdotal, positive feedback. More information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | See J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Board, GAC, NomCom and Staff action was needed to fulfill reporting obligations. | NA | Please refer to separate "Reference Materials" sheet for hyperlinks to referenced materials.

## Reference Materials
Reference Materials
Document | Link
Accountability & Transparency Review Team 1 (ATRT1) Final Report and Recommendations, January 2010 | https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf
ATRT Recommendations - Proposed Implementation Plans; Ocotber 2011 | http://www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf
ATRT Implementation Summary Report 2012 | www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf
2012 Annual Report - Implementation of the Accountability & Transparency Review Team Report; January 2013 | http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf
NomCom web site | http://nomcom.icann.org/
ICANN 2012 NOMCOM FINAL REPORT | http://nomcom.icann.org/nomcom-final-report-08oct12-en.pdf
Adopted Board Resolution - Chair Remuneration, August 2013 | http://www.icann.org/en/groups/board/documents/resolutions-05aug10-en.htm#5
Community Input Advice Framework, September 2012 | www.icann.org/en/news/in-focus/accountability/input-advice-function-24sep12-en.pdf
Policy vs. Implementation Public Comment Period, January 2013 | http://www.icann.org/en/news/public-comment/policy-implementation-31jan13-en.htm
ICANN Accountability & Transparency | http://www.icann.org/en/news/in-focus/accountability
FY12 Operating Plan and Budget Fiscal Year Ending 30 June 2012, adopted 24 June 2011 | http://www.icann.org/en/financials/adopted-opplan-budget-fy12-09sep11-en.pdf
GAC High Level Meeting, Toronto - October 2013 | http://toronto45.icann.org/gac-hlm
JWG Final Report & Public Comment Forum, July 2011 | http://www.icann.org/en/news/announcements/announcement-07jul11-en.htm
Revised GAC Operating Principles | https://gacweb.icann.org/display/gacweb/Core+Principles
Publication of what constitutes GAC advice, July 2011 | http://www.icann.org/en/news/announcements/announcement-07jul11-en.htm