## WHOIS
Questions from ATRT2 regarding implementation of recommendations of WHOIS
WHOIS Recommendations | Board Action | Implementation Assignments |  | A. What was the baseline? | B. What did s/he understand the recommendation to be? | C. What did s/he understand the underlying issue to be that led to the recommendation? | D. What did s/he understand the desired outcome to be from the recommendation? | E. How did s/he implement the recommendation? What options were considered and how was the actual option chosen for implementation? | F. Percentage/portion that is complete? | G. Does s/he believe ICANN fully implemented the recommendation? If not, why not? If not, what parts were not implemented, and why not? | H. Did s/he run into any new or unforeseen problems or issues while implementing the recommendation? (i.e. scope increase, costs, legal, resources, timing) | I. Did s/he identify additional opportunities for improvement by virtue of the implementation of these recommendations? | J. What has been the outcome and effect both inside ICANN and external to ICANN as a result of the implementation of the recommendation? | K. What has been the feedback both inside ICANN and external to ICANN as a result of the implementation of the recommendation? | L. How does s/he feel that ICANN has improved as a result of the implementation of the recommendation? | M. What were the dependencies as seen from each group involved in implementation? | N. In view of ATRT1 what changes in workflows and/or organization where undertaken? | Additional Information
Strategic Priority
1. WHOIS, in all its aspects, should be a strategic priority, form the basis of staff incentivization (including CEO’s) and organizational objectives; Board should create a committee that includes the CEO to be responsible for priority and key actions; issue public updates on progress against targets for all aspects of WHOIS. | -Board agrees that gTLD WHOIS is a strategic priority for ICANN. -Consistent with advice from SSAC (SAC055), Board directs the CEO to create an expert working group to create material to launch GNSO policy work and inform contractual negotiations, as appropriate. Working group output is expected within 90 days and will ideally include a strawman model for managing gTLD registration data. -The working group’s output form the basis for an Issues Report to accompany Board-initiated, expedited GNSO policy work that is expected to result in consensus policy that, at a minimum, addresses the purpose of collecting, maintaining and making available gTLD registration data, and related accuracy, data protection, and access issues. -The Board also will call upon the registrars, registries, and the staff to address the working group’s output in contractual negotiations and registry contracts, as appropriate. -The CEO will oversee improvements to the enforcement of the contractual conditions relating to gTLD WHOIS in the gTLD registry and gTLD registrar agreements. Appropriate reporting of these improvements will be developed, and the CEO will be responsible for appropriate staff incentives. -The Board will incorporate performance of the WHOIS strategy into the incentive program for the CEO. | Office of the CEO; Strategic Initiatives; Legal; Compliance | Staff: Denise Michel; Margie Milam; John Jeffrey; Dan Halloran; Maguy Serad | The baseline was that WHOIS was one of several important policies that ICANN was committed to enforcing. | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially that the WHOIS RT desired to see the Board, CEO, and Executive Team oversee and direct a thorough plan and attention to all aspects of WHOIS. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT believed that insufficient resources had been dedicated in the past to managing the operational, policy, and compliance related activities pertaining to the WHOIS policy. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is a highly visible and coordinated effort led by ICANN executives to redefine the manner in which ICANN addresses the WHOIS issue. | Staff and the Board fully embraced this obligation in its implementation, as initiated by the Board's November resolution. Staff has been incentivized through ICANN's bonus system, as WHOIS projects are identified in both At-Task and the Halogen system, for the managers/executives responsible for its implementation. Fadi's compensation is based on the overall goals and objectives of the entire organization and set forth in the new Management Plan system, which includes specific projects related to WHOIS. The Board and public are kept closely apprised of implementation progress through regular updates, blog posts, and webinars. | Approximately 25% | Full implementation is underway, as directed by the Board. Note that due to the importance of the issue, the entire Board is monitoring the progress of the implementations rather than a committee of the Board (per the Board's direction). | No | Yes, as part of the analysis surrounding the WHOIS RT Report, a new effort was launched at the Board's request to create a new system for data directory services, rather than continue to rely on the current WHOIS policies and its enforcement, which are widely viewed as antiquated and broken. This "clean slate" effort, which is currently underway through the creation of the Expert Working Group, is expected to produce a new system that can address many of the inadequacies of the current WHOIS system. | N/A, as the implementation has not been fully completed. | There has been widespread support for the announcement of the creation of the Expert Working Group, and the effort underway to create a new approach to Data Directory Services. In addition, on a recent Webinar on the implementation of the WHOIS recommendations, participant seemed generally pleased with the overall progress to date. | N/A, as the implementation has not been fully completed. | None | ICANN's Compliance Function was restructured in that a new position, the Vice President of Compliance, reporting directly to the ICANN CEO, was created. As a result, the CEO now oversees and has direct visibility into the enforcement of WHOIS. A cross-functional Staff team was formed to coordinate on implementation of the recommendations. | For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
Single WHOIS Policy
2. Board should oversee creation of a single WHOIS policy document, and reference it in agreements with Contracted Parties; clearly document the current gTLD WHOIS policy as set out in the gTLD Registry & Registrar contracts & Consensus Policies and Procedure. | -The Board directs the CEO to create and maintain a single public source that compiles current gTLD WHOIS requirements for gTLD registries, registrars and registrants (including consensus policies and contractual conditions). | Legal | Staff: Dan Halloran | Before the implementation of this recommendation there was no single public source that compiled gTLD WHOIS requirements for registries, registrars, and registrants. | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially to create single public source that compiled gTLD WHOIS requirements for registries, registrars, and registrants. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT believed that before the implementation of this recommendation the only way to identify and review gTLD WHOIS requirements was to search through the ICANN website through dozens of separate policies, procedures and agreements. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is the creation of a single public source that compiles gTLD WHOIS requirements for registries, registrars, and registrants. | The recommendation was implemented by reviewing an earlier draft compilation of WHOIS requirements (created for the WHOIS RT); consulting with staff subject matter experts; reviewing options for implementation including a prose or bullet-point summary; finalizing the compilation document; posting the compilation document; and posting an ICANN blog post <http://blog.icann.org/2013/04/single-source-of-whois-related-agreement-provisions-and-policies/> to let the community know about the new resource. | Complete. | Yes, the recommendation was fully implemented. | No unforeseen problems or issues were encountered in implementing the recommendation. | There are likely other ICANN issues and topics that could benefit from the idea of creating a single compilation or index page. This concept of a single source will be kept in mind for future development of ICANN webpages. | The new single source of WHOIS-related agreement provisions and policies will be of use to the general public, and also to ICANN registrars, registries, and staff. | The implementation of the recommendation was completed on 15 April 2013, and not much feedback has been received. One person added a comment to the blog post questioning the value of new compilation in light of his impression that registrars are not serious about "WHOIS accuracy compliance". | The new single source compiling WHOIS provisions should be useful inside and external to ICANN. The webpage received over 200 hits in the first two weeks since posting. | The implementation of the recommendation (following Board adoption) did not have any external dependencies. | N/A. | For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
Outreach
3. ICANN should ensure that WHOIS policy issues are accompanied by cross community outreach, including outreach to the communities outside of ICANN with a specific interest in the issues, and an ongoing program for consumer awareness. | -The Board directs the CEO to create an information portal with clear explanation of how to access the existing WHOIS information. -The portal also will make it clear how to notify relevant parties of a data accuracy issue. -The Board directs the CEO to have staff to create and execute a communication and outreach plan that provides key stakeholders, including users, with the information they need to use, and help improve, the collection and maintenance of gTLD registration data. | Online Communications Services; Communications | Staff: Chris Gift; Jim Trengrove; Lynn Lipinski | The baseline for this recommendation is the existing Internic website as well as the content currently on ICANN.ORG. Regarding outreach, WHOIS policy issues, like all policy issues, are regularly included in ICANN's web site and Policy Update newsletter as milestones are reached or action is taken. | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially to raise awareness about WHOIS policy issues beyond the ICANN community, and to raise consumer awareness related to WHOIS. Additionally, to create a site, or place, for individuals and communities with an interest in WHOIS to access a single source of information and data on WHOIS. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT believed that there was a lack of general awareness about where to find WHOIS information and why it is needed. ICANN must proactively reach stakeholders outside the community, and to raise consumer awareness related to WHOIS. In addition to raising awareness about where to find information, within existing websites there is also a fragmentation of WHOIS terminology, information and tools that must be consolidated. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is that stakeholders - beyond those who are keyed in to ICANN issues - are aware of WHOIS issues and efforts, and know how to make their voices heard in the process, and to raise consumer awareness related to WHOIS. A key element is that stakeholders have easier access to WHOIS tools and information, that uses easy to understand terminology and language for the general public. | Planning is in progress. | In progress. | Yes | In progress. | In progress. | In progress. | In progress. | In progress. | In progress. | In progress. | For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
Compliance
4. ICANN should ensure that its compliance function is managed in accordance with best practice principles, including full transparency on resourcing and structure; provide annual reports; appoint a senior executive whose sole responsibility would be to oversee and manage ICANN’s compliance function (reporting to Board Committee); provide all necessary resources to manage and scale compliance team’s activities. | -The Board directs the CEO to create and publicize a reporting structure on compliance activities, and regularly report on compliance activities related to gTLD registration data. | Compliance | Staff: Maguy Serad | ICANN understood the baseline, recommendation and underlying issue to be as articulated in the WHOIS Review Team Report: http://www.icann.org/eN/About/aoc-review/whois/final-report-11may12-en.pdf Quote from WRT Report on Recommendation 4: "Despite substantial efforts made, and dedicated staff, the Compliance function has suffered from lack of resources, and has struggled to maintain organizational priority…We find that basic information, for example on staffing, budget vs. actual spend, and key performance metrics, remain difficult to obtain...There should be clear and appropriate lines of reporting and accountability, to allow compliance activities to be pursued pro-actively and independently of other interests." |  |  | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is to enhance overall accountability and transparency of the Contractual Compliance department by implementing improvements to compliance resources, operations and communication. | Please refer to the Board Resolutions: http://www.icann.org/en/groups/board/documents/prelim-report-08nov12-en.htm which references "Action Plan to Address WHOIS Policy Review Team Report Recommendations"—ICANN Board Submission Number 2012-11-08-01" (http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf [PDF, 265 KB]). "As part of the work of the President and CEO to ensure continued compliance with existing policy and conditions, the President and CEO has moved the Compliance Department to report directly to the President and CEO (http://www.icann.org/en/news/announcements/announcement-14sep12-en.htm), and the Board granted financial authorization to establish a Contractual Compliance Audit Program through an independent Service Provider (http://www.icann.org/en/groups/board/documents/resolutions-03oct12-en.htm#1.d) In summary: the implementation focused on strengthening the Contractual Compliance program (operations, Enforcement of the current obligations on gTLD WHOIS), performance measurement, improving on community reporting and launching the Audit Program. Focus on People, Processes, Systems and Communication | ICANN reported on efforts to improve compliance, enforcement and communication at all ICANN meetings; 1) People - grow staff in skills and expertise and number; Increase staff to 15 FTEs and contractors based on projects; Compliance led by VP reporting to CEO (100% complete) 2)Processes - build, communicate, implement and publish operational processes (100%) 3) Systems - consolidate and automate the fragmented tools (100% for WHOIS; 50% for the full consolidation of other systems) 4) Communication (100%) -Annual Report redesigned and published in 6 UN languages to provide data on budget and across all areas -Monthly Updates published in 6 UN languages 5) Performance Measurement - Metrics published on MyICANN (100%) 6) Audit Program launched (Year one 80% complete) | ICANN is fully implementing the recommendations, as directed by the Board. Please refer to column F. Note that due to the importance of the issue, the entire Board is monitoring the progress of the implementations rather than a committee of the Board (per the Board's direction). | ICANN has not identified any material unforeseen issues during implementation of these recommendations. | ICANN has not identified any additional material opportunities during implementation of this recommendation. | ICANN community recognized and appreciated the Contractual Compliance efforts to improve operations and communications. | At ICANN Meeting 46, positive input and recognitions were given at all stakeholders meetings - Registrars, Registries, At Large Advisory Committee, Intellectual Property Constituency and Law Enforcement Agencies. ICANN notes that a definition of the purpose and provision of gTLD directory services is critical to the framework and scope of contractual compliance. Community expectations vary as it relates to WHOIS inaccuracy - the outcomes of the Expert Working Group should act as guidance and should serve as a basis of work within the PDP. | As reported, ICANN has improved Contractual Compliance resources, operations, measurement and communication. | The dependencies were the following areas: PEOPLE - 1. Internal ICANN stakeholders 2. Contracted Parties 3. External ICANN stakeholders SYSTEMS - 1. identification of solution 2. IT resources to implement 3. Compliance resources 4. Contracted parties to review and test | N/A. See column F for changes, which the WHOIS Review Team Report helped reinforce. | For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
Data Accuracy
5. ICANN should ensure that the requirements for accurate WHOIS data are widely and proactively communicated, including to current and prospective Registrants, and should use all means available to progress WHOIS accuracy, including any internationalized WHOIS data, as an organizational objective. | -The Board directs the CEO to: 1) proactively identify potentially inaccurate gTLD data registration information in gTLD registry and registrar services, explore using automated tools, and forward potentially inaccurate records to gTLD registrars for action; and 2) publicly report on the resulting actions to encourage improved accuracy. -The Board directs the CEO to ensure that WHOIS information pages make clear the requirements for registrants to provide accurate information, and the consequences of providing inaccurate information. -The Board continues to support the RAA negotiation process to find ways to improve WHOIS accuracy, and as per (1) above is initiating a PDP to reform the WHOIS policy to support the objectives and balance the concerns of the multi-stakeholder community. | Online Communications Services; Compliance; Communications | Staff: Chris Gift; Maguy Serad; Jim Trengrove; Lynn Lipinski | ICANN understood the baseline to be as articulated in the WHOIS Review Team Report: http://www.icann.org/eN/About/aoc-review/whois/final-report-11may12-en.pdf. Quote from WRT Report: "In 2009-10, ICANN commissioned a study on data accuracy, which was undertaken by the National Opinion Research Council of the University of Chicago (NORC) (the “NORC WHOIS Data Accuracy Study 2009/10”). The study found that only 23% of WHOIS records met the study’s criteria for No Failure, and over 20% were categorized as Full Failure or Substantial Failure. Concerns about the accuracy of WHOIS records were raised in a number of responses to the WHOIS Review Team’s public Discussion Paper and in public sessions at four ICANN meetings." | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially to create a global outreach & communications plan so that WHOIS obligations will be widely known, whether by registrants or users of WHOIS services. One of the root causes of inaccuracies in WHOIS records is the apparent lack of understanding of these obligations. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT believed that "The low level of accurate WHOIS data is unacceptable, and decreases consumer trust in WHOIS, in the industry which ICANN provides rules for and coordinates, and therefore in ICANN itself. The organization’s priority in relation to WHOIS should be to improve WHOIS data accuracy and sustain improvement over time…The WHOIS Data Reminder Policy is ineffective in achieving its goal of improving accuracy of data." | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is to ensure that registrants and users of WHOIS information are knowledgeable of how to access information, report inaccuracies, and maintain accurate information for their domain names in an effort to improve accuracy rates on a global basis. | Implementation planning involves several aspects: (1) creating an informational portal to have information more easily available related to WHOIS and reporting inaccuracies, (2) Creating the Registrant Rights & Responsibilities Document to educate registrants on their obligations to maintain the accuracy of WHOIS, (3) establishing a detailed communications plan with respect to the WHOIS portal and registrant's obligations for accuracy, and (4) creating an expert working group to develop a blueprint for a new model for delivering data directory services that will be sent to the GNSO Council for further policy development. | In progress. | In progress. | In progress. | N/A | N/A | N/A | N/A | Dependencies include working with the GNSO Council in the PDP process to achieve consensus recommendations for the development of the policies that relate to the work of the EWG. | N/A | For more information, please see: http://www.icann.org/en/news/in-focus/whois-recommendations-implementation
6. ICANN should take appropriate measures to reduce the number of WHOIS registrations that fall into the accuracy groups “Substantial Failure and Full Failure” (as defined by the NORC Data Accuracy Study, 2009/10) by 50% within 12 months and by 50% again over the following 12 months. |  | Online Communications Services; Compliance; Communications | Staff: Chris Gift; Maguy Serad; Jim Trengrove; Lynn Lipinski | Concerns about the accuracy of WHOIS records were raised in a number of responses to the WHOIS Review Team’s public Discussion Paper and in public sessions at four ICANN meetings. | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially to improve the accuracy of the population of WHOIS records by sampling individual records, verifying the accuracy of the record, and then forwarding inaccurate records to Compliance. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT believed that a majority of the WHOIS records are substantially inaccurate. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is to follow-up and follow-thru on the identified WHOIS inaccuracy with the registrars. | In progress and will be implemented in conjunction with the accuracy reporting application and tools. | In progress. | In progress. | In progress -ICANN staff has concerns regarding adopting the NORC definition of accuracy, as it will not be possible to produce the desired outcome with automated tools. If the Substantial Failure and Full Failure measure, as defined by NORC, is adopted, ICANN will not be able to accomplish this with automation and further discussion is required. | In progress. | In progress. | In progress. | In progress. | In progress. | N/A. | For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
7. ICANN shall produce and publish an accuracy report focused on measured reduction in WHOIS registrations that fall into the accuracy groups “Substantial Failure and Full Failure” on an annual basis. |  | Online Communications Services; Compliance; Communications | Staff: Chris Gift; Maguy Serad; Jim Trengrove; Lynn Lipinski | There is little statistical data available on WHOIS accuracy, and no systematic on-going monitoring to gather metrics regarding whether the accuracy rates are improving. | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially to create easily accessible reports that measure the accuracy of the population of WHOIS records. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT believed that there is no clear and shared understanding on the level of accuracy within WHOIS records. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is to provide the community with data and information on WHOIS accuracy based on sound statistical analysis of global WHOIS records. | In progress -- ICANN is currently considering developing applications that can provide dynamic reporting, accessible and useable by anyone with a browser. | In progress. | In progress. | In progress - ICANN staff has concerns regarding adopting the NORC definition of accuracy, as it will not be possible to produce the desired outcome with automated tools. If the Substantial Failure and Full Failure measure, as defined by NORC, is adopted, ICANN will not be able to accomplish this with automation and further discussion is required. | In progress. | In progress. | In progress. | In progress. | In progress. | N/A. | For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
8. ICANN should ensure that there is a clear, unambiguous and enforceable chain of contractual agreements with registries, registrars, and registrants to require the provision and maintenance of accurate WHOIS data; agreements should ensure that clear, enforceable and graduated sanctions apply to registries, registrars and registrants that do not comply with its WHOIS policies; sanctions should include de-registration and/or deaccreditation in cases of serious or serial noncompliance. |  | Online Communications Services; Compliance; Communications | Staff: Margie Milam | The current registrar and registry agreements. | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially for Contractual Compliance to follow the process with the registrars to "investigate and correct" the identified WHOIS inaccuracies. Additionally, for the RAA negotiation process to find ways to improve WHOIS accuracy, and as per (1) above is initiating a PDP to reform the WHOIS policy to support the objectives and balance the concerns of the multi-stakeholder community. | The current agreements are not as clear when it comes to WHOIS related obligations. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is improved contractual framework to support ICANN's Compliance Function. | Staff went through an extensive internal process to identify areas to improve the registry and registrar agreements. The outcome of this effort led to the additional negotiation topics for the RAA negotiations and the new gTLD Registry Agreements. | 50% as the Proposed Final RAA is currently open for public comment, and the new gTLD Registry Agreement is expected to be finalized shortly. | In progress. | ICANN received resistance from the contracted parties during negotiations resulted in language that differed from original proposals. | See above related to the EWG work. | N/A | N/A | N/A | Getting the contracted parties to agree to the new language, and to enforce the obligations with respect to the registrants. | More vigorous advocacy of amendment to the RAA to enhance the contractual framework surrounding WHOIS. | For more information, please see: http://www.icann.org/en/news/public-comment/proposed-raa-22apr13-en.htm For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
9. Board should ensure that the Compliance Team develop metrics to track the impact of the annual WHOIS Data Reminder Policy (WDRP) notices to registrants; metrics should be used to As per (1) above, the Board will initiate a policy on the purpose of the gTLD WHOIS service, and this will help drive the principles behind privacy/proxy develop and publish performance targets, to improve data accuracy over time; if this is unfeasible, Board should ensure that an alternative, effective policy is developed and implemented that achieves the objective of improving data quality, in a measurable way. |  | Online Communications Services; Compliance; Communications | Staff: Chris Gift; Maguy Serad; Jim Trengrove; Lynn Lipinski | Staff understood the baseline to be the current situation where there are very few contractual obligations that relate to WHOIS accuracy. One of the current policies that relate to accuracy is the WDRP, for which ICANN has not historically collected data with regard to its effectiveness. | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially to find ways to track WHOIS accuracy, and to make changes wherever possible in contracts or to initiate policy work in order to achieve the desired result. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT believed that there was a need to establish a baseline in order to track whether Staff's implementation of the WHOIS RT recommendations will lead to the desired improvement in WHOIS accuracy. In addition, there is a need for ICANN to collect and provide visibility into whether accuracy rates are improving over time. | The desired outcome is improved communication of WHOIS related obligations, tracking of the accuracy rates, with an overall goal of increasing WHOIS accuracy rates. | No further action required here per board direction as it relates to the impact of the annual WHOIS Data Reminder Policy - The WRT recommendation as stated is not feasible. The policy only requires registrars to send the reminder in a specific form including specific information. The WDRP audit focuses on ensuring registrar compliance with the policy requirements. The policy does not require registrars to track changes directly resulting from the reminder. As the WRT noted during previous discussions, neither Compliance nor most registrars have the tools to measure the impact of the annual data reminder notices that registrars send to registrants. Thus, metric reporting has been difficult. ICANN incorporated the WHOIS Data Reminder Policy (WHOIS accuracy) in the Audit Program. As in the past, Registrars must, at least once a year, send a reminder to Registered Name Holders reminding them to verify/update WHOIS data – ICANN to validate that the reminder notices sent and stating consequences for inaccurate WHOIS data. Implementation of this recommendation involved (1) Staff seeking amendments to the RAA and the Registry Agreements to enhance the contractual framework for WHOIS, (2) the creation of the Expert Working Group to create a new policy framework to better address the inadequacies of the current contractual framework; (3) Staff to initiate a process to create an accreditation program for privacy/proxy providers, and work with the GNSO to develop a policy framework for these services, and (2) establishment of the online portal and proactive monitoring to be able to establish some metrics on accuracy over time. | Approximately 20% | In progress. | With respect to contractual changes, push back from the contracted parties on WHOIS related provisions affected the negotiations. | See above related to the EWG work. | In progress. | ICANN received criticism in response to proposed contractual conditions related to implementation of the WHOIS RT recommendations after posting the registry and registrar agreements for public comment. | In progress. | With respect to contractual changes, the dependencies relate to the willingness of the contracted parties to accept corresponding changes to their agreements. With regard to the policy changes, success is dependent upon the ability to achieve consensus in the GNSO for policy changes in the PDP Process. | More vigorous advocacy of amendment to the RAA to enhance the contractual framework surrounding WHOIS. | For more information, please see: http://www.icann.org/en/news/public-comment/proposed-raa-22apr13-en.htm
Data Access – Privacy and Proxy Services
10. ICANN should initiate processes to regulate and oversee privacy and proxy service providers; processes should be developed in consultation with all interested stakeholders and note relevant GNSO studies; a possible approach to achieving this would be to establish an accreditation system for all proxy/privacy service providers, and consider the merits (if any) of establishing or maintaining a distinction between privacy and proxy services; goal is to provide clear, consistent and enforceable requirements for the operation of these services consistent with national laws, and to strike an appropriate balance between stakeholders with competing but legitimate interests -- including privacy, data protection, law enforcement, the industry around law enforcement and the human rights community. A list of objectives for regulation is provided for consideration, including: labeling WHOIS entries made by a privacy or proxy service; providing full WHOIS contact details for the privacy/proxy service provider; adopting agreed standardized relay and reveal processes and timeframes; Registrars should disclose their relationship with any proxy/privacy service provider; maintaining dedicated abuse points of contact for each provider; conducting periodic due diligence checks on customer contact information; maintaining the privacy and integrity of registrations in the event that major problems arise with a privacy/proxy provider; and providing clear and unambiguous guidance on the rights and responsibilities of registered name holders, and how those should be managed in the privacy/proxy environment. | -The Board notes that staff has made the use and accreditation of privacy and proxy providers part of the RAA negotiations. The Board also notes that the GNSO has had discussions about a potential PDP relating to these issues. -The Board notes that staff has initiated community discussions on privacy and proxy “best practices” that will inform next steps. -As per (1) above, the Board will initiate a process to create a straw-man document on the purpose collecting and maintaining gTLD registration data, and this will help guide further policy in this area. | Strategic Initiatives | Staff: Margie Milam | The baseline is that currently there are no policies or rules that apply to privacy or proxy providers. | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially to implement a holistic approach that includes contract enhancements and policy development. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT believed that the lack of any rules or policies related to privacy or proxy services has led to confusion among customers of these services, and an expectation that ICANN can address problems that arise from these services. Without an accreditation program or applicable contract terms, ICANN is unable to meet these expectations. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is the creation of policies, procedures, and rules that create a consistent, minimum set of requirements for the provision of these types of services. | Amendments to the RAA have been proposed and have been agreed to by Registrars in the Proposed Final 2013 RAA posted for comment on 4/23/13. In this Agreement, an Interim Specification on Privacy and Proxy Services creates obligations that apply while ICANN creates the accreditation program and undertakes the policy development processes necessary to create policies supported by the ICANN community. | Approximately 15% | Full implementation is underway, as directed by the Board, and as described. | During the negotiations for the RAA, it was difficult to identify the set of generally accepted principles that should apply to privacy/proxy services. For example, the recommendations state that there should be standardized relay and reveal processes and timelines, but no real guidance on what the standards should be. As a result, these difficult issues are to be turned to the GNSO to evaluate and consider. | N/A, as the implementation has not been fully completed. | N/A, as the implementation has not been fully completed. | There has been general acceptance in the ICANN community for the idea of privacy/proxy accreditation, and the need for further policy work in this regard. | N/A, as the implementation has not been fully completed. | Dependencies include working with the GNSO Council in the PDP process to achieve consensus recommendations for the development of the policies that relate to privacy/proxy services. | N/A | See the Proposed Final 2013 RAA, and its specifications, posted at: http://www.icann.org/en/news/announcements/announcement-22apr13-en.htm For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
Data Access – Common Interface
11. It is recommended that the Internic Service is overhauled to provide enhanced usability for consumers, including the display of full registrant data for all gTLD domain names (whether those gTLDs operate thin or thick WHOIS services); operational improvements should include enhanced promotion of the service to increase user awareness. | See (3) above. | Strategic Initiatives | Staff: Chris Gift | The baseline is the existing Internic site has not improved since its original inception. | Rather than improve Internic, it is our intention to create a site, or place, for individuals and communities with an interest in WHOIS to access a single source of information and data on WHOIS. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT believed that there was a fragmentation of WHOIS terminology, information, and tools which need to consolidated. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is to provide easier access to WHOIS tools and information as well as easy to understand terminology and language for the general public. | Implementation planning involves several aspects: (1) creating an informational portal to have information more easily available related to WHOIS and reporting inaccuracies, (2) Creating the Registrant Rights & Responsibilities Document to educate registrants on their obligations to maintain the accuracy of WHOIS, and (3) establishing a detailed communications plan with respect to the WHOIS portal and registrant's obligations for accuracy. | In progress. | Yes. | In progress. | In progress. | In progress. | In progress. | In progress. | In progress. | In progress. | For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
Internationalized Domain Names
12. ICANN should task a working group within six months of publication of this report, to determine appropriate internationalized domain name registration data requirements and evaluate available solutions; at a minimum, the data requirements should apply to all new gTLDs, and the working group should consider ways to encourage consistency of approach across the gTLD and (on a voluntary basis) ccTLD space; working group should report within a year. | -The Board directs the CEO to have Staff: 1) task a working group to determine the appropriate internationalized domain name registration data requirements, evaluating any relevant recommendations from the SSAC or GNSO; 2) produce a data model that includes (any) requirements for the translation or transliteration of the registration data, taking into account the results of any PDP initiated by the GNSO on translation/ transliteration, and the standardized replacement protocol under development in the IETF’s Web based Extensible Internet Registration Data Working Group; 3) incorporate the data model in the relevant Registrar and Registry agreements within 6 months of adoption of the working group’s recommendations by the ICANN Board or put explicit placeholders in place for gTLD program agreements, and existing agreements; 4) valuate available solutions (including solutions being implemented by ccTLDs), and 5) to provide regular updates on technical development of the IRD, including the estimated timeline or roadmap of such technical development, so that the ICANN community, particularly the IDN gTLD applicant, can fully prepare for implementation of IRD features in its operation. -As per (5) above, the CEO to investigate using automated tools to identify potentially inaccurate internationalized gTLD domain name registration data in gTLD registry and registrar services, and forward potentially inaccurate records to gTLD registrars for action. | Online Communications Services; Policy Development | Staff: Chris Gift, Steve Sheng | No requirements exist today for internationalized registration data. Registries deploy different solutions. | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially to: 1) to work with the community to determine appropriate internationalized domain name registration data requirements; 2) evaluate available solutions; 3) require the data requirement apply to all new gTLDs; 4) consider ways to encourage consistency of approach across the gTLD and (on a voluntary basis) ccTLD space. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT believed that registries today deploy various ad hoc solutions for internationalized data, the lack of consistency creates a bad user experience. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is a requirement for internationalized domain name registration data. | As requested by the WHOIS RT, ICANN will form a working group to determine the requirements. | In progress. | In progress. | In progress. | In progress. | In progress. | In progress. | In progress. | In progress. | N/A | For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
13. The final data model, including (any) requirements for the translation or transliteration of the registration data, should be incorporated in relevant Registrar & Registry agreements within 6 months of Board adoption of working group’s recommendations, or put explicit placeholders in the new gTLD program agreements, & in existing agreements when they come up for renewal. |  | Online Communications Services; Policy Development | Staff: Chris Gift, Steve Sheng | No standards exist for the translation/transliteration of registration data. | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially to develop a model that also takes into account the translation/transliteration of registration data. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT believed that lack of clarity for how WHOIS is to evolve to address IDN issues. | Data Model that addresses IDN information, and incorporate findings in the Registry or Registrar Agreements, wherever located. | In progress. Placeholders have been incorporated into the RAA and the new gTLD Registry Agreements. | In progress. | In progress. | Awaiting GNSO policy on translation or transliteration. | N/A | N/A | N/A | N/A | GNSO policy development resulting from the PDP on translation/transliteration. | N/A | See: http://gnso.icann.org/en/issues/gtlds/transliteration-contact-final-21mar13-en.pdf and http://newgtlds.icann.org/eN/Applicants/agb/base-agreement-specs-05feb13-en.pdf For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
14. Metrics should be developed to maintain and measure the accuracy of the internationalized registration data and corresponding data in ASCII, with clearly defined compliance methods and targets. |  | Online Communications Services; Policy Development | Staff: Chris Gift, Steve Sheng | There is no reporting on accuracy of WHOIS records for international domain names. | Create applications and reports to provide analysis of accuracy of the WHOIS records for international domain names. | There is no clear and shared understanding on the level of accuracy within international domain names WHOIS records. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is easier access to WHOIS tools and information as well as easy to understand terminology and language for the general public. | In progress - Currently evaluating how to achieve these metrics. ICANN is awaiting definitions of the standard IDN WHOIS record to be published. | 0% | Unsure at this time. IDN WHOIS records will skew towards countries where automated address verification will be more difficult and costly. More information will be known in August, 2013. | In progress. | In progress. | In progress. | In progress. | In progress. | In progress. | N/A | For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8.
Detailed and Comprehensive Plan
15. ICANN should provide a detailed and comprehensive plan within 3 months after the submission of the Final WHOIS Review Team report that outlines how ICANN will move forward in implementing these recommendations. | -As per (1) above, the Board agrees that gTLD WHOIS should be a strategic priority. -The Board directs the CEO to incorporate a work plan for the improvement of WHOIS into the operating plan. | Office of the CEO; Strategic Initiatives | Staff: Denise Michel; Margie Milam | N/A | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially to develop a comprehensive plan to be communicated to the ICANN community for Board approval. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT wanted to ensure that ICANN provided transparency into the implementation of its detailed recommendations. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is s complete implementation of each and every recommendation, based on the direction from the Board. | An initial proposed plan was provided to the Board for its consideration prior to its November 2012 meeting. Subsequent updated implementation plans have been posted and publicly discussed. | Complete. | Yes. It should be noted that the delivery date included in this recommendation was not implementable, as the Board did not approve the WHOIS Review Team Report and direct implementation until 6 months after the submission of the Report. | No | No | Implementation is ongoing. | The feedback has generally been positive, although there are some members of the WHOIS RT that expressed disappointment in that their view that the Board did not accept the Report's findings in the same way that it accepted the findings of the initial ATRT Report. | The result is that there is much more clarity and visibility on how the WHOIS RT recommendations are to be implemented. | Staff needed to undergo a series of internal cross-functional meetings to ensure that the appropriate executives were given responsibility to implement each recommendation. | Overall management of the WHOIS RT Recommendations was assigned to the Strategic Initiatives Department under Denise Michel, in order to coordinate all of the various aspects of the Plan. | For more information, please see: http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8. http://www.icann.org/en/news/public-comment/base-agreement-29apr13-en.htm
Annual Status Reports
16. ICANN should provide at least annual written status reports on its progress towards implementing the recommendations of this WHOIS Review Team. The first of these reports should be published one year, at the latest, after ICANN publishes the implementation plan mentioned in recommendation 15, above. | - The Board directs the CEO to provide resources and budget to carryout these activities, to provide annual public reports on implementation of these activities and related efforts. | Office of the CEO; Strategic Initiatives | Staff: Denise Michel; Margie Milam | N/A | Staff understood the recommendation to be as stated in the WHOIS RT Final Report and the Board's Resolution and Supporting Board Materials -- essentially to prepare Annual Status Reports detailing the progress of the recommendations. | Staff understood the issue to be as stated in the WHOIS RT Final Report -- that, in general, the WHOIS RT wanted to ensure that ICANN provided transparency into the implementation of its detailed recommendations. | Staff understood the desired outcome to be what was articulated in the WHOIS RT Final Report and Board Resolution and Supporting Material. In general, the expected outcome is Annual Status Reports made available to the ICANN Community. | N/A | 0%, as this item is not due yet | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Overall management of the WHOIS RT Recommendations was assigned to the Strategic Initiatives Department under Denise Michel, in order to coordinate all of the various aspects of the Plan. | For more details on the implementation, please see: <blog.icann.org/2013/03/whois-whats-to-come/>; the Board Resolution on the WHOIS Policy Review Team Report <http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a>; and the supporting Board material <http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf>, which includes an Annex with Board direction starting on page 8. http://www.icann.org/en/news/public-comment/base-agreement-29apr13-en.htm

## Reference Materials
Reference Materials
Document | Link
WHOIS Policy Review Team Final Report, May 2012 | http://www.icann.org/en/about/aoc-review/whois/final-report-11may12-en.pdf
Adopted Board Resolution on WHOIS Policy Review Team Final Report, November 2012 | http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm#1.a
Board Briefing Materials on WHOIS Policy Review Team Final Report, November 2012 | http://www.icann.org/en/groups/board/documents/briefing-materials-1-08nov12-en.pdf
Preliminary Report - Special Meeting of the ICANN Board, November 2012 | http://www.icann.org/en/groups/board/documents/prelim-report-08nov12-en.htm
Blog post "WHOIS & What's to come" | http://blog.icann.org/2013/03/whois-whats-to-come/
Blog post: "Single Source of Whois-Related Agreement Provisions and Policies", April 2013 | http://blog.icann.org/2013/04/single-source-of-whois-related-agreement-provisions-and-policies/
Announcement: "New ICANN CEO is Out of the Blocks with Ambitious Operational Plans", Seotember 2012 | http://www.icann.org/en/news/announcements/announcement-14sep12-en.htm
Adopted Board Resolution on Contractual Compliance Audit Program, October 2012 | http://www.icann.org/en/groups/board/documents/resolutions-03oct12-en.htm#1.d
Webinar on WHOIS Policy Review Team Recommendations - Implementation Update, April 2013 | http://www.icann.org/en/news/in-focus/whois-recommendations-implementation
Public Comment Period: Proposed Final 2013 RAA | http://www.icann.org/en/news/public-comment/proposed-raa-22apr13-en.htm
Final Issue Report Translation and Transliteration of Contact Information, March 2013 | http://gnso.icann.org/en/issues/gtlds/transliteration-contact-final-21mar13-en.pdf
Proposed Final New gTLD Registry Agreement, April 2013 | http://www.icann.org/en/news/public-comment/base-agreement-29apr13-en.htm
Draft New gTLD Registry Agreement, February 2013 | http://newgtlds.icann.org/en/applicants/agb/base-agreement-specs-05feb13-en.pdf