## ATRT1
ATRT1 Recommendations | Implementation Assignments |  | F. Percentage/portion that is complete? | G. Does s/he believe ICANN fully implemented the recommendation? If not, why not? If not, what parts were not implemented, and why not? | I. Did s/he identify additional opportunities for improvement by virtue of the implementation of these recommendations? | J. What has been the outcome and effect both inside ICANN and external to ICANN as a result of the implementation of the recommendation? | L. How does s/he feel that ICANN has improved as a result of the implementation of the recommendation? | N. In view of ATRT1 what changes in workflows and/or organization where undertaken? | ATRT2 Recommendation?
Public Input & Multilingual Access - 9.1 (c)
15. Implement stratified, prioritized public Notice & Comment processes. | Board/PPC | Sébastien Bachollet/Chris Disspain | [6 empty] | Missing data?
| Staff: Policy | David Olive/Sally Costerton/Chris Gift | Please see 2012 Implementation Summary re: ATRT Rec. No. 15 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). 100% (1 Jan 2012) as proposed by Staff and amended based upon Focus Group and Public Comment community feedback. | Yes - all parts were implemented as planned. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No additional opportunities for improvement were identified relative to this specific recommendation; however, now that it has been implemented for a full year, Staff suggests that the community be asked, perhaps via a survey instrument, whether the Stratification and Prioritization enhancements have provided value and whether any additional improvements are advisable. | Each Public Comments solicitation is now categorized (16 subject areas) to help the community with participation decisions; additional fields are also available to help explain context and relative importance. There are no formal metrics to gauge the effect or outcome of stratifying Public Comments. Now that this enhancement has been in place for over a year, Staff recommends that the community be asked (e.g., via survey instrument) to assess the value of the stratification enhancement and the supplemental prioritization information. | With respect to Rec #15, data has not yet been collected concerning the extent to which these enhancements have improved ICANN's process for Public Comments. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | New Staff Guidelines were published including standard templates to capture the appropriate category(ies), status, next steps, et al., pertaining to this recommendation. | Definitely needed / See input from the Community
16. & 17. Provide “Comment” cycle & a “Reply Comment” comment cycles; review and adjust fixed timelines for Notice & Comment | Board/PPC | Sébastien Bachollet/Chis Disspain | [6 empty] | Missing Data?
| Staff: Policy | David Olive/Sally Costerton/Chris Gift | Please see 2012 Implementation Summary re: ATRT Rec. Nos. 16 and 17 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). 100% (1 Jan 2012) as proposed by Staff and amended based upon Focus Group and Public Comment community feedback. | Yes - all parts were implemented as planned. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Staff identified and tested a potential replacement technical solution (Confluence Wiki) for Public Comments that would permit dynamic threading (comments and replies) vs. static email submissions. That project was not formally evaluated for implementation due to other important organizational priorities at the time (2012); however, it remains a viable alternative for future consideration. | A formal study of the Public Comments experience from 2010-2012 has recently been completed including supported inferences concerning the effectiveness of the Reply Cycle implementation. It is clear from the data analysis that a majority (over 70%) of Reply submissions were not related to any prior Comment; rather, were forwarded after the initial period ended. One hypothesis to be further evaluated is whether some community members may be utilizing the Reply Cycle as a virtual extension of the initial Comment period. | An analysis of the Public Comments experience from 2010-2012 has recently been completed including supported inferences concerning the effectiveness of the Reply Cycle implementation. The data analysis shows that a majority (over 70%) of Reply submissions were not related to any prior Comment; rather, were forwarded after the initial period ended. The Comment/Reply Cycle enhancement appears to require further study to improve its effectiveness within the overall Public Comments process. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | New Staff Guidelines were published including standard templates/flowcharts to simply presentation and formally document roles/responsibilities. The Guidelines encourage Staff members to extend the timeframes for Comment/Reply Cycles based upon perceived topic complexity and/or to accommodate community needs. | Definitely needed / See input from the Community
18. Ensure multilingual access in PDP to maximum extent feasible | Board/PPC | Sébastien Bachollet |  |  |  | · |  |  | Missing Data?
| Staff: Communications | Christina Rodriquez | Please see 2012 Implementation Summary re: ATRT Rec. No. 18 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). The implementation plan for this recommendation is 100% complete. Follow-up work to fully implement the LSPP throughout the organization is ongoing. | Yes. One of the first accomplishments was the creation and approval by the Board of the Language Services Policy and Procedures document. The ATRT1 recommendation to “Enhance Multilingual Strategy” also added significant improvements (more interpretation support, transcription support, teleconference interpretation). Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Yes, one of them being the provision of teleconference interpretation support by our own team of interpreters | One outcome was a substantial increase in work and resulted in the need to create better processes. Also, it has demonstrated a clear need to switch from a translation function to a translation department to attend to all of the needs, external and internal. | The provision of translated material is more organized, and ICANN attends to the needs and requests from the community. ICANN also has laid the path toward more effective engagement with global stakeholders. | Many changes and new processes and workflows were created to provide better language support. | Translations still need much time. Is there an open indication tracking system for translations?
21. Create annual public comment forecast | Board/PPC | Sébastien Bachollet/Chris Disspain | [6 empty] | Missing Data?
| Staff: Policy | David Olive/Sally Costerton/Chris Gift | Please see 2012 Implementation Summary re: ATRT Rec. No. 21 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). 100% (1 July 2011) as originally developed by Staff including guidelines, procedures, and flowcharts for ongoing administration. [Note: the annual update process was not completed in Dec 2012 per the guidelines. Staff is currently simplifying the process and templates and expects to launch another formal refresh cycle shortly.] | Yes - all parts were implemented as originally proposed. [Note: the annual update process was not completed in Dec 2012 per the guidelines. Staff is currently simplifying the process and templates and expects to launch another formal refresh cycle shortly.] Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | As a result of a missed opportunity (Dec 2012) to refresh the annual Upcoming Topics data, Staff is currently revising the process and template to operate on a trimester schedule. A refresh cycle is expected to commence shortly once the process has been put in place. Staff also recommends that, after another six months experience, the community be asked for its feedback on the value of publishing Upcoming Topics. | There are no formal metrics to gauge the effect or outcome of publishing Upcoming Public Comments topics. There is anecdotal evidence that some community members perceive value in consulting the Upcoming topics list; however, a formal study should be undertaken approximately six months after the information has been refreshed. | With respect to Rec #21, data has not yet been collected concerning the extent to which this enhancement has improved the overall Public Comments process. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | New Staff Guidelines were published including standard templates/flowcharts to collect and update Upcoming Topics on an annual basis. [Note: Staff is currently revising the process and template to operate on a trimester basis. A new data refresh cycle will be launched once the modified process has put in place.] | No
22. Ensure senior staffing arrangements are appropriately multilingual | Staff: HR | Steve Antonoff | Complete. Please see 2012 Implementation Summary re: ATRT Rec. No. 22 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | Yes Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No | Senior staff is significantly more multilingual. It is hard to measure the external effect. | We have demonstrated an ongoing commitment to transforming ICANN into a more global organization. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Job postings modified, interview process modified | Metrics?

## Reference Materials
Reference Materials
Document | Link
Accountability & Transparency Review Team 1 (ATRT1) Final Report and Recommendations, January 2010 | https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf
ATRT Recommendations - Proposed Implementation Plans; Ocotber 2011 | http://www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf
ATRT Implementation Summary Report 2012 | www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf
2012 Annual Report - Implementation of the Accountability & Transparency Review Team Report; January 2013 | http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf
NomCom web site | http://nomcom.icann.org/
ICANN 2012 NOMCOM FINAL REPORT | http://nomcom.icann.org/nomcom-final-report-08oct12-en.pdf
Adopted Board Resolution - Chair Remuneration, August 2013 | http://www.icann.org/en/groups/board/documents/resolutions-05aug10-en.htm#5
Community Input Advice Framework, September 2012 | www.icann.org/en/news/in-focus/accountability/input-advice-function-24sep12-en.pdf
Policy vs. Implementation Public Comment Period, January 2013 | http://www.icann.org/en/news/public-comment/policy-implementation-31jan13-en.htm
ICANN Accountability & Transparency | http://www.icann.org/en/news/in-focus/accountability
FY12 Operating Plan and Budget Fiscal Year Ending 30 June 2012, adopted 24 June 2011 | http://www.icann.org/en/financials/adopted-opplan-budget-fy12-09sep11-en.pdf
GAC High Level Meeting, Toronto - October 2013 | http://toronto45.icann.org/gac-hlm
JWG Final Report & Public Comment Forum, July 2011 | http://www.icann.org/en/news/announcements/announcement-07jul11-en.htm
Revised GAC Operating Principles | https://gacweb.icann.org/display/gacweb/Core+Principles
Publication of what constitutes GAC advice, July 2011 | http://www.icann.org/en/news/announcements/announcement-07jul11-en.htm