Webinars Preparation Check List

|  | Action | Time |
| --- | --- | --- |
| Webinar Team | Selects the topic, Identifies the objectives, confirms the topic is within ICANN remit. | At least 5-6 weeks prior to webinar date |
|  | Confirm date and time of the webinar | 4 weeks prior to the webinar |
|  | Ensure speakers have submitted the webinar description and objectives as well as the biography and head photos to staff | 4-3 weeks prior to the webinar |
|  | Confirm promotional Material sent by the social media team | 3-2 weeks prior to the webinar |
|  | Send promotional Material to staff to start advertising the webinar | 3-2 weeks prior to the webinar |
|  | Confirm receiving the communication information from the relevant social media co-chair – pre ICANN webinars | 3-2 weeks prior to the webinar |
|  | Coordinate practice sessions with speakers and staff if required | No later than 1 week prior to the webinar |
|  | Confirm that staff has received the slide deck and quiz questions | 3 working days prior to the webinar |
| Staff | Use the webinar’s team invitation template to send an invitation letter to the speaker/s to formally confirm their availability and commitment to deliver the webinar. | 5 weeks prior to the webinar |
|  | Add topic to the webinar wiki page, with the confirmed date and time | 4 weeks prior to the webinar |
|  | Use the webinar’s team confirmation template to send a follow-up email to the speaker/s. The follow-up email should include instructional content and a deadline for delivery, along with authorization to use ‘head photos’ and biography in all the webinars promotional materials. To send along with the confirmation letter best practice suggestions in relation to using the zoom video during the webinar. ( In case the speaker/s wishes to use their video) Schedule a zoom practice session for the speaker if required. | Upon receive of speakers’ confirmation – 4 weeks prior to the proposed date. |
|  | Send the received webinar description, objectives, biography and ‘head photos’ to the Social Media Team | 3 weeks prior to the webinar |
|  | Confirm that the slide deck and quiz questions have been received. | 3 working-days prior to the webinar |
| Staff | Start advertising the webinar using the material prepared by the social media team and confirmed by the webinar team | 3-2 weeks prior to the webinar |
|  | Confirm receiving the communication information from the social media co-chair = pre ICANN webinars | 3-2 weeks prior to the webinar |
| Social Media Team | Start designing the promotional materials | 3 weeks prior to the webinar |
|  | Send promotional material to the webinar team for confirmation | 3-2 weeks prior to the webinar |
|  | Social Media co-chair – depending on the region – picks the appropriate communication & outreach strategies. That includes, corresponding 1) hashtags, 2) graphics for engagement, 3) At-Large pre-ICANN69 Webinar and communicates this information to the staff and webinar team. | 3-2 weeks prior to the webinar |