{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1904","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":58,"n_cols":17,"rows_kept":58,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[null,"Dates in months","2011-10-01","2011-11-01","2011-12-01"," January 2012","2012-02-01","2012-03-01","2012-04-01","2012-05-01","2012-06-01","2012-07-01","2012-08-01","2012-09-01","2012-10-01","2012-11-01","2012-12-01"]
[]
[null,"(ICANN meetings)","ICANN 42 (23-28)Dakar",{"$nulls":4},"ICANN 43 (11-16)     San Jose",null,null,"ICANN 44 (24-29) Prague",null,null,null,"ICANN 45 (14-19) Toronto"]
["Tasks and events"]
[]
["ccNSO coordination"]
["ccNSO Workplan  ",null,"No Review activties and update","Review activties and update",null,"Review activites and update plan","Review activites and update plan","Review Work Plan Present to community & adopt workplan","Review activites and update","Review activites and update","Review activites and update","Review activites and update","Review activites and update","Review activites and update","Review activites and update"]
["GAC-ccNSO Liaison WG"]
["Liaison GNSO-ccNSO",null,"Appointment of councillors to act as intermediates",{"$nulls":4},"GNSO-Council meeting",null,null,"GNSO-Council meeting"]
[]
["Administrative activities"]
["Council meetings (conference calls)",null,null,"2011-11-15","2011-12-20","1/10/2011, propose schedule for post Costa Rica","2011-02-14"]
["F-2-F meetings",null,"f-2-f 25 October",{"$nulls":4},"Logistical meeting 11 March Formal meeting 13 Mar",null,null,"Logsitical meeting"]
["Council elections",null,"Elections completed and adopted","Adopt report election manager"]
["Chair and vice chair elections",{"$nulls":6},"Chair and vice-chair election",{"$nulls":4},"appoint Election manager","Call for nominations","Elections","Adopt report election manager"]
["Council Workshops",null,"logistical meeting",{"$nulls":4},"2011-03-10",{"$nulls":6},"13 Ocotber Workshop"]
["Council Roles and responsibilities",{"$nulls":6},"Review and adoption"]
["Board Selection",null,"Elections finshed completed and Board secretary informed"]
["ccNSO Programme meeting WG",null,null,"Appointment of co-chair to liaise between council and WG",null,"Meeting on draft Agenda. Publish draft agenda","Meeting to refine draft and Agenda","Meeting evaluation","Meeting on draft Agenda","Meeting to refine draft and publsih Agenda"]
[]
["Recurring Activities: ICANN Planning"]
["ICANN Strat Plan",null,"Draft Strat Plan + Public comment",null,"Draft Final Strat Plan","ICANN Board Adoption Strat Plan",{"$nulls":4},"Initial presentation","Draft Strat Plan Framework and Public comment","Public comment",null,"Draft Strat Plan + Public comment","ICANN Board Adoption Strat Plan"]
["SOP WG activities",null,"Organise Submission Teams formed","Draft submission prepared and submit","Prepare submission, if any",null,null,"TBC: Strategic Planning session",null,null,null,"Organise submission","Submission of comment",null,"Organsie Submission"]
["ICANN Budget and Ops Plan",null,"Kick-off request for services Ops Plan FY 2013",null,null,null,"Draft Ops Plan Framework FY 2013",null,null,"Publication draft FY 2013 Ops Plan","Adoption FY 2013 Ops Plan"]
["SOP WG activities",null,"No action needed",{"$nulls":4},"Prepare and submit input and feed-back Ops Plan Framework FY 2013 in cooperation with Finace WG",null,"Prepare and submit input and feed-back Draft Ops Plan  FY 2013in cooperation with Fiance WG",{"$nulls":4},"Prepare input on services request"]
["Finance WG",null,"No Action needed",{"$nulls":4},"Prepare submission in coordination with SOP WG",null,"Prepare and submit input and feed-back Draft Ops Plan  FY 2013 in cooperation with Fiance WG"]
[]
["Policy related activities"]
["IDN ccPDP",null,"Council Report  Deferred to Costa Rica ",{"$nulls":6},"Publication of Final Report Issue Manager, inform GAC","Council vote","Members vote"]
["Working group 1",null," Process adjsutment for cnfusingly similarity still under discussion",null,null,"Conclude discussions on process ","Publication of Draft Final report","Discussion Draft Final Report","Submit Final Report to Issue manager"]
["Working group 2",null,"Draft Final Report report publsihed for comment",null,"Adjustment of Rules and Procedures","Submission of Final Report to Issue Manager"]
["Framework of Interpretation WG",null,"Community discussion Interim on Consent Report",null,null,null,"Publication 2nd progress and Interim report and Recomendatioon Consent","Community Discussion, Adoption 1st RoI Report by ccNSO and GAC","Submission 1st RoI Report to the ICANN Board ( chair of the ccNSO)","Publication 3rd progress and Interim Report and 2nd RoI Report","Community Discussion, Adoption 2nd RoI Report by ccNSO and GAC","Submission 2nd RoI Report to the ICANN Board ( chair of the ccNSO)",null,"Publication 4th progress and Interim Report and 3rd RoI Report","Community Discussion, Adoption 3rd RoI Report by ccNSO and GAC","Submission 3rd RoI Report to the ICANN Board ( chair of the ccNSO)"]
["ccPDP on Retirement of ccTLDs","TBD, depending on progress FoI WG"]
["Study Group on Use of Teritory Names",null,"WG discussion on typology. UNESCO involved",null,null,null," Progress Report","Discussion on Typology with communities","Identify issues","second progress report","Fianse Issues","Preapre final reprot and recommendations"]
["Joint IDN workin group (JIG)",null,"Discussion on Single character IDN TLD implementation ",null,"Publication of initial report on universal acceptance of IDN TLD's"]
[]
["ccTLD community related activites"]
["IRI WG",null,null,"Change name of WG",null,null,null,"Present initial results",null,null,"Present final results",null,null,null,"Final Report and recommendations"]
["Finance Working Group ",null,"Initial Discussion of models by WG",{"$nulls":4},"Overveiw of models to community",null,"WG provides report for ccTLD community","Open sessions on report"]
[]
["ccNSO related ICANN activities"]
["Update IDN Guidelines",null,"No action required"]
["IDN Variant Issue Project",null,"Public comment no action required",null,"Publication Overview",null,null,"?"]
["ccNSO related activity other SO or AC"]
["ccNSO Response and Statements"]
[]
["AoC SSR review",null,"No action needed"]
["AoC WHOIS review",null,"No action needed",null,null,"Publication of Final Report","Decision to initiate repsonse","?"]
["SSR Review team",null,"Informational session",null,null,"Publication of Final Report","Decision to intiate response","?"]
["Geographic Regions WG",null,"Drafting Group established",null,"Submission of ccNSO statement",null,null,"?"]
["Joint Activties"]
["DSSA WG",null,"Update provided"]
["Implementation ccNSO improvements"]
["ccNSO review recommendations"]
[]
["Outreach to GAC to increase involvement of Government run ccTLDs in ccNSO",null,"Council ADOPTED Briefing Paper","Inform chair of GAC",null,"Organiise briefing session GAC",null,"Briefing session GAC","Inform SIC"]
["Translation of Documents",null,null,null,"Council to appoint informal council WG on translations","Prepare briefing note on translations for council",null,"Commnunity discussion on translations","Update briefing note",null,"Decision council on translations","Inform SIC"]
["Introduction of coolaborative tools (closed website)",null,"Closed wiki presented. Training work shop by staff","Community invited to learn about wiki","Closure of wiki and invitation to subscribe","Launch of closed wiki",null,"Wiki and ADOBE training",null,null,"Present Process and  use evalaution"]