## ccNSO Review Prep Calendar
ccNSO ORGANIZATIONAL REVIEW
Possible Review Prep Timeline
| Work items in the below phases may be carried out via email, or during teleconference/in-person meetings (Adobe Connect services will be provided). Review plans continuously aligned with community workload and flexibility to accommodate extensions, when necessary. | 2017 |  |  |  | 2018 | [11 empty] | 2019
|  | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | completed
|  | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | planned
|  |  | 60 |  |  |  |  | 61 |  |  | 62 |  |  |  | 63 |  |  |  |  | 64 |  |  | 65 |  |  |  |  | 66
1. Pre-Planning
Board resolution | bar: SEP
Appoint ICANN org project lead | bar: DEC
SO/AC forms Review Working Party | bar: FEB
2. Planning
SO/AC selects review leadership team | bar: FEB
MSSI / RWP kick-off call | bar: FEB
ICANN org + RWP + OEC discuss scope | bar: FEB to MAR
ICANN org develops RFP Overview | bar: FEB to MAR
ICANN org Procurement develops RFP draft | bar: MAR
RWP provides feedback on RFP draft | bar: MAR
OEC approves key elements of RFP = RFP finalized | bar: MAR
3. Select Independent Examiner
ICANN org solicits proposals from RFP bidders | bar: APR to JUN
ICANN org collects & analyzes proposals | bar: JUN
ICANN org IDs finalist, seeks OEC confirmation | bar: JUL
OEC reviews scorecards, confirms IE selection | bar: JUL
IE executes agreement with ICANN | bar: JUL to AUG
ICANN org announces IE agreement | bar: JUL to AUG
4. Conduct Review / Perform Assessment
Review prep session @ ICANN62 | bar: JUN
RWP delivers self-assessement document | bar: JUN
IE holds kickoff sessions with ICANN org and RWP | bar: JUL