{"text_format":"2","workbook":"xls","n_sheets":2,"sheets":["Sheet1","Sheet2"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1904","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":58,"n_cols":22,"rows_kept":58,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[null,"Dates in months","2011-05-01","2011-06-01","2011-07-01","2011-08-01","2011-09-01","2011-10-01","2011-11-01","2011-12-01"," January 2012","2012-02-01","2012-03-01","2012-04-01","2012-05-01","2012-06-01","2012-07-01","2012-08-01","2012-09-01","2012-10-01","2012-11-01","2012-12-01"]
[]
[null,"(ICANN meetings)",null,"ICANN 41(19-24) Singapore",null,null,null,"ICANN 42 (23-28)Dakar",{"$nulls":4},"ICANN 43 (11-16)",null,null,"ICANN 44 (24-29)",null,null,null,"ICANN 45 (14-19) Toronto"]
["Tasks and events"]
[]
["ccNSO coordination"]
["ccNSO Workplan  ",null,"Draft workplan complete, buy-in WG chairs","Present to community",null,"Adopt workplan","Update Work plan, buy-in WG chairs","Review Workplan",{"$nulls":10},"Update Workplan, buy-in WG chairs","Present to community & adopt workplan"]
["GAC-ccNSO Liaison WG",null,null,"TBD"]
["Liaison GNSO-ccNSO",null,null,"TBD"]
[]
["Administrative activities"]
["Council meetings (conference calls)",null,"2011-05-12","2011-06-07",null,"2011-08-23","2011-09-27",null,"2011-11-15","2011-12-20","2011-01-10","2011-02-14"]
["F-2-F meetings",null,null,"f-2-f 21 June",null,null,null,"f-2-f 25 October",{"$nulls":4},"f-2-f 13 Mar"]
["Council elections"]
["Chair and vice chair elections",{"$nulls":4},"Appoint Election manager","Call for nominations","Elections","Adopt report election manager",null,null,null,"Chair and vice-chair election",{"$nulls":4},"appoint Election manager","Call for nominations","Elections","Adopt report election manager"]
["Council Workshops",null,null,"informal 19 June",null,null,null,"2011-10-22",{"$nulls":4},"2011-03-10",null,null,"23 June workshop",null,null,null,"13 Ocotber Workshop"]
["Council Roles and responsibilities",{"$nulls":11},"Review and adoption"]
["Board Selection",{"$nulls":4},"Appoint Election Manager","Call for Nominations","Elections finshed","Select Board member"]
["ccNSO Programme meeting WG",null,"Publish draft agenda",null,null,"Meetings draft agenda ","Meeting on draft and publsih agenda",null,null,null,"Meeting on draft Agenda","Meeting on draft and publsih Agenda"]
[]
["Recurring Activities: ICANN Planning"]
["ICANN Strat Plan",null,null,"Initial presentation","Draft Strat Plan Framework and Public comment","Public comment",null,"Draft Strat Plan + Public comment","ICANN Board Adoption Strat Plan",{"$nulls":6},"Initial presentation","Draft Strat Plan Framework and Public comment","Public comment",null,"Draft Strat Plan + Public comment","ICANN Board Adoption Strat Plan"]
["SOP WG activities",null,null,null,"Organise submission","Submission of comment",null,"Organsie Submission",{"$nulls":8},"Organise submission","Submission of comment",null,"Organsie Submission"]
["ICANN Budget and Ops Plan",null,"Draft Ops Plan","Adoption Ops Plan",null,null,null,"Kick-off request for services Ops Plan FY 2013",null,null,null,"Draft Ops Plan Framework FY 2013",null,null,"Publication draft FY 2013 Ops Plan","Adoption FY 2013 Ops Plan"]
["SOP WG activities",null,"18 May meeting start public comment input","Closure Public comment Mid June",null,null,null,"Prepare input on services request",{"$nulls":4},"Prepare and submit input and feed-back Ops Plan Framework FY 2013",null,"Prepare and submit input and feed-back Draft Ops Plan  FY 2013",{"$nulls":4},"Prepare input on services request"]
["Finance WG"]
[]
["Policy related activities"]
["IDN ccPDP",null,null,"Split IDN ccPDP (Council decision)",null,null,null,"Council Report ","Members vote on inclusion of IDN ccTLD's","Members Vote","Revisit Hybernation of IDN ccPDP WG 2","Final Board Report"]
["Working group 1",null,null,"Propose guidelines for confusing similarity","Hybernation",{"$nulls":5},"Reconvene? Propose new chair?"]
["Working group 2",null,null,"Propose method for voting + Interim Paper on Rules and Guidelines",null,null,"Publsih Final Report ","Council adoption of Final Report","ccNSO Members vote on Final Report",null,"Adoptiion Baord report by ccNSO Council","Submission Board Report to the Board (chair ccNSO)"]
["Framework of Interpretation WG",null,"Establishing WG","Presntation Work Plan","WG meetings","WG meetings","Publication first progress and Interim report","Community discussion Interim Report",null,null,null,"Publication 2nd progress and Interim report and 1st Recoomendations of Interpretation ( RoI Report","Community Discussion, Adoption 1st RoI Report by ccNSO and GAC","Submission 1st RoI Report to the ICANN Board ( chair of the ccNSO)","Publication 3rd progress and Interim Report and 2nd RoI Report","Community Discussion, Adoption 2nd RoI Report by ccNSO and GAC","Submission 2nd RoI Report to the ICANN Board ( chair of the ccNSO)",null,"Publication 4th progress and Interim Report and 3rd RoI Report","Community Discussion, Adoption 3rd RoI Report by ccNSO and GAC","Submission 3rd RoI Report to the ICANN Board ( chair of the ccNSO)"]
["ccPDP on Retirement of ccTLDs","TBD, depending on progress FoI WG"]
["Study Group on Use of Teritory Names",null,"Nomination of chair, WG meetings","Appointment chairs, Overview of policies",null,null,"Second progress Report","Community discussion of draft recommendations",null,"Draft Final Report "]
["Joint IDN workin group (JIG)",null,null,"Extension mandate, update charter"]
[]
["ccTLD community related activites"]
["IRI WG",null,"Appoint volunteers",null,"Draft Work plan","TBD",{"$nulls":13},"Final Report and recommendations"]
["Finance Working Group ",null,null,"Fact finding Inventory of models, and needed information",null,null,null,"Discussion of models by WG",{"$nulls":4},"Overveiw of models to community",null,"WG provides report for ccTLD community","Open sessions on report"]
[]
["ccNSO related ICANN activities"]
["Update IDN Guidelines"]
["IDN Variant Issue Project"]
["ccNSO related activity other SO or AC"]
["ccNSO Response and Statements"]
["Feed-back and Input ICANN SSR Plan",null,"Draft and submit comments"]
["AoC SSR review"]
["AoC WHOIS review"]
[]
["Joint Activties"]
["DSSA WG",null,null,"Work Plan DSSA WG"]
[]
["Implementation ccNSO improvements"]
["ccNSO review recommendations",null,"Discuss draft workplan (council)","Present to community + Adopt workplan (council)","Inform SIC of workplan"]
["Mechanisms for statements and opinions of cNSO",null,"Draft mechanisms","Present mechanisms to community and Adopt mechanisms","Inform SIC "]
["Outreach to GAC to increase involvement of Government run ccTLDs in ccNSO",{"$nulls":4},"Prepare briefing document on benefits and costs of joining the ccNSO","Organiise briefing session GAC","Briefing session GAC","Inform SIC"]
["Translation of Documents",{"$nulls":8},"Council to appoint informal council WG on translations","Prepare briefing note on translations for council",null,"Commnunity discussion on translations","Update briefing note",null,"Decision council on translations","Inform SIC"]
["Introduction of coolaborative tools (closed website)",null,"Council decision on closed website","Training WiKI and ADOBE Connect",null,"Develop requirements ( Support staff) in close cooperation with community","Intitate implementation of wiki or closed section","Present closed wiki for ccTLD community"]

{"sheet":"Sheet2","index":1,"n_rows":64,"n_cols":40,"rows_kept":64,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[null,"Dates in months","2011-05-01","2011-06-01","2011-07-01","2011-08-01","2011-09-01","2011-10-01","2011-11-01","2011-12-01"," January 2012","2012-02-01","2012-03-01","2012-04-01","2012-05-01","2012-06-01","2012-07-01","2012-08-01","2012-09-01","2012-10-01","2012-11-01","2012-12-01","2013-01-01","2013-02-01","2013-03-01","2013-04-01","2013-05-01","2013-06-01","2013-07-01","2013-08-01","2013-09-01","2013-10-01","2013-11-01","2013-12-01","2014-01-01","2014-02-01","2014-03-01","2014-04-01","2011-05-14","2014-06-01"]
[]
[null,"(ICANN meetings)",null,"ICANN 41(19-24) Singapore",null,null,null,"ICANN 42 (23-28)Dakar",{"$nulls":4},"ICANN 43 (11-16)",null,null,"ICANN 44 (24-29)",null,null,null,"ICANN 45 (14-19) Toronto",{"$nulls":5},"ICANN 46 (7-12)",null,null,"ICANN 47 (14-19)",null,null,null,"ICANN 48 (17-22)",null,null,null,"ICANN 49 (23-28)",null,null,"ICANN 50 (22-27)"]
["Tasks and events"]
[]
["ccNSO coordination"]
["ccNSO Workplan  ",null,"Draft workplan complete, buy-in WG chairs","Present to community",null,"Adopt workplan","Update Work plan, buy-in WG chairs","Review Workplan",{"$nulls":10},"Update Workplan, buy-in WG chairs","Present to community & adopt workplan",{"$nulls":11},"Update workplan ","Present to community & adopt workplan"]
["GAC-ccNSO Liaison WG",null,null,"TBD"]
["Liaison GNSO-ccNSO",null,null,"TBD"]
[]
["Administrative activities"]
["Council meetings (conference calls)",null,"2011-05-12","2011-06-07",null,"2011-08-23","2011-09-27",null,"2011-11-15","2011-12-20","2011-01-10","2011-02-14"]
["F-2-F meetings",null,null,"f-2-f 21 June",null,null,null,"f-2-f 25 October",{"$nulls":4},"f-2-f 13 Mar"]
["Council elections"]
["Chair and vice chair elections",{"$nulls":4},"Appoint Election manager","Call for nominations","Elections","Adopt report election manager",null,null,null,"Chair and vice-chair election",{"$nulls":4},"appoint Election manager","Call for nominations","Elections","Adopt report election manager",{"$nulls":4},"Chair and Vice-chair election"]
["Council Workshops",null,null,"informal 19 June",null,null,null,"2011-10-22",{"$nulls":4},"2011-03-10",null,null,"23 June workshop",null,null,null,"13 Ocotber Workshop",{"$nulls":5},"6 April Workshop"]
["Council Roles and responsibilities",{"$nulls":11},"Review and adoption",{"$nulls":12},"Review and adoption"]
["Board Selection",{"$nulls":4},"Appoint Election Manager","Call for Nominations","Elections finshed","Select Board member",{"$nulls":20},"Appoint Eelction Manager","Call for Nominations","Elections finshed","Select Board member"]
["ccNSO Programme meeting WG",null,"Publish draft agenda",null,null,"Meetings draft agenda ","Meeting on draft and publsih agenda",null,null,null,"Meeting on draft Agenda","Meeting on draft and publsih Agenda"]
[]
["Recurring Activities: ICANN Planning"]
["ICANN Strat Plan",null,null,"Initial presentation","Draft Strat Plan Framework and Public comment","Public comment",null,"Draft Strat Plan + Public comment","Adoption Strat Plan",{"$nulls":6},"Initial presentation","Draft Strat Plan Framework and Public comment","Public comment",null,"Draft Strat Plan + Public comment","Adoption Strat Plan",{"$nulls":7},"Initial presentation","Draft Strat Plan Framework and Public comment","Public comment",null,"Draft Strat Plan + Public comment","Adoption Strat Plan"]
["SOP WG activities",null,null,null,"Organise submission","Submission of comment",null,"Organsie Submission",{"$nulls":8},"Organise submission","Submission of comment",null,"Organsie Submission",{"$nulls":9},"Organise submission","Submission of comment",null,"Organsie Submission"]
["ICANN Budget and Ops Plan",null,"Draft Ops Plan","Adoption Ops Plan",null,null,null,"Kick-off request for services Ops Plan FY 2013",null,null,null,"Draft Ops Plan Framework FY 2013",null,null,"Publication draft FY 2013 Ops Plan","Adoption FY 2013 Ops Plan"]
["SOP WG activities",null,"18 May meeting start public comment input","Closure Public comment Mid June",null,null,null,"Prepare input on services request",{"$nulls":4},"Prepare and submit input and feed-back Ops Plan Framework FY 2013",null,"Prepare and submit input and feed-back Draft Ops Plan  FY 2013",{"$nulls":4},"Prepare input on services request",{"$nulls":4},"Prepare and submit input and feed-back Ops Plan Framework FY 2014",null,"Prepare and submit input and feed-back Draft Ops Plan  FY 2014",{"$nulls":5},"Prepare input on services request",{"$nulls":4},"Prepare and submit input and feed-back Ops Plan Framework FY 2015",null,"Prepare and submit input and feed-back Draft Ops Plan  FY 2015"]
["Finance WG"]
[]
["Policy related activities"]
["IDN ccPDP",null,null,"Split IDN ccPDP (Council decision)",null,null,null,"Council Report ","Members vote on inclusion of IDN ccTLD's","Members Vote","Revisit Hybernation of IDN ccPDP WG 2","Final Board Report"]
["Working group 1",null,null,"Propose guidelines for confusing similarity","Hybernation",{"$nulls":5},"Reconvene? Propose new chair?"]
["Working group 2",null,null,"Propose method for voting + Interim Paper on Rules and Guidelines",null,null,"Publsih Final Report ","Council adoption of Final Report","ccNSO Members vote on Final Report",null,"Adoptiion Baord report by ccNSO Council","Submission Board Report to the Board (chair ccNSO)"]
["Framework of Interpretation WG",null,"Establishing WG","Presntation Work Plan","WG meetings","WG meetings","Publication first progress and Interim report","Community discussion Interim Report",null,null,null,"Publication 2nd progress and Interim report and 1st Recoomendations of Interpretation ( RoI Report","Community Discussion, Adoption 1st RoI Report by ccNSO and GAC","Submission 1st RoI Report to the ICANN Board ( chair of the ccNSO)","Publication 3rd progress and Interim Report and 2nd RoI Report","Community Discussion, Adoption 2nd RoI Report by ccNSO and GAC","Submission 2nd RoI Report to the ICANN Board ( chair of the ccNSO)",null,"Publication 4th progress and Interim Report and 3rd RoI Report","Community Discussion, Adoption 3rd RoI Report by ccNSO and GAC","Submission 3rd RoI Report to the ICANN Board ( chair of the ccNSO)"]
["ccPDP on Retirement of ccTLDs","TBD, depending on progress FoI WG"]
["Study Group on Use of Teritory Names",null,"Nomination of chair, WG meetings","Appointment chairs, Overview of policies",null,null,"Second progress Report","Community discussion of draft recommendations",null,"Draft Final Report "]
["Joint IDN workin group (JIG)",null,null,"Extension mandate, update charter"]
[]
["ccTLD community related activites"]
["IRI WG",null,"Appoint volunteers",null,"Draft Work plan","TBD",{"$nulls":13},"Final Report and recommendations"]
["Finance Working Group ",null,null,"Fact finding Inventory of models, and needed information",null,null,null,"Discussion of models by WG",{"$nulls":4},"Overveiw of models to community",null,"WG provides report for ccTLD community","Open sessions on report",{"$nulls":10},"Draft and submit comments"]
[]
["ccNSO related ICANN activities"]
["Update IDN Guidelines"]
["IDN Variant Issue Project"]
["ccNSO related activity other SO or AC"]
["ccNSO Response and Statements"]
["Feed-back and Input ICANN SSR Plan",null,"Draft and submit comments"]
["AoC SSR review"]
["AoC WHOIS review"]
[]
["Joint Activties"]
["DSSA WG",null,null,"Work Plan DSSA WG"]
[]
["Implementation ccNSO improvements"]
["ccNSO review recommendations",null,"Discuss draft workplan (council)","Present to community + Adopt workplan (council)","Inform SIC of workplan"]
[]
[]
[]
[]
[]
[]
["Mechanisms for statements and opinions of cNSO",null,"Draft mechanisms","Present mechanisms to community and Adopt mechanisms","Inform SIC "]
["Outreach to GAC to increase involvement of Government run ccTLDs in ccNSO",{"$nulls":4},"Prepare briefing document on benefits and costs of joining the ccNSO","Organiise briefing session GAC","Briefing session GAC","Inform SIC"]
["Translation of Documents",{"$nulls":8},"Council to appoint informal council WG on translations","Prepare briefing note on translations for council",null,"Commnunity discussion on translations","Update briefing note",null,"Decision council on translations","Inform SIC"]
["Introduction of coolaborative tools (closed website)",null,"Council decision on closed website","Training WiKI and ADOBE Connect",null,"Develop requirements ( Support staff) in close cooperation with community","Intitate implementation of wiki or closed section","Present closed wiki for ccTLD community"]