{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1904","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":58,"n_cols":18,"rows_kept":58,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[null,"Dates in months","2011-08-01","2011-09-01","2011-10-01","2011-11-01","2011-12-01"," January 2012","2012-02-01","2012-03-01","2012-04-01","2012-05-01","2012-06-01","2012-07-01","2012-08-01","2012-09-01","2012-10-01","2012-11-01"]
[]
[null,"(ICANN meetings)",null,null,"ICANN 42 (23-28)Dakar",{"$nulls":4},"ICANN 43 (11-16)     San Jose",null,null,"ICANN 44 (24-29) Prague",null,null,null,"ICANN 45 (14-19) Toronto"]
["Tasks and events"]
[]
["ccNSO coordination"]
["ccNSO Workplan  ",null,"Review activities  and update","Review activties and update","Review activties and update","Review activties and update","Review activites and update","Review activites and update","Review activites and update","Review Work Plan Present to community & adopt workplan","Review activites and update","Review activites and update","Review activites and update","Review activites and update",null,null,"Present to community & adopt workplan"]
["GAC-ccNSO Liaison WG"]
["Liaison GNSO-ccNSO"]
[]
["Administrative activities"]
["Council meetings (conference calls)",null,"2011-08-23","2011-09-27",null,"2011-11-15","2011-12-20","2011-01-10","2011-02-14"]
["F-2-F meetings",null,null,null,"f-2-f 25 October",{"$nulls":4},"f-2-f 13 Mar"]
["Council elections",null,"Appoint Election manager","Call for nominations","Elections","Adopt report election manager"]
["Chair and vice chair elections",{"$nulls":8},"Chair and vice-chair election",{"$nulls":4},"appoint Election manager","Call for nominations","Elections","Adopt report election manager"]
["Council Workshops",null,null,null,"logistical meeting",{"$nulls":4},"2011-03-10",null,null,"23 June workshop",null,null,null,"13 Ocotber Workshop"]
["Council Roles and responsibilities",{"$nulls":8},"Review and adoption"]
["Board Selection",null,"Appoint Election Manager","Call for Nominations","Elections finshed","Select Board member"]
["ccNSO Programme meeting WG",null,"Meetings draft agenda ","Meeting on draft and publsih agenda",null,null,null,"Meeting on draft Agenda","Meeting on draft and publsih Agenda"]
[]
["Recurring Activities: ICANN Planning"]
["ICANN Strat Plan",null,"Public comment","Posting of draft Strat Plan","Draft Strat Plan + Public comment",null,"ICANN Board Adoption Strat Plan",{"$nulls":5},"Initial presentation","Draft Strat Plan Framework and Public comment","Public comment",null,"Draft Strat Plan + Public comment","ICANN Board Adoption Strat Plan"]
["SOP WG activities",null,"Submission of comment",null,"Organsie Submission",{"$nulls":8},"Organise submission","Submission of comment",null,"Organsie Submission"]
["ICANN Budget and Ops Plan",null,null,null,"Kick-off request for services Ops Plan FY 2013",null,null,null,"Draft Ops Plan Framework FY 2013",null,null,"Publication draft FY 2013 Ops Plan","Adoption FY 2013 Ops Plan"]
["SOP WG activities",null,null,"Prepare input on services request in conjunction Finance WG",{"$nulls":5},"Prepare and submit input and feed-back Ops Plan Framework FY 2013",null,"Prepare and submit input and feed-back Draft Ops Plan  FY 2013",{"$nulls":4},"Prepare input on services request"]
["Finance WG",null,null,"Prepare input on services request in conjunction with SOP WG"]
[]
["Policy related activities"]
["IDN ccPDP",null,null,null,"Council Report ","Council Vote","Members Vote",null,"Final Board Report"]
["Working group 1",null,"Prepare Guidelines Improvement confusing similarity test","Publish Final Report","Inform GAC"]
["Working group 2",null,null,"Publsih Final Report ",null,null,null,"Adoptiion Baord report by ccNSO Council","Submission Board Report to the Board (chair ccNSO)"]
["Framework of Interpretation WG",null,"WG meetings","Publication first progress and Interim report","Community discussion Interim Report",null,null,null,"Publication 2nd progress and Interim report and 1st Recoomendations of Interpretation ( RoI Report","Community Discussion, Adoption 1st RoI Report by ccNSO and GAC","Submission 1st RoI Report to the ICANN Board ( chair of the ccNSO)","Publication 3rd progress and Interim Report and 2nd RoI Report","Community Discussion, Adoption 2nd RoI Report by ccNSO and GAC","Submission 2nd RoI Report to the ICANN Board ( chair of the ccNSO)",null,"Publication 4th progress and Interim Report and 3rd RoI Report","Community Discussion, Adoption 3rd RoI Report by ccNSO and GAC","Submission 3rd RoI Report to the ICANN Board ( chair of the ccNSO)"]
["ccPDP on Retirement of ccTLDs","TBD, depending on progress FoI WG"]
["Study Group on Use of Teritory Names",null,"Involvement UNESCO","Develop Typology   First progress Report","Community discussion of  First Progress Report",null,null,null,"Second Progress Report"]
["Joint IDN workin group (JIG)",null,"Extension Mandate charter "]
[]
["ccTLD community related activites"]
["IRI WG",null,"Develop Work Plan",{"$nulls":13},"Final Report and recommendations"]
["Finance Working Group ",null,"Appointment of Teams",null,"Initial Discussion of models by WG",{"$nulls":4},"Overveiw of models to community",null,"WG provides report for ccTLD community","Open sessions on report"]
[]
["ccNSO related ICANN activities"]
["Update IDN Guidelines"]
["IDN Variant Issue Project"]
["ccNSO related activity other SO or AC"]
["ccNSO Response and Statements"]
[]
["AoC SSR review"]
["AoC WHOIS review"]
[]
["Joint Activties"]
["DSSA WG"]
[]
["Implementation ccNSO improvements"]
["ccNSO review recommendations"]
[]
["Outreach to GAC to increase involvement of Government run ccTLDs in ccNSO",null,"Prepare briefing document on benefits and costs of joining the ccNSO",null,"Council to ADOPT Briefing Paper",null,null,"Organiise briefing session GAC",null,"Briefing session GAC","Inform SIC"]
["Translation of Documents",{"$nulls":5},"Council to appoint informal council WG on translations","Prepare briefing note on translations for council",null,"Commnunity discussion on translations","Update briefing note",null,"Decision council on translations","Inform SIC"]
["Introduction of coolaborative tools (closed website)",null,"Develop requirements ( Support staff) in close cooperation with community DEFERRED TO SEPTEMBER","Intitate implementation of wiki or closed section Staff organise extended training work shop","Present closed wiki for ccTLD community Training work shop by staff"]