V2 | 3 June 2022 | Timeline: Council Elections

| Item | Action | Start Date | Closing Date |
| --- | --- | --- | --- |
| 1 | CCNSO COUNCIL APPOINTS AN ELECTION MANAGER AND ADOPTS ELECTION TIMELINE | 16 June 2022 (ICANN74 ccNSO Council Meeting) | Latest During August Council Meeting |
| 2 | COUNCIL ELECTION WEBINAR |  | Week 5-9 September 2022 |
| 3 | CCNSO MEMBERS SUBMIT NOMINATIONS & SECONDMENTS | Wednesday, 14 September 2022 (00:01 UTC) | Wednesday, 5 October 2022 (23:59 Utc) |
|  | ICANN75 ¦ 17-22 SEPTEMBER 2022 |  |  |
| 4 | ACCEPTANCE OF NOMINATION BY THE ELIGIBLE CANDIDATES |  | Wednesday, 12 October 2022 (23:59 UTC) |
| 5 | ELECTION MANAGER INFORMS COUNCIL AND COMMUNITY ABOUT THE LIST OF CANDIDATES |  | Thursday, 13 October 2022 (23:59 UTC) |
| 6 | Q&A WITH THE CANDIDATES |  | Week 17-21 October |
| 7 | ELECTIONS (FIRST ROUND) | Tuesday, 25 October 2022 (00:01 UTC) | Tuesday, 8 November 2022 (23:59 UTC) |
| 8 | ELECTION MANAGER INFORMS COUNCIL AND COMMUNITY ABOUT THE RESULTS OF THE FIRST ELECTION ROUND (IF ANY) & NEXT STEPS |  | Wednesday, 9 November 2022 (23:59 UTC) |
| 9 | SECOND ROUND OR RUN-OFF ELECTIONS, IF NECESSARY | Tuesday, 15 November 2022 (00:01 UTC) | Tuesday, 29 November 2022 (23:59 UTC) |
| 10 | ELECTION MANAGER INFORMS COUNCIL AND COMMUNITY ABOUT THE RESULTS OF THE SECOND ELECTION ROUND OR RUN-OFF ELECTIONS (IF ANY) & NEXT STEPS |  | Wednesday, 30 November 2022 (23:59 UTC) |
| 11 | ELECTION MANAGER SUBMITS REPORT TO COUNCIL |  | Wednesday, 7 December 2022 (23:59 UTC), or sooner, if no 2nd Round or Run-Off |
| 12 | COUNCIL ADOPTS REPORT: CLOSURE OF ELECTION PROCESS | 15 December 2022 at the Council Meeting (or earlier if no run-off election) | Latest during the January ccNSO Council meeting |
| 13 | CANDIDATES TAKE THEIR SEAT ON CCNSO COUNCIL |  | End ICANN76 Community Forum, March 2023 |