Very Short-term Communication Strategy ccTLD community

Objectives

Very Short term ( now-until end of May 2015): Inform the ccTLD community on progress made to date, and engage in public comment processes. Given this objective is directly linked with the public comment on the CWG proposals, outreach and engagement is in the remit of the tasks of the ccNSO appointed CWG members (and participants).

Short term (Currently around BA meeting): Engage ccTLD community in decision-making process around support for CWG proposal and CCWG recommendations. Given this objective is directly linked with the decision making on the CWG proposals, which should be organized by the ccNSO Council outreach, it is in the remit of the tasks of the ccNSO Council to organize outreach and engagement in the decision-making process.

Long term: Legitimacy of proposal and recommendations, legitimacy of multi-stakeholder model

ccTLD Audiences/Stakeholder categorization

The ccTLD community’s diversity is illustrated and reflected in their level of engagement with the IANA Transition and related enhancement of accountability processes:

- ccTLD Members CWG/CCWG

- Active ccTLD Participants CWG/CCWG

- Informed/engaged ccTLDs, observers CWG/CCWG

- Interested ccTLDs (responded to survey)

- Passive ccTLDs

Note the group of interested ccTLDs is declining in the course of the CWG/CCWG process. Signals for this declining interest are:

- Declining response rate to questionnaires/ surveys.

- Declining interest noticed by Regional Organizations

It is unclear whether this declining engagement is due to declining interest in the process as such (too complex, slow progress) or lack of interest in the subject itself ( it does not affect me). Anecdotal evidence suggests the former: process is too complex, too slow.

If correct, then the outreach and engagement efforts should be focused on:

- Keeping ccTLDs who have been informed/engaged, informed and engaged in this cycle of the process.

- Keep those ccTLDs who have shown an interest, interested.

To engage the group of passive ccTLD in this short time frame will most likely be too burdensome.

High level topics that need to be explained, communicated to engage ccTLD community

Relevancy and Interdependency of the processes

Background (NTIA announcement) and interrelation of work of CWG and CCWG, meaning explanation is needed on:

Why are processes relevant to ccTLD?

What are issues at stake?

- What are high-level issues relating to Transition and Accountability, and why is it an issue from a ccTLD perspective)?

- How are issues being addressed, and why in the way proposed?

- Interrelation of different elements in proposals and recommendations (from a ccTLD perspective)

Proposed approach to engage ccTLD community in public comment process

(Short term objective).

The following combination of outreach and engagement tools is proposed. This is based on effectiveness of different tools, and need keep critical group of ccTLD who are interested engaged in processes.

Preparation phase

| Item | Description | Date to be completed | Who is lead | Comment |
| --- | --- | --- | --- | --- |
| Agreement on Approach |  |  |  |  |
| Combined effort to engage ccTLD community | Approach RO on combined outreach and engagement effort for public comment | 16 April |  |  |
| Dates Webinar | Agreement on dates and organization of ccTLD specific regional/timezone based webinars |  |  | ccNSO staff can provide tools for webinars, including ADOBE room, telephone infrastructure |
| Invite | Combined invite for webinars | 16 April | Members CWG |  |
| Summary text of process | Text to explain at high level of process and possibly core elements | 19 April | Members CWG |  |

Outreach and Engagement Plan

| Action | Description | Date | Who is lead | Comment |
| --- | --- | --- | --- | --- |
| Announcement | Email to the community announcing the various elements: invite to participate in public comment invite to webinars announce summary document | 17 April | CWG members | To be send when date of public comment and others dates are confirmed. Email to be send through ccTLD world, ccTLD community, RO lists and ccNSO members list to ensure widest coverage |
| Informal discussion co-chairs CWG/CCWG and ccNSO Council |  | 17 April , noon UTC |  | Focus on timeline, interdependencies, expectations, etc. Recording and made available |
| Conclude and Sent summary document | Date to conclude summary document 19 April, Sending document 20 April following opening public comment forum | 20 April |  | To be send by CWG members, to ccTLD lists, post on ccNSO website, distribute to RO lists (translations?) Refer to webinars |
| Public Forum Open. Announcement to be forwarded | Staff to forward announcement of public forum to lists, announce also on ccNSO website | 20 April |  |  |
| ccTLD specific Webinars | Webinar on proposal: Summary of Proposal Q & A Explain most effective method to provide feed-back and input Next steps | 21, 22 and 23 April Tome to be determined | CWG members | ccNSO staff to set up ADOBE and |
| Email to Update on public comments received, |  | 2 Days after closure of Public comments | CWG Members | Goal to provide an overview and inform on next steps |

Additional tool that could  be used: Pod cast based on summary document to explain and summarize main elements.

To be recorded in week 20 April- 25 April and posted on ccNSO website and by ROs

Annex A

Tools available

| Tools | Benefits | Contra | Use for | When? |
| --- | --- | --- | --- | --- |
| Email updates (World list, ccTLD list, regional email lists) | Easy to use, wide audience, | Uni-directional. Uncertain if read | Updates, Announcement | In preparation of Public comment, progress moving forward |
| Blog post | Personal view, engaging | Uni-directional. Unclear who will read | Updates on progress and highlight milestones |  |
| Summary document (Decision document) | Informative, explains core of proposal in easy terms. | Summary, does not capture the full breadth of the proposal. Unclear who will read. Content dependent on who will write summary. | Inform community on core of proposal | Preparation of public comment, preparation for decision-making |
| Pod –cast | Informative, and engaging narrative | Uni-directional | Explanation | Update and inform on proposal |
| ccTLD Focused webinar, including Q&A, regional | Informative, Engaging Regional outreach, Specific for | Regional bias, Combining results of Q & A. How does Q& A impact proposal? | Combined outreach and engagement effort (Regional Org and ccNSO membership) | In preparation of public comment, Prepare for decision-making |
| ccTLD focused webinar, including Q & A (global) | Informative, engaging | Less engaging as Regional focused. How does input will be taken into consideration. Language, cultural barriers. |  | Prepare for decision-making |
| General CWG Webinar | Informative, understand concerns of broad community | Non-ccTLD specific, substance depending on key concerns CWG. Language, cultural barriere |  | In preparation of public comment, Prepare for decision-making |
| ccTLD focused Website announcements | Channeling information, broadly availble | Non-engaging, uni-directional ( push of information) |  |  |
| Draft Proposal Public forum | Full proposal, major opportunity to influence outcome |  |  |  |
| General CWG announcement | Wide-availability |  |  |  |
| Face-to face meetings, including remote participation tools | Most effective to generate feed-back, input or sense concensus | Costly, difficult to organize in short timeframe. How is feed-back taken into consideration?. Structuring effective f-2-f meeting . | Decision-making |  |