Timeline RZERC selection process

The term of current ccNSO appointee on RZERC ( Peter Koch, DNIC, .de) ends on 1 October 2019. In order to meet the requirement under the Guideline: ccNSO Actions Respecting the Root Zone Evaluation Review Committee (https://ccnso.icann.org/workinggroups/ccnso-rzerc-guideline-01sep16-en.pdf ) Council asked the secretariat to propose a timeline.

The suggested timeline assumes that the ccNSO member should be appointed by 1 October 2019, preferably earlier.

Timeline selection ccNSO member on RZERC

| ITEM # | ACTION | START DATE | END DATE | COMMENT/GUIDELINE SECTION |
| --- | --- | --- | --- | --- |
| 1 | Secertariat to Update wiki page |  | 10 July | Check if page needs to be updated |
| 2 | Secretariat to Prepare template EoL |  | 10 July | Update previous template |
| 3 | Secretariat to prepare call for volunteers |  | 10 July |  |
| 4 | Council decision to launch | 11 | 18 July |  |
| 5 | Call for expression of interest | 19 July | 9 August | Section 5 |
| 6 | Secretariat to prepare overview of application | 12 August | 12 August |  |
| 7 | Selection by Councillors | 13 August | 20 August | Section 5.2.2.2 Guideline |
| 8 | Selection report adoption |  | 22 August | Council meeting, concludes selection process |