## Slide 1: Possible Road Map for ccNSO Review
Feb
Provide draft RFP to ccNSO
Mar
ccNSO provides feedback on RFP
May
Independent Examiner selected
May
June
Start Review
Jun-Dec
Interviews, Survey, Analysis
Jan
Draft Report for WP
April
Final Report for WP
Final Report
ICANN58
ICANN61
Review plans continuously aligned with community workload and flexibility to accommodate extensions, when necessary.
2017 2018
12 Dec 2016
ICANN59
March
Public Comments
ICANN60
Jan
OEC Chair-ccNSO Meeting

## Slide 2: Roles and Responsibilities
Review Working Party
  Liaison
  Conduct self-assessment
  Help tailor review methodology
  Input into review scope, deliverables and selection criteria
  Community outreach support
  Input into data collection – online assessment and interviews
  Provide clarification and factual corrections
  Assess usefulness & feasibility of recommendations
  Assess effectiveness of prior review improvements
  Review of documents, records
  Observe proceedings
  Develop and conduct online surveys
  Conduct interviews
  Factual observations and implementable recommendations
  Engage with stakeholders for clarification and correction
  Prepare report(s)
  Oversight
  Scope of review
  Confirm Independent Examiner
  Accept Report*
  Approve Implementation Plans*
  Monitor progress of implementations
Independent Examiner
ICANN Org.
  Prepare RFP, run competitive bidding process
  Monitor timeline and resources
  Support review
  Support outreach and engagement
  Manage report and public comment process
  Assist with preparation of Review Implementation Plan
OEC
*Prepare Recommendations for Board Action
Independent Examiner