Detailed Schedule and Timeline Review Mechanism first

|  | Event |  | Entity | Tentative Date completion | Comment |
| --- | --- | --- | --- | --- | --- |
| 1 | Draft Issue Report |  | Issue Manager | March 2017 | To be presented to the Council for its Copenhagen meeting |
| Initiation PDP |  |  |  |  |  |
| 2 | Formal Decision to initiate the ccPDP |  | ccNSO Council | March 2017 | ccNSO Council vote |
| Comments on Issue PDP |  |  |  |  |  |
| 3 | Comments on Issue PDP | Public notification of Initiation of ccPDP | Issue Manager | March 2017 | Notification of initiation of the ccPDP on the ICANN Website and to the other ICANN Supporting Organizations and Advisory Committees. Open comment period (in accordance with the PDP Time Line. At least 40 days long) shall be commenced for the issue. |
| 4 |  | Call for Volunteers | Issue Manager | March 2017 |  |
| 5 |  | Formal request to Chair of the GAC to offer opinion or advice | ccNSO Council | March 2017 |  |
| 6 |  | Formation of Working Group I under ccPDP Call for volunteers, invite participants | ccNSO Council | March 2017 | As part of the ccPDP, create a Working Group to propose and develop policy for Review Mechanism |
| Preparing Recommendations |  |  |  |  |  |
| 7 |  | Appointment members, chair | Council | May 2017 | With appointment of chairs etc, kick-off second phase PDP |
| 8 |  | Interim Paper | ccPDP WG I | October 2017 | To be published in time to be discussed at ICANN meeting and public comment |
| 9 |  | Formation WG II, Call for volunteers, appointment etc. | ccNSO Coucil | December 2017 | Call fro volunteers WG 2 Retirement of ccTLDs, Self-nominations, invite ALAC, GAC, GNSO and, SSAC to appoint at least one participant. Invite Regional Organisations to appoint at least 1 participant. Invite PTI staff and expert on ISO 3166. |
| 10 |  | Update Paper WG I | ccPDP WG I | January 2018 | Interim paper on Review Mechanism will need to be updated to take into account the public comments. |
|  |  | Hybernation of WG I | ccNSO Council | January 2018 | WG 1 will recommence its work after WG 2 has fished its work to update the proposal to incorporate |
| 11 |  | Interim Paper WG 2 | ccPDP WG 2 | May 2018 | Interim paper for public comment on Retirement of ccTLDs |
| 12 |  | Final Paper WG 2 | ccPDP WG 2 | October 2018 | Submission Final Paper to Issue Manager and chair of WG 1. |
| 13 |  | Closure of Working Group 2 |  | October 2018 |  |
| 14 |  | Draft Final Paper WG 1 | WG 1 | January 2019 | Review and update proposal WG 1, based on final paper WG 2. Open for public comment. |
|  |  | Final Paper WG 1 |  | March 2019 | Submission Final Paper to Issue Manager. |
| 15 |  | Initial Report ccPDP | Issue Manager | March 2019 | Initial Report of IM. This report consolidates final recommendations WG 1 and WG 2 into one report. Needs to be published in time for full discussion at ICANN meeting and public comment |
| 16 |  | Final Report | Issue Manager | May 2019 | Final Report of the ccPDP. This contains the recommendations to resolve issues as identified in Issues Report and wil be submitted to the Council. This step initiates the decision making process. |
| ccNSO Decision making phase |  |  |  |  |  |
| 18 |  | Submission of Final Report to the ccNSO Council | Issue Manager | May 2019 |  |
| 19 |  | Invite the Chair of the GAC to offer opinion or advice | ccNSO Council | May 2019 | Formal step as defined for the ccPDP |
| 20 |  | ccNSO Council Adoption of Final Report | ccNSO Council | June 2019 | Decision ccNSO Council |
| 21 |  | ccNSO members vote | ccNSO Members | July or September 2019 | Final vote of the ccNSO members |
| 22 |  | Board Report | ccNSO Council | October 2019 | Conclude the ccNSO Decision making |
| Board Decision making Phase |  |  |  |  |  |
| 23 |  | Submission Board report | Issue Manager | October 2019 |  |