ccNSO activity overview (work plan)

Monthly overview

Version: February 2017

	Overview ccNSO policy (related) activities version February 2017

	Activity
	Description
	Initiated
	Target Date
	Chair/

owner
	Actions/status

dependency

	Framework of Interpretation 
	Closing/Final report
	
	28 February 
	Keith Davidson
	Board decision 25 June on Adoption FOI, and directing Staff to start implementation. 



	
	Implementation FOI Recommendations.

	June 2015

	TBD
	Becky Burr
	Submitted 23 August
No further action to date

Awaiting implementation by PTI staff



	IDN ccPDP/Fast Track
	Complete review of WG EPSRP.  WG to provide guidance on split decision lower –upper case, other elements second panel
	February 2015
	Completed
	WG ESPRP
	Board Decision June 2015, request to provide guidance together GAC and SSAC 
WG EPSRP established in fall 2015, including members from GAC.

Final report submitted to the Board. 
Awaiting Board decision
WG EPSRP Closed

	
	Adoption of IDNccTLD proposed policies (Board paper)
	
	Pending
	Chair of the ccNSO
	Board report submitted October 2013.

Board Vote anticipated after decision on WG EPSRP

(closure of pending review Fast Track experiment with second panel.) 

	Retirement of ccTLD PDP
	To be launched 
	June 2016
	Depends on combining the topics, minimal duration: 1 year post launch Rev. Mechanism
	Chair of the ccNSO (managing the work plan)
	Further discussed in Hyderabad
Draft Team WG charter Launched in Hyderabad

Launched in Copenhagen, pending Issue Report



	Independent Appeals Mechanism
	To be launched
	June 2016
	Depends on combining the topics, at least 1.5  year after launch PDP. 
	Chair of the ccNSO (managing the work plan)
	Further discussed in Hyderabad
Draft Team WG charter Launched in Hyderabad

Launched in Copenhagen, pending Issue Report

	First phase Combined PDP 
	Preparing Issue Report
	June 2016
	Copenhagen meeting
	Issue Manager
	To be made public before Copenhagen meeting, includes draft charters

	CCWG Use of Country and Territory Names
	WG progress
	February 2015
	November 2016
	Annebeth Lange, Paul Szyndler
	Discussion Feasibility and development of framework decision CCWG.

Progress reported at Dublin meeting

	
	Decision on proposed framework
	
	 November 2016
	Community and Council 
	Decision on Framework: Not feasible

	
	Call for input ccTLD community 3 letter codes
	
	
	
	Completed and included in Interim Paper

	
	Preparing Interim Paper
	August 2016
	Juine 2017 
	Annebeth Lange and Paul Szyndler
	Depending on outcome CCWG discussion. Harmonised Framework is NOT considered feasible 
Interim Paper to go through public comment


	ccTLD community related activities version February 2017 

	Activity
	Description
	Launch date
	End Date
	Owner
	Description

	CWG on Principles CCWG
	Framework of Principles
	22 May 2014
	November 2016
	Becky Burr
	Adoption at Hyderabad
WG Closed  

	Tech WG
	Tech Day programme @ ICANN meetings    Eberhard Lisse    Tech WG.
Preparation Copenhagen meeting have started

	Strategic and Ops plan
WG
	Submissions SOP WG on ICANN update 5 year ops plan and FY 2018 Operating Plan and Budget


	March 2017
	June 20167
	Giovanni Seppia
	Process to be launched at Copenhagen Dublin meeting. Following publication of FY 2018 Operational Plan and Budget, and update Five year operational plan, SOPWG to prepare its input. 
Inform about “rejection process”

	CCWG Geographic Regions Final Report
	The ccNSO Council supported recommendations of the Geographic Regions WG Final Report
	
	
	
	Public comment closed
Awaiting Board decision 



	Secure Implementation Incident response repository WG, phase 1
	Draft charter Oversight and Governance Committee,

Prepare call for volunteers
	August 2015
	Cristian Hesselman
	Membership oversight complete

Discussion on scope of use of list and subscription.
Workshop Copenhagen: strictly closed session 

 

	 Secure Implementation Incident response repository WG, phase 2
	Design Add-on’s, including secure messaging
	June 2016
	June 2017
	Cristian Hesselman
	TBD’ed Follow-up Phase 1
TLD-OPS Standing Committee to revisit use etc. of TLD –Ops list. 

	CCWG IG
	Cross-community WG focusing on all Internet Governance events with exception of IANA Stewardship Transition and Accountability
	
	On going
	Co-chair Young-Eum Lee
	Discussion on status CCWG: is another vehicle more appropriate?

(Working party/interest group)

Discussion needed on participation ccNSO
Progress By Copenhagen?



	CSC Related work 
	Coordinate Charter review
	Copenhagen, March 2017
	March 2018
	TBD 
	ccNSO together wih RySG to coordinate and appoint committee first CSC charter review. Review to start October 2017. 
Update charter, if at all, to be supported by ccNSO and GNSO 

	
	Review of SLE
	TBD 
	TBD
	Chair of the ccNSO 
	Review of SLE as included in IANA naming function agreement at request of CSC or PTI.


	CCWG enhancement ICANN’s accountability

WS 2

And Implementation
	WS 2 parallel Processes 

1
	June 2016
	
	Mathieu Weill
	ccNSO appointed members + participants, not available for other activities.

Re-confirmation membership others 



	
	Decision making ccNSO on WS 2 proposals
	TBD
	
	Chair of the ccNSO 
	Preparing and taking decision on proposals developed by CCWG WS 2 



	
	Decision making next steps ccNSO Council accountability
	May 2016
	Ongoing 
	Chair of the ccNSO 
	Pending requests and proposals CCWG WS 2 SO/AC accountability discussions

	
	Implementation ccNSO aspects WS 1 Recommendations flowing from ICANN Bylaws 1 October 20167
	June 2016
	TBD
	Chair of the GRC
	GRC mandated and tasked to propose Guidelines to implement ccNSO specific aspects of new Bylaws regime (Empowered Community etc.)


	Implementation Accountability
	ccNSO as Decisional Participant 
	October 2016 
	On-going
	Chair of the ccNSO 
	ccNSO accepted role as Decisional Participant. Role and procedures will be developed by GRC.
Order of priority: 

· Rejection Procedure

· Approval and Removal

· Mediation etc.



	
	Procedure ICANN & IANA Budget and Ops Plan FY 2018
	March 2017
	
	Chair of ccNSO
	Role and responsibility to be defined


	Overview Administrative Activities February  2017

	Activity
	Description
	Launch
	Target Date
	Chair/ owner
	Pending action/status/dependency

	ccNSO Council meetings
	Monthly Council meetings 
	
	Ongoing
	Chair of the ccNSO
	Monthly Council meeting focusing on administration of the ccNSO

	Council Elections
	Council election FY 2017
	September 2016
	January 2017
	Election manager ( Joke Braeken
	Completed

New Councillors to take seat at the end of ICANN 58 meeting 


	Board member Election
	Board seat 11 Nomination
	September 2016
	January 2017
	Election manager ( Joke Braeken) 
	Completed

Nominated Board member will take seat at AGM 2017 (October/November 2017)


	Appointments Liaisons 
	GNSO Liaisons
	December 2016
	February 2017
	
	Call for volunteers closed
Council selection

	
	ALAC Liaison
	September 2016
	January  2017
	Chair of the ccNSO 
	Liaison appointed

ALAC informed 



	Appointment members ICANN governance bodies 
	Member NomCom 2017
	July 2016
	August 2016
	Chair of the ccNSO
	Call for volunteers July 2016

Council Selection July/August 2016

Selection Joerg Schweiger (.de) for second term

	
	Customer Standing Committee
	June 2016
	August 2016
	Chair of the ccNSO
	Call for Volunteers June 2016

Selection Council ccNSO appointed members July 2016

Approval Full slate CSC: August 2016

Joint statement ccNSO-GNSO chaird August 2016

	
	RZERC
	June 2016
	October 2016
	
	Pending approval Selection RZERRC Guideline (September 2016)

Interim member: Katrina Sataki (chair ccNSO)

Call for volunteers September 2016



	
	Representative EC Administration
	September 2016
	
	Chair of the ccNSO
	Guideline adopted,
Stephen Deerhake selected



	
	Special Reviews:

Security, Stability and Resilience review
	June 2016
	?
	Chair of the ccNSO
	Currently Under Bylaws effective 1 October 2016, special review

Council adopted selection and appointment ccNSO members on Special Review teams (September 2016). 

Issue pending:

 appointment SSR 2 and DRS

scope DRS and ATRT 3

To provide feed-back etc. Operating Standards (Copenhagen)

Appoint Statement drafting team?



	Meetings Programme
	Review Survey Hyderabad
	November 2016
	December 2016
	Alejandra Reynoso
	Review and analysis of meeting survey and prepare responses to community

Feed-back on feed-back published 

	
	Prepare ccNSO Copenhagen 
	November 2016 
	
	Alejandra Reynoso
	Prepare Agenda for Copenhagen meeting.

First agenda published January 2017
 

	
	Meeting ~Organsization
	June 2015
	 Ongoing
	Alejandra Reynoso
	Overall scheduling ICANN f-2-f meetings
Selection of common topics

	Assign

Council roles and responsibilities
	Guideline roles and responsibilities
	
	 March 2017
	Chair of the ccNSO
	Upcoming

Succession planning chair and vice-chair to be completed by Copenhagen meeting. 

Preparation of review Rolls and Responsibilities.
Awaiting selection of standing committee members

	Council Triage Committee
	
	
	Ongoing
	Debbie Monhan, Margarita Valdes, 

Christelle Vaval
	Triage committee has submitted set of recommendations. 
Overview of recommendations see:
http://ccnso.icann.org/about/council/decisions.htm 

	Membership Application
	Processing and prepare for Council approval of membership applications
	
	Ongoing
	Abibu Ntahigiye 
	Ongoing

	ccNSO Travel Funding Committee
	Processing applications Copenhagen meeting closed
	June 2016
	August 2016
	Travel Funding Committee 
(Young Eum, Souleymane, Christelle)
	Names submitted to ICANN travel.

Processing by ICANN travel

Need for increase # slots?

	Rules and Guidelines update
Committee
	Update ccNSO Guidelines, and improvement voting system
	December 2014
	TBD
	Katrina Sataki, chair of the GRC
	Progress report delivered at Hyderabadmeeting

Guideline SOP archived.
Review Guidelines Working groups, Work plan, Triage committee, ccNSO Statements completed. Review Guideline ccNSO meeting, ccNSO programme WG review of language. Start review of Council election, Board Selection, NomCom appointee and Liaisons and Observers 

First set of Guidelines completed and approved by Council and effective.

Mandate extended see above.
Prepare overview of processes and procedures to meet requirements of new ICANN bylaws

	ccNSO Workplan update and review
	Update overview of activities and adjust portfolio for 2016-2017 timeframe
	1 March 2016
	30 March 2017
	Chair of the ccNSO
	Monthly update
August  2016 version

Annual version to be published early April 2016



	Update ccNSO Rules and Guidelines to include IDN ccTLD in ccNSO
	The current set of Rules and Guidelines needs to be updated to reflect the updates to Article IX and Annex B of the ICANN Bylaws as a result of inclusion of IDN ccTLD in the ccNSO
	
	Post Adoption of IDN ccPDP overall policy recommendations.Buenos Aires meeting (in conjunction with adoption of the changes to Article IX and Annex B of the ICANN Bylaws resulting from the IDN ccTLD ccPDP.
	Chair
	After adoption of IDN ccPDP by the Board, in conjunction amendment of the ICANN Bylaws Article IX and Annex B


