ccNSO activity overview (work plan)

Monthly update

Version: February 2013

	Overview ccNSO policy (related) activities version December 2012

	Activity
	Description
	Initiated
	Target Date
	Chair/

owner
	Pending action/status

dependency

	Framework of Interpretation WG
	Consent
	
	
	Keith Davidson
	To be included in full set of recommendations

	
	SIP
	
	Beijing (11 April)
	Keith Davidson
	GAC Response received June 2012. FoI WG send response October 2012. Awaiting further comments from GAC before finalizing Report on SIP.
No progress to date

	
	Revocation
	
	Beijing

( 11 April)

Potentially not final for Beijing meeting
	Keith Davidson
	Discussion at WG level in preparation of Interim Report. Interim report to be published before Beijing meeting.
Discussion focuses on substantial misbehaviour

	
	IANA Reporting
	
	
	Keith Davidson
	

	
	Glossary
	
	
	Keith Davidson
	

	
	Closing report
	
	Durban
	Keith Davidson
	Closure of the FoI WG. Depends on Finalisation of Final report

	IDN ccPDP
	Overall Policy selection IDN ccPDP

Final Report
	18 October 2012
	8 Nov. 2012
	Chris Disspain
	Collecting and analysing comments on draft Final report. Draft Final report. Public comment period closed 14 November. Update to Final Report for adoption by WG.
Summary and Analyses of comments adopted by WG December 2012.
Final report published December 2012

	
	Inclusion IDN ccTLD in ccNSO Final Report
	
	8 Nov. 2012
	Hiro Hotta
	Final report adopted by WG and published. To be included in Interim report

	
	Interim Report ccPDP
	1 December 2012
Publshed 5 February 2013
	21 February  2013
Closing date end March 2013
	Issue Manager
	Closure of IDN ccPDP WG 1 and WG 2 activities.
Interim report published for public comments. Public comment (comment and reply period) closes end-March 2013

	
	Final Report

ccPDP
	
	15 Feb 2013
	Issue Manager
	

	
	Council Vote
	Submit Final Report

20 March 2013,

Inform the GAC chair
	Council Beijing 10 April 2013
	Chair of the ccNSO
	

	
	Members Vote
	Announce 11 April
	27 June
	ccNSO Council
	Members report, including the deliberations and outcome of Council vote. Adoption of recommendations by Council

	
	Board Report. To be adopted by Council
	
	10 July (ccNSO Council meeting Durban
	ccNSO Council
	Outcome ccNSO Members vote.

	
	Submit Board paper
	
	
	Chair of the ccNSO
	

	Retirement of ccTLD PDP
	
	To be determined
	
	
	

	Study Group use of country names as TLD
	Survey UNESCO Member

States
	August 2012
	Nov. 2012
	UNESCO
	Survey
Still open but no new responses received

	
	Survey ICANN community
	Nov. 2012
No further steps taken
	
	Paul Szyndler, Study Group
	To be determined

	
	Draft Advise WG
	December 2012
	Beijing meeting
	Chair of WG
	Publish before Beijing and public consultations

	
	Final advise
	18 April 2013
	18 May 2013
	Chair
	

	At-Large White Paper on future ICANN
	ccNSO Letter
	1 December
	20 December
	Chair of the ccNSO
	Public comment period closes 4 January 2013. Issue raised around difference between ccTLD and gTLD’s and role of ICANN.
Completed


	ccTLD community related activities version 1, December 2012

	Activity
	Description
	Launch date
	End Date
	Owner
	Description

	Financial contr.
	Model for ccTLD contribution to ICANN
	
	
	Byron Holland
	EAG replace by value based approach
Intersessional discussions with ICANN staff anticipated mid March. In preparation of Beijing meeting 

	
	Distribution of contribution model
	
	
	Byron Holland
	Intersessional meeting anticipated mid-March

	Tech WG
	Update programme definition
	Prague meeting
	Beijing meeting
	Eberhard Lisse
	Update of mandate
Patrick Jones (ICANN staff) invited to participate in program sub committee

	
	Tech Day programme
	
	Beijing meeting
	Eberhard Lisse
	Tech Day. Request for Tech thread through ICANN meeting

	Strategic and Ops plan
	High level overview submissions SOP WG on ICANN Strat plan
	1 November 2012
	20 December 2012
	Roelof Meijer
	Following submission on draft Strat Plan 2013-2016, commitment to provide overview

	ccNSO submission IANA call for comments
	Letter from chair to ask extension comment period
	
	14 December
	Chair of the ccNSO
	Letter from chair to request extension of comment period and to align with ccNSO procedures
Completed

	
	“Call for” volunteers to prepare draft
	
	14 December 2012
end February 2013
	
	Membership of FoI Wg and Tech WG to form drafting team.
No volunteers from Tech WG. Drafting comprises of Keith Davidson, Becky Burr, Paul Szyndler

	
	IANA Customer Service Complaint Resolution Process
	26 November
	31 January 2013
March 2013
	Chair of drafting team
	

	
	IANA Delegation and redelgation PKI’s
	17 December 2012
	End February
March 2013
	Chair of drafting team
	

	
	IANA ccTLD delegation and redelegation documentation
	Anticipated March 2013
	Post Beijing
	
	

	Incident response repository WG
	Develop terms of reference, governance models, and cost assessment method for implementation of Incident response repository
	
	Beijing meeting, presentation to community and council
	Chair of the WG ( Luise Espinoza)
	Preparing draft 

	Overview Administrative Activities December 2012

	Activity
	Description
	Launch
	Target Date
	Chair/ owner
	Pending action/status/dependency

	Council Elections
	
	August 2012
	November 2012
	Election Manager
	Election statements.

Elections. Completed 19 November 2012

	
	Extraordinary Election LAC-Region
	
	
	
	

	Meetings Programme
	Prepare Beijing meeting
	18 October
	11 April 2013
	Chair Program
	Programme Wg had its first meeting 19 November

	
	Prepare Durban Meeting
	12 April

2013
	
	Chair Program
	

	Chair and vice chair elections
	
	
	10 April 2013
	ccNSO Council
	

	Assign

Council roles and responsibilities
	20 March 2013
	
	10 April 2013
	Chair of the ccNSO
	Workshop 7 April 2013. Workshop needs to be scheduled

	Council Study Group Capacity
	Final Report, contains recommendations for Triage Committee and prioritization of activities method
	
	10 April 2013
	Fernando Espania
	To be discussed at Council Workshop, Adopt at 10 April Council meeting.

	Rules and Guidelines update
	Update ccNSO Council Election Guidelines, and improvement voting system
	20 November 2012
	10 April 2013
	TBD
	Based on incidents during 2012 Council elections, procedures need to be updated.

Appoint Council Committee, propose to the community at the Beijing meeting.

Council committee appointed December 11, 2012.
Committee will prepare high level document on principles underlying elections for discussion at the Council workshop in Beijing

	ccNSO Workplan review
	Update overview of activities and adjust portfolio for 2013-2015 timeframe
	1 March  2013
	10 April 2013
	Chair of the ccNSO/ Senior policy advisor
	For discussion at 7 April 2013 council workshop. Present to the ccNSO Community present, adopt at the 10 April 2013 council meeting

	Update ccNSO Rules and Guidelines to include IDN ccTLD in ccNSO
	The current set of Rules and Guideliens needs to be updated to reflect the updates to Article IX and Annex B of the ICANN Bylaws as a result of inclusion of IDN ccTLD in the ccNSO
	
	Post Beijing (in conjunction with adoption of the changes to Article IX and Annex B of the ICANN Bylawas resulting from the IDN ccTLD ccPDP.
	Hiro Hotta
	Paper needs to be signed off by WG 2 members

	ccNSO Translation Policy
	Survey on need for translation and quality
	October 2012
	10 April 2013
	Staff
	Recommendation 2 of ccNSO improvements based on survey early 2010, needs to be updated.

Survey will be prepared by staff and is targeted for early 2013

	
	Overview of tools, costs and funding of translations
	October 2012
	10 April 2013
	Staff
	Translation by volunteers was one proposed method. Benefits and costs of translations need to be assessed and taking into account.

Overview will be prepared by staff

	10th Anniversary ccNSO
	Council and ccNSO appointed Board members committee, to organise festivties 10th Anniversary ccNSO in June 2013
	20 November
	July 2013 ( ICANN Durban meeting)
	Chair (to be appointed)
	Call for volunteers

Appointment of Anniversary Committee 11 December 2012.
Call for chair send out.
Committee met for the first time in January 2013. Will report to the Council by Beijing.


