ccNSO activity overview (Monthly Work Plan)

June 2016

Cluster of Projects and Activities related to IANA Stewardship Transition and associated enhancement of ICANN’s Accountability

Proposed owner of cluster: Byron Holland

| IANA Stewardship Transition and ICANN Accountability (Byron Holland) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | Launch date | Target date | Owner | Priority | Actions/Status/dependencies |
| Implementation of CWG-Stewardship | Interaction on behalf ccNSO with CWG, ICAN staff and leadership on Implementation of CWG –Stewardship Proposals CWG internal oversight committee | March 2016 | First phase to be completed mid-August 2016, Consecutive phases Anticipated end date 2018 | ccNSO appointed members CWG | HIGH | All committees, procedures for post transition IANA need to be implemented. Sequence determined by required timeline as proposed by CWG-Stewardship https://www.icann.org/stewardship-implementation Implementation Oversight Task Force. The IOTF and CWG-Stewardship are working on PTI Bylaws and Contract between PTI and ICANN, which should include SLE’s, Terms under which ccTLDs sould be provided services ( no contract etc.) |
| Implementation of IANA Stewardship related ccNSO specific processes and procedures | Implementation of selection and appointment process CSC membership. MUST be in place for Stewardship transition. | May 2016 | 15 August 2016 | Guideline Review Committee (GRC) | HIGH | Development of ccNSO specific processes and procedures. CSC Guidelines to be adopted by Council. Council to determine which method it wants to use for coordinating with rySG and GNSO COuncil Call for expression of Interest to go out on 30 June / 1 July |
|  | Implementation of selection and appointment process RZERC membership. MUST be in place for Stewardship transition | June 2016 | 15 August | GRC |  | RZERC charter published for Public Comment June 2016. RZERC Guideline needs to be developed by GRC, Call for Expression needs to go in time for ccNSO Council to appopi9nt. |
|  | Implementation of set of processes and procedures that follow from the Stewardship transition | August 2016 |  | GRC |  |  |
| Implementation of CCWG-Accountability | Interaction on behalf ccNSO with CWG, ICANN staff and leadership on Implementation of CCWG –Accountability WS 1 Proposals | March 2016 | First phase to be completed mid August 2016, Consecutive phases | ccNSO appointed members CCWG | HIGH | All mechanisms, committees, procedures for post transition to meet requirements CCWG need to be implemented. Sequence determined by requirements and timeline as proposed by CCWG-Accountability. New Bylaws adopted by ICANN Board of Directors. https://www.icann.org/stewardship-implementation |
| Implementation of CCWG-Accountability specific ccNSO specific rules and procedures | Implementation of selection and appointment processes MUST be in place for Stewardship transition | April 2016 | October 2016 | GRC (Katrina | HIGH | To be determined. |
|  | Implementation of set of WS 1 Accountability processes and procedures that will be in place following Stewardship transition | 30 September |  | GRC |  | To be determined |
| CCWG – Accountability WS 2 | Coordinate discussions and actions on CCWG – Accountability WS 2 | March 2016 | ? | ccNSO appointed members and participants CCWG | Helsinki meeting discussion on format and timing of WS 2 discussion |  |
|  | ccNSO Council Survey Accountability | June 2016 | 1 July 2016 | ccNSo Council | Medium | Survey Council to be used as input for SO/AC Accountability discussion and to update ccNSO Council meeting Guideline and Council election Guideline |
| Implementation WS 2 | Interaction on behalf ccNSO with CCWG, ICANN staff and leadership on Implementation of CCWG –Accountability WS 2 Proposals | 2017 |  | GRC |  | In schedule, if and when implementation will start not defined. |
| Coordination Council, CWG and CCWG members | Coordination across ccNSO appointed members CWG, CCWG and ccNSO Council | On-going |  | Chair ISTACC |  | First call of newly established group: mid-June 2016 |
| Coordination CWG members | ccTLD community internal coordination | On going |  | Chair ISTC (Lise Fuhr) |  | Two out of 5 WG members are not involved engaged. |
| Project Cost Support Team | Initial effort to manage costs ICANN & community lead efforts, in particular if external expertise is hired (law-firms other) | March 2016 | June 2016 | Chair and vice-chair ccNSO (Debbie) Monitor the issue with SOP WG |  | Effort to be monitored to assess impact on broader work. Will be presented shortly to the CWG-Stewardship. |
| ICG | ICG is in hibernation up & until coordination is needed between different IANA Function user communities to implement their proposals. | On going | October 2016 | Keith Davidson, Martin Boyle, Mary Uduma, Xiuadong Lee |  | https://www.ianacg.org/ |

Cluster of Projects and Activities of policy development and policy related ccNSO efforts. Includes implementation efforts

Porposed owner of cluster: Demi Getschko

| Policy and Policy related work (Demi Getschko) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | Launch date | Target date | Owner | Priority | Actions/Status/dependencies |
| IDN ccPDP completion | Ensure closure of the IDN ccPDP | On-going | October 2016 |  |  | Final Report submitted to Board. Awaiting closure test phase of Extended Process similarity review process (EPSRP). |
|  | Develop Guidelines EPSRP |  | June 2016 | EPSRP WG (Giovanni Seppia) | Middle | Series of Guidelines under development, at request Board. WG includes members GAC. SSAc has been informed. WG is finalising its recommendations. Expectation is that they will be send to the Council, to open public comment on the recommendations. Public comment period anticipated post Helsinki meeting. |
|  | Implementation team IDN ccPDP | October 2016 |  |  | LOW | According to recommendations, create a advisory team, to monitor and advise staff on implementation |
| FoI Implementation | Monthly (regular) ccNOS Council meetings | On-going | Mid-August 2016 | Advisory team (Becky Burr, Keith Davidson | HIGH | Advise and provide responses to questions IANA staff on implementation Framework of Interpretation |
| ccNSO PDP retirement & review mechanism | Develop framework for launch combined PDP | March 2016 | June 2016 | Chair ccNSO | HIGH | In preparation launch develop framework for launch and running PDP, Included sense of community in Marrakesh. Impact analyses one or two separate PDPs. |
|  | Launch PDP | June 2016 | 1 July 2016 | Council | HIGH | Council decisions at Helsinki meeting: - Request issue Report (combine topics) - Appoint Issue Manager - Appoint oversight committee - Tentative Timeline Issue reporting To be discussed at ccNSO meeting days Helsinki, Topic of GAC-ccNSO meeting. |
|  | Combined Issue Report Focus on Review mechanism for decisions on Delegation, revocation, and retirement decisions | June 2016 | October 2016 | Issue manager | HiGH | ISSUE Report, Council decision to initiate at Hyderabad meeting |
|  |  | WG 1 Phase, October 2018 | June 2017 | Issue Manager | HIGH | Call for volunteers WG 1, Public comment, substantial work on review mechanism. Note potential conflict with WS 2 Accountability |
|  | Initiate Retirement ccTLD | Issue reporting June 2017 | October 2016 |  | HIGH |  |
|  |  | WG 2 Phase (June 2017) | June 2018 |  |  |  |
|  | Voting Phase combined PDP | July 2018 | October 2018 | Issue manager |  | Assumption of one PDP. And end-vote on full set of recommendations |
| Use of Country & Territory names as TLD | CCWG launched to assess feasibility of frasmework for use of names of country and territories listed on ISO 3166-1 as TLDs as (IDN) ccTLD and/or gTLD | On-going | March 2017 | Annebeth Lange, Paul Szyndler |  | Cross-community session Helsinki meeting. Output to be used to progress work CCWG CTN. Cross-community Working group recommendations to feed into policy work of ccNSO and GNSO. To be completed by launch of policy work on second round new gTLDs |
| Internet Governance efforts | Cross-community WG to consolidate work community on Internet Governence issues | On-going |  | Young Eum Lee |  | CCWG was created to ensure efforts would be endorsed by Supporting organisation and advisory committees (in response to Netmundial community input). Question for community discussion: Is CCWG still right vehicle for effort (assumption no concrete output that could imply the ccNSO). Issue for discussion with GNSO |

Cluster of Projects and Activities focused on providing input on ICANN plans (none policy related) with a potential impact on ccTLD community.

Proposed Cluster owner: Katrina Sataki

| ICANN Focused work (Katrina Sataki) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | Launch date | Target date | Owner | Priority | Actions/Status/dependencies |
| ICANN FY 17 Ops Plan & Budget process | Provide input to ICANN’s FY 17 Ops Plan & Budget | March 2016 | April 2016 | SOPWG |  | Input provided in time for the FY 17 budget Focus on Operational aspects http://ccnso.icann.org/workinggroups/sopiwg.htm |
|  | Cross-community Session Operational Aspects | May 2016 | June 2016 | Chair SOPWG and Debbie | High | Cross-community session at Helsinki meeting |
| ICANN 5 year ops Plan update | Provide input to ICANN’s FY 17-20 Ops Plan | March 2016 | April 2016 | SOPWG |  | Input provided in time for the FY 17 budget Focus on Operational aspects http://ccnso.icann.org/workinggroups/sopiwg.htm |
| ICANN FY 18 Ops Plan & Budget process | Provide input to ICANN’s FY 18 Ops Plan & Budget | March 2017 | April 2017 | SOPWG |  | Focus on Operational aspects http://ccnso.icann.org/workinggroups/sopiwg.htm |
| ICANN 5 year ops Plan update | Provide input to ICANN’s FY 18-20 Ops Plan | March 2017 | April 2018 | SOPWG |  | Focus on Operational aspects http://ccnso.icann.org/workinggroups/sopiwg.htm |
| Interaction Post transition groups and committees | Interaction between ccNSO and CSC and other groups post transition of IANA Stewardship | 1 October 2016 | On going | GRC |  | Processes and procedures to be defined by GRC. Requirements/parameters included final Proposal ICG (assuming approval by NTIA) |
| Accountability processes and (virtual) groups | Interaction between ccNSO and Accountability processes and (virtual) groups (Empowered community) | January 2017 | On-going |  |  | Processes and procedures to be defined. By GRC. Requirements/parameters included final Proposal CCWG-Accountability |
| Accountability Processes ccNSO & others | Interaction between ccNSO and Accountability processes flowing from WS 2 | January 2018 | On-going | GRC |  | Operational ccNSO related processes and procedures flowing from WS 2. To be defined by GRC or its successor |
| Affirmation Reviews | ATRT, WHOIS Consumer protection and SSR reviews | Consumer choice review started in January 2017 | March 2019 |  |  | Timing of reviews not well defined. Review teams may request members from ccTLD community General overview: https://www.icann.org/resources/reviews/aoc |
| Cross-community WG on Framework for use of CCWG’s | CCWG to develop framework and principles for the creation and use of CCWGs, | On-going | October 2016 | CCWG2 ( Becky Burr) |  | CCWG currently first public comment. Takes into account CCWG Accountability and others. Update Draft Guidelines, for discussion at Helsinki meeting. Based on input etc. anticipated the Guidelines will be send to GNSO and ccNSO Councils for adoption, other groups may adopt them as well. |

Cluster of Projects and Activities to manage and administer activities of the ccNSO and ccNSO Council

Proposed Cluster Owner: Katrina Sataki

| Administration of ccNSO Council and ccNSO (Katrina Sataki) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | Launch date | Target date | Owner | Priority | Actions/Status/dependencies |
| ccNSO Members application | Oversee and execute members application process | Ongoing |  | Abibu / Secretariat |  | Oversee and execute members application process. |
| ccNSO Council Meetings | Monthly (regular) ccNOS Council meetings | Ongoing ( monthly) |  | Chair of the ccNSO Council |  | Scheduling, Agenda setting preparatory meetings. Oversight secretariat Include reference to ccNSO Council meetings once adopted |
| Oversight and appointment ccNSO WG | Oversee progress and progress WG and CCWG in which ccNSO is participating. | Ongoing |  |  |  | ccNSO Guideline WGs and possibly Include link Guideline when adopted |
| Annual Work Plan 16-18 | Describe annual work plan, based on discussion at annual planning workshop | March 2016 | March 2018 | Chair ccNSO / secretariat |  | Describe annual work plan, based on annual discussion Include Guideline when adopted |
| Prep Annual Work Plan 17-19 | Describe annual work plan, based on discussion at annual planning workshop | January 2017 | March 2017 | Chair ccNSO / secretariat |  | Adopted April 2016. |
| Monthly Work plan | Provide overview and update at detailed level of recently completed and upcoming activities/events | April 2016 | Ongoing | Chair ccNSO / Secretariat |  | Version June 2016 prepared. |
| Triage/ prioritization | Assess importance and urgency for ccTLD to respond/participate in activities. | Ongoing |  | Triage Committee |  | See: http://ccnso.icann.org/about/council/triage |
| Council Roles and Responsibilities | Assign(ed) roles and responsibilities to Councillors | March 2016 | March 2017 | Chair ccNSO |  | Include Guideline when adopted |
| Chair, vice-chair selection | Annual ccNSO chair and vice –chair selection by ccNSo Council | January 2017 | March 2017 | Chair ccNSO |  | Launch process for annual chair and vice-chairs election. Announce at January Council meeting |
| CSC members and liaisons appointment | Appointment by ccNSO of ccTLD members and approval of full slate of members and liaisons Customer Standing Committee | June 2016 | 15 August 2016 | Appointed Selection manager |  | Procedure needs to be developed by GRC and approved by Council at meeting in Helsinki, after consultation community. Interaction with RySG and GNSO See above |
| RZERC member appointment | Appointment by ccNSO of ccTLD members on RZERC | June 2016 | 15 August 2016 | Appointed Selection manager |  | Procedure needs to be developed by GRC and approved by Council at meeting in Helsinki, after consultation community |
| Appointment ccNSO member on NomCom | ccNSO needs to appoint member on NomCom 2017, by September 2016. | May 2016 | July 2016 | Appointed NomCom selection manager |  | Procedure needs to be updated by GRC and approved by Council before start of procedure |
| ccNSO Council Election 2017 | Annual Council Elections | 1 September 2016 August 2016 | January 2017 (in case of run-off elections) | Council election manager |  | Procedure needs to be updated by GRC and approved by Council before start of procedure(tentative) . Proposed date to start election process 1 September 2016. Decisions needed: - Appointment Election manager - Approval of Timeline This will allow for interview session at Hyderabad meeting (November 2016) Elected Councillors will take seat in March 2017 |
|  | Special Council Election ( replacement Becky Burr) | At closure of Hyderabad meeting |  | Election manger |  | It is anticipated that Becky Burr will step down at the end of the Council meeting in Hyderabad ( November 2016). To fil the vacancy , need to initiate Council election process for NA region. Decisions needed: - Appointment of Election manger - Approval of Timeline |
| Board Seat 11 (S)Election | ccNSO Selection for Board 11 | 1 Septemebr 20162016? | March 2017 (Run-off needs to concluded in March 2017 (6 months before October 2017) | Board Seat Selection manager |  | Procedure needs to be updated by GRC and approved by Council before start of procedure (tentative). Decisions to be made: - Appointment of Election manager - Adoption of Timeline This will allow for interview session at Hyderabad meeting (November 2016) Selected Board member will take seat in October 2017 |
| ccNSO Review | ICANN Bylaw required review ccNSO | (Not earlier then January 2017) |  |  |  | https://www.icann.org/resources/reviews/org/ccnso |

Cluster of Projects and Activities to manage and administer Outreach and Engagement efforts focused on broader ccTLD community

Proposed Cluster Owner: Katrina Sataki

| Interaction and Engagement (Katrina Sataki) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | Launch date | Target date | Owner | Priority | Actions/Status/dependencies |
| ccNSO Meetings Helsinki (ICANN 56) | Coordinate all aspects re ccTLD meeting Helsinki ( 27-30 June 2016 | March 2016 | July 2016 | Programme WG (Alejandra Reynoso |  | Includes Agenda, Scheduling, Survey and review. http://ccnso.icann.org/workinggroups/mpwg.htm Include reference to Guideline and charter Program WG when adopted |
| Tech Day ICANN 56 | Coordinate Tech Day @ ICANN 56 | March 2016 | June 2016 | Tech WG |  | http://ccnso.icann.org/workinggroups/techwg.htm |
| ccNSO Travel funding Hyderabad (November 2016) | ccNSO travel funding for the 12 Slots | June 2016 | August 2016 | ccNSO Travel Funding Committee |  | http://ccnso.icann.org/about/travel-funding |
| ccNSO Meeting ICANN 57 | Coordinate all aspects re ccTLD meeting ICANN 57(3 November – 3 Nov 2016) | August 2016 | November 2016 | Programme WG |  | http://ccnso.icann.org/workinggroups/mpwg.htm Include reference Guideline and charter Program WG when adopted |
| Tech Day ICANN 57 | Coordinate Tech Day @ ICANN 57 | August | November 2016 | Tech WG |  | http://ccnso.icann.org/workinggroups/techwg.htm |
| ccNSO Travel funding ICANN 57 |  | August 2016 | November 2016 | ccNSO Travel Funding Committee |  | http://ccnso.icann.org/about/travel-funding |
| ccNSO Meeting ICANN 58 | Coordinate all aspects re ccTLD meeting ICANN 58 (11-16 March 2017) | December 2016 | March 2017 | Programme WG |  | http://ccnso.icann.org/workinggroups/mpwg.htm (Include Guideline, when adopted) |
| Tech Day ICANN 58 | Coordinate Tech Day @ ICANN 58 | January 2017 | March 2017 | Tech WG |  | http://ccnso.icann.org/workinggroups/techwg.htm |
| ccNSO Travel Funding ICANN 58 |  | November 2016 | March 2017 | ccNSO Travel Funding Committee |  | http://ccnso.icann.org/about/travel-funding |
| SO/AC chairs meeting | Formal meeting with chairs other SO/ACs | March 2016 | March 2017 | ? |  | Part of ICANN meeting Helsinki session scheduled Sunday 26 June 2016 |
| Meeting with gNSO Council, GAC and ALC | Formal meeting with other SO and ACs | March 2016 | March 2017 | Chair ccNSO/Program WG |  | No structure in place No meeting scheduled with ALAC and GNSO. ( Note this is anomaly in outreach and engagement session) GAC meeting in Helsinki scheduled for Tuesday 28 June 2016, 15.15-16.15 ( ad-hoc agenda setting committees. Formalise to ensure broad support? |
| TLD-OPS mailing list | All aspects relating to incident response mailing list | Ongoing |  | TLD-OPS Standing Committee |  | Re-appointment of Steering committee March 2017. Extension of list to information sharing and inclusion other TLDs |
| Review and Revamp ccNSO Website | ccNSO web-site will be redesigned | October 2016 | June 2017 | ?/Secretariat |  | Create user group to under auspices secretariat. Define user requirements and provide feed-back to ICANN communication |
| Social Media | User of twitter, Facebook and other channels | March 2016 | March 2017 | ? / Secretariat |  | Create support group which together with secretariat will maintain and use social media for and from community |
| Update Regional Org meetings | Provide basic updates to ccTLD at Regional Organisations meetings | March 2016 | March 2017 | Councillors per Region / Secretariat |  | Provide basis slide set to Councillors who will inform ccTLD at Regional Organisations. Set up pool of Councillors, and basic template |