Action items flowing from UA working session

| Timeline | Action Item | What is available already? | Who will execute? | Success Indicator |
| --- | --- | --- | --- | --- |
| 0-3 months (completed by Mumbai) | Create clear UA definition document Simple explanation (under 5 pages) of what UA is, why it matters, standards to follow |  |  |  |
|  | Develop motivation toolkit 5-10 compelling use cases showing real-world impact |  |  | Use by GAC members and they can explain UA after reading |
|  | Draft model procurement language Ready-to-use policy text for government RFPs |  |  | Adopted by 2+ countries in adapted form |
| 3-6 months | Establish/promote government task forces 2-3 pilot countries with monitoring |  |  | Task forces meeting regularly including ccTLDs; progress reports published |
|  | Create simplified implementation roadmap Step-by-step guides for the four technical pillars |  |  | Roadmap rated 4/5+ helpful by users |
|  | Launch pilot implementations Document everything: problems, solutions, timelines, costs |  |  | Comprehensive case study completed |
| 6-24 months | Engage software licensing organizations Incorporate UA compliance into certification standards |  |  | 1+ licensing body formally adopts UA requirements |
|  | Activate bilateral relationships Coordinate UA requirements between trading partners |  |  | Country pairs with synchronized UA mandates |
|  | Align national with international standards Ensure interoperability through standards coordination |  |  | 95%+ success rate on cross-border interoperability tests |
|  | Strengthen UA tools website Central hub with testing tools, guides, case studies Increase subscription rate, promote ICANN UA website |  |  |  |

ccNSO UAC Action Plan  (https://docs.google.com/document/d/1Td27YCcDrDZ3pa4JzyX6n6CAY6anIG_n2kizDMcJACQ/edit?tab=t.0

Taking into consideration the various steps in the development of the UAC work plan, the UAC agreed on the following work items:

In the near or immediate future

- Completion library and email list (ongoing)

- Share success stories on implementation, explain benefits UA readiness

- Inform ccTLDs about future UA Day events (ongoing)

- Coordination with other groups under the ICANN umbrella (ongoing)

  - ccNSO appointed liaison to UASG, replaced with Expert Group

- Share existing UA-readiness roadmaps

Mid- to long term

The  UAC identified work items which require additional planning. These items will be detailed and addressed in the following order:

- Develop ccTLD readiness journeys case studies

- Conduct survey among ccTLDs regarding UA adoption (replaced with session on drivers and barriers)

- Assisting and cooperating with local counterparts to organize local events

- Liaising with email - and other service providers (e.g. local programming groups, W3C, registries and registrars etc)

- Planning and organizing a tabletop exercise