## DETAIL CALENDARS
OCT |  | NOV | DEC |  |  | JAN |  | FEB |  | MAR |  | APR | MAY |  | JUN |  | JUL
2014 | [5 empty] | 2015
5-YEAR OPERATING PLAN
-> OCT
STAFF finalizes DRAFT Planning Calendar and Roles & Responsibilities,
DRAFT 5-Year Operating Plan (goal-level), and
DRAFT 5-Year Financial Model
11 NOV
STAFF posts DRAFTS
11 NOV - 5 JAN
STAKEHOLDERS review & comment on DRAFTS
JAN
STAFF addresses public comments
JAN - FEB
STAFF consults & engages with STAKEHOLDERS, & updates DRAFTS
STAKEHOLDERS workshop during ICANN 52 (comments and responses)
MAR
BOARD approval
Version 1 - as of 10 November 2014. All dates are preliminary and subject to change.
OCT |  | NOV | DEC |  |  | JAN |  | FEB |  | MAR |  | APR | MAY |  | JUN |  | JUL
2014 | [5 empty] | 2015
FY16 OPERATING PLAN & BUDGET
27 OCT - 3 DEC
Ops STAFF prepares kick off package for Global Leadership meeting
3-15 DEC
Global Leaders set hi-level direction, Ops STAFF finalizes pkg for data collection
15 DEC - 4 FEB
Budget Owners develop DRAFT FY16 Op Plan & Budget
[TBD] JAN
BFC & BOARD review & provide input on PRELIM FY16 Revenue & Initiatives
29 JAN
STAFF posts PRELIM FY16 Revenue and Initiatives for ICANN 52
9-12 FEB
STAKEHOLDERS' consultation input at ICANN 52 on PRELIM FY16 Revenue & Initiatives
16 FEB - 4 MAR
STAFF reviews STAKEHOLDERS' input for adjustments
& finalizes DRAFT FY16 Op Plan & Budget
wk of 4 MAR
BFC review of DRAFT FY16 Op Plan & Budget
14-17 MAR
STAFF finalizes DRAFT FY16 Op Plan & Budget and posts
18 MAR - 1 MAY
STAKEHOLDERS review and comment on DRAFT FY16 Op Plan & Budget
[TBD] APR
BOARD briefing of DRAFT
1 - 22 MAY
STAFF addresses public comments
'1 - 22 MAY
STAFF consults & engages with STAKEHOLDERS
& updates DRAFT FY16 Op Plan & Budget
wk of 22 MAY
BFC review of
FINAL DRAFT FY16 Op Plan & Budget
1 -5 JUN
STAFF finalizes for BOARD
19 JUN
BOARD approval of
FY16 Op Plan & Budget
Version 1 - as of 10 November 2014. All dates are preliminary and subject to change.
OCT |  | NOV | DEC |  |  | JAN |  | FEB |  | MAR |  | APR | MAY |  | JUN |  | JUL
2014 | [5 empty] | 2015
FY16 SO/AC ADD'L BUDGET REQUESTS
1 DEC - 28 FEB
SO/ ACs submit funding requests for specific activities
not included in the recurring ICANN budget
9-12 FEB
SO/ACs consultation at ICANN 52
1-15 MAR
STAFF finalizes recommendations
15-31 MAR
BFC review of STAFF's recommendations
and makes recommendations to BOARD
15 APR
BOARD approval
Version 1 - as of 10 November 2014. All dates are preliminary and subject to change.
ICANN 52
ICANN 53
Global Leadership direction on:
revenue assumption/ scenarios
initiatives
baseline operating exp envelop
FY15 exit run-rate scenarios
FY16 exit run-rate scenarios
FY16 Op Plan & Budget package:
- overview
- portfolios
- risks & dependencies
- key performance indicators
- budget & projects of each portfolio
Public
Comment
Draft
ICANN
ICANN 53
ICANN 53
Public
Comment
ICANN 52
ICANN 53
Draft

## Sub-processes (hidden)
Topic | Owner | Action
Headcount planning | HR | HR to meet with budget owners about hiring needs
Capital | IT | IT to meet with budget owners re: capital needs for FY15
IT Infrastructure | Finance | Finance to provide expected headcount w/ location for IT planning