## Slide 1: ICANN FY15 Operating plan and Budget Process improvement working group October 30th 2013 – Call & Adobe room

## Slide 2: Table of Contents
Planning process environment
2. Guiding principles
3. Target planning
4. FY15 planning phases and timeline
5. Community interaction
6. Content overview
7. Additional budget requests process
8. Next steps

## Slide 3: 1. Planning process environment
ICANN Strategy panels
  Announced in July 2013,
  Intended conclusion April 2014
ATRT2 working group
  Expected recommendation on planning process
  Suggested public comment and Board communication processes
Internet Governance activity potentially affecting FY15
  Follow up of Bali IGF
  Brazil Internet governance summit

## Slide 4: 2. Guiding principles
Low visibility/predictability into FY15
  Need for increased flexibility in planning
  Increase contingency portion of the budget
While 5-year strategy is in development…
  Focus on Operating plan definition and communication for the next 18 months until June 2015.

## Slide 5: 3. Target Planning Process
STRATEGIC PLAN
OPERATING PLAN
BUDGET
5-year view
Input from Strat Plan (from multi year to fiscal year)
Activities & Projects
Objectives
Goals by year
Activities & Projects (refined)
Activities / Tasks
COMMUNITY & BOARD
Public Comments / Budget Approval
Notes: Community will be providing valuable input early on in the process, through frequent and effective interactions from the Strategic Plan and during the Framework building process (then validated by Board and CEO)
This will allow to already have community feedback, consensus, and buy-in on the content of the Framework while it is being developed.
ICANN staff can then refine the programs and projects defined by the Framework and resourced them within the constraint of the targeted fiscal year budget.
The community and the board will be re-engage when the draft Operating Plan and Budget is published.
The proposed Public Comments period will not be about gathering input for inclusion in the final Ops Plan but will serve as an opportunity to request clarification or comment on the process and provide ideas for improvements in upcoming year.

## Slide 6: 4. FY15 Planning Phases and Timeline
2013
Additional SO-AC budget requests
Draft Budget development
Draft Operating Plan Development
Dec
Oct
June
April
March
Feb
Jan
May
Nov
2014
Community and Staff interactions
* Directed Comments with focus areas to gather input **Comment on Process, request for clarity on particular content area, or improvements only; not to be included in Adopted Plan
**Public Comments
*Community Feedback
Publish Draft
Operating plan
Publish Draft Budget
London
Meeting
Singapore
Meeting
Buenos Aires
Meeting
ICANN Strategy Panels
Board approval
BFC review
BFC review

## Slide 7: 5. Community interaction
Operating plan
  Presentation of Operating plan by function (GSE, Policy, DNS Services, gTLD operations, Operations Services, Compliance,…) – End of January 2014 – Format to define (f2f meeting, Adobe sessions,…)
  Public comment process – concludes in Singapore
  Finalize Operating plan and start Budget development
Operating plan and Budget
  Operating plan and Budget presentation
  Published and communicated through call
  Public comment process
  Finalize for Board approval

## Slide 8
Operating plan
By Function
Total resources estimates (FTE, $$)
Budget
Variance of FY15 Budget vs FY14 Forecast
Objectives by Jun 2015 by portfolio/project
Recurring activities and projects
Build up by dept/function
Breakdown by portfolio/project, by category of costs
Deliverables
Multiple scenarios
Resources
6. Content Overview

## Slide 9: 7. Community Additional Budget requests process
Issues/needs | Suggested solution
Need more clarity on criteria when designing the requests | Provide at the inception of the process (November) the list of criteria used
Requests and their context may be require explanation | Schedule a call immediately after submission of requests with representative of requesting organization to review
Fast/regular track useful but confusing | Merge both tracks into one, which adopts the timing of the FY14 fast track.
Results coming too late and not clearly communicated | Results to be published immediately after Board approval. Call to be organized with each requesting organization to go over the results.
Implementation process not clear | Design and communicate the implementation process early Provide the ICANN Staff name to be contacted when publishing the results after Board approval
Missing issue?
Alternative approach?

## Slide 10: 8. Next steps
Format of interactions to be designed
Finalize detailed timing
Review with BFC in Buenos Aires