## Volunteer INPUT for Tues., 2 Ma
# | Theme | Subject | Board Action | Rec # | Recommendation(s) | Progress | ALAC Evaluation of the PRIORITY | ALAC Evaluation of the EFFORT | ALAC Evaluation of the URGENCY | Status/Comments/Notes | Overall Priority : Effort : Urgency | Internal Session SubPro (04-05-22) (Y, N, P) | Internal Session SubPro (04-05-22) SubPro Group INPUTS PLS include your name | Prerequisites None / Unknown | Timeline Implications Y, N, ? | Fora
1 | DNS abuse | SSR2 Rec | Pending the ordered "...evaluate[ion] how this grouping of recommendations, along with other recommendations that pertain to DNS security threats should be considered in a coordinated way,... " see Board Resolution 22jun21 | 12 | #12 - ICANN org should create a DNS Abuse Analysis advisory team composed of experts without financial conflicts of interest to recommend an overhaul of the DNS Abuse Reporting activity with actionable data, validation, transparency, and independent reproducibility of analyses as its highest priorities. | In progress | High++ | Moderate | High | This is linked to 14/15. There is lots of expertise available and ICANN should use external experts to help with the measurement of DNS abuse indicators. This is not the same as SSAC. In particular, it would make sense to involve academic researchers who are experts in "proper" methodology. | High, medium, high | Y | Example: Chantelle - None Susie - None
2 | DNS abuse | CCTRT | Accept the recommendation. The Board accepts recommendation 21, noting that items (1), (3), (4) and (5) listed within this recommendation are already part of ICANN Contractual Compliance Department’s reporting process. In connection with item (2) of the recommendation relating to “the gTLD that is target of the abuse”, the Board directs ICANN org to investigate the potential negative impacts of implementing this item on enforcement of compliance, track this effort and propose a mitigation plan in case of any negative effects. | 21 | Include more detailed information on the subject matter of complaints in ICANN publicly available compliance reports. Specifically, more precise data on the subject matter of complaints, particularly: (1) the class/type of abuse; (2) the gTLD that is target of the [DNS abuse]; (3) the safeguard that is at risk; (4) an indication of whether complaints relate to the protection of sensitive health or financial information; (5) what type of contractual breach is being complained of; and (6) resolution status of the complaints, including action details. These details would assist future review teams in their assessment of these safeguards. | Approved | High++ | Minimal | High | high priority for individual users, low difficulty, HIGH. Note: political, but easy to do. |  | N
3 | Metrics DNS abuse | CCTRT | Accept the recommendation. The Board directs ICANN org to initiate engagement within its existing budget, role, and work. The Board notes that while engagement can be initiated, it is unclear that ICANN org may have the ability to collect this data under the current contractual agreements and obligations. | 22 | Initiate engagement with relevant stakeholders to determine what best practices are being implemented to offer reasonable and appropriate security measures commensurate with the offering of services that involve the gathering of sensitive health and financial information. Such a discussion could include identifying what falls within the categories of “sensitive health and financial information” and what metrics could be used to measure compliance with this safeguard. | Approved | High++ | Significant | High | high priority for individual users, high difficulty, HIGH urgency |  | P
4 | DNS abuse | CCTRT | [This action pertains to a portion of the recommendation language - refer to bold text.] Note the portion of the recommendation and pass it through to the noted community groups for consideration. The Board is not accepting the policy directives that may be inherent here but rather, passes on such elements of the recommendation to the relevant community groups to consider. | 16 | Further study the relationship between specific registry operators, registrars, and DNS Security Abuse by commissioning ongoing data collection, including but not limited to, ICANN Domain Abuse Activity Reporting (DAAR) initiatives. For transparency purposes, this information should be regularly published, ideally quarterly and no less than annually, in order to be able to identify registries and registrars that need to come under greater scrutiny, investigation, and potential enforcement action by ICANN organization. Upon identifying abuse phenomena, ICANN should put in place an action plan to respond to such studies, remedy problems identified, and define future ongoing data collection. | Referred to another group | High++ | Significant | High | High priority for ALAC, high difficulty [SBT] Check if it is included in the current discussion about the DNS used to abuse end-users.
5 | DNS abuse | CCTRT | Note the recommendation and direct ICANN org to pass it along as input to the next CCT review for its consideration recognizing that the CCT Review Teams have the ability to set their charter according to the Bylaws and the Board cannot mandate their scope/charter. | 19 | The next CCT should review the "Framework for Registry Operator to Respond to Security Threats" and assess whether the framework is a sufficiently clear and effective mechanism to mitigate abuse by providing for systemic and specified actions in response to security threats. | Referred to another group | High++ | Significant | High | High priority for ALAC, high difficulty, high urgency
6 | DNS abuse | CCTRT | [This action pertains to a portion of the recommendation language - refer to bold text.] Note the portion of the recommendation and pass it through to the noted group, recognizing that the CCT Review Teams have the ability to set their charter according to the Bylaws and the Board cannot mandate their scope/charter. | 20 | Assess whether mechanisms to report and handle complaints have led to more focused efforts to combat abuse by determining: (1) the volume of reports of illegal conduct in connection with the use of the TLD that registries receive from governmental and quasi-governmental agencies; (2) the volume of inquires that registries receive from the public related to malicious conduct in the TLD; (3) whether more efforts are needed to publicize contact points to report complaints that involve abuse or illegal behavior within a TLD; and (4) what actions registries have taken to respond to complaints of illegal or malicious conduct in connection with the use of the TLD. Such efforts could include surveys, focus groups, or community discussions. If these methods proved ineffective, consideration could be given to amending future standard Registry Agreements to require registries to more prominently disclose their abuse points of contact and provide more granular information to ICANN. Once this information is gathered, future review teams should consider recommendations for appropriate follow up measures. | Referred to another group | High++ | Minimal | High | High priority for ALAC, low difficulty, high urgency
7 | DNS abuse Applicant Support Applicant Guidebook | CCTRT | Note the recommendation and pass the recommendation through to the noted community group, noting that ICANN org’s role is to implement the adopted recommendations resulting from the Sub Pro PDP WG’s work. To the extent that policies are adopted consistent with the recommendations, ICANN org will update the Applicant Guide Book (AGB) accordingly. | 25 | To the extent voluntary commitments are permitted in future gTLD application processes, all such commitments made by a gTLD applicant must state their intended goal and be submitted during the application process so that there is sufficient opportunity for community review and time to meet the deadlines for community and Limited Public Interest objections. Furthermore, such requirements should apply to the extent that voluntary commitments may be made after delegation. Such voluntary commitments, including existing voluntary PICs, should be made accessible in an organized, searchable online database to enhance data-driven policy development, community transparency, ICANN compliance, and the awareness of variables relevant to DNS abuse trends. | Referred to another group | High++ | Minimal | Medium | high priority for ALAC, low difficulty, high urgency
8 | Applicant Support | CCTRT | Note the recommendation and pass the recommendation through to the noted community group for their consideration. The Board notes that this topic is being discussed in the New gTLD Subsequent Procedures PDP WG and expectation is for a high-level program/guidance to be provided as a result of this work. | 32 | Revisit the Applicant Support Program. | Referred to another group | High | Moderate | Medium | high priority for ALAC, medium difficulty | Subject to availability of relevant ressources (Discount application fees, Pro-Bono and recurrent costs discount). Possible use of auction proceeds.
9 | Surveys | CCTRT | Place the recommendation in “Pending” status. The Board notes that ICANN org has already conducted periodic surveys, so work toward this recommendation has already taken place. The Board directs ICANN org to perform a gap analysis over the what has already been completed towards this recommendation and measured against broader community considerations of information that might be needed to support future community efforts. Once the scope of such surveys is better defined, the Board directs ICANN org to advise on what the cost of implementation would be. Additionally, outcome of the implementation of Recommendation 1 will inform the Board’s decision on next steps and whether this recommendation can be adopted to move into costing discussion phase of implementation. | 8 | Conduct periodic surveys of registrants that gathers both objective and subjective information with a goal of creating more concrete and actionable information. | Pending | High | Moderate | Medium | high priority, high cost, | Low difficulty if utilizing professional survey services. High cost if utilizing professional survey services
10 | Surveys | CCTRT | Place the recommendation in “Pending” status. As ICANN org has already conducted such surveys, the Board directs ICANN org to perform a full impact assessment on whether there will be any duplication of work or gap analysis. Once the scope of such surveys is better defined, Board directs ICANN org to advise on what the cost of implementation would be. Additionally, the outcome of the implementation of Recommendation 1 will inform the Board’s decision on next steps and whether this recommendation can be adopted to move into costing discussion phase of implementation. | 11 | Conduct periodic end-user consumer surveys. Future review teams should work with survey experts to conceive more behavioral measures of consumer trust that gather both objective and subjective data with a goal toward generating more concrete and actionable information. | Pending | High | Moderate | Medium | high priority, high cost | Low difficulty if utilizing professional survey services. High cost if utilizing professional survey services
11 | DNS abuse | CCTRT | Place the recommendation in “Pending” status. The Board directs ICANN org to consider if there are already effort that could be leveraged to meet this recommendation, such as the continuation of the previous DNS abuse study. In considering potential implementation, the Board also directs ICANN org to consider availability of data as part of its planning efforts, and the types of information that are available through contract as opposed to voluntary compliance through contracted parties. Additionally, the outcome of the implementation of Recommendation 1 will inform the Board’s decision on next steps and whether this recommendation can be adopted to move into costing discussion phase of implementation. | 13 | ICANN should collect data in conjunction with its related data collection activities on the impact of restrictions on who can buy domains within certain new gTLDs (registration restrictions) to help regularly determine and report: 1. Whether consumers and registrants are aware that certain new gTLDs have registration restrictions; 2. Compare consumer trust levels between new gTLDs with varying degrees of registration restrictions; 3. Determine whether the lower abuse rates associated with gTLDs that impose stricter registration policies identified in the Statistical Analysis of DNS Abuse in gTLDs Study continue to be present within new gTLDs that impose registration restrictions as compared with new gTLDs that do not 4. Assess the costs and benefits of registration restrictions to contracted parties and the public (to include impacts on competition and consumer choice) and; 5. Determine whether and how such registration restrictions are enforced or challenged. | Pending | High+ | Significant | Medium | high priority, high cost | Low difficulty if utilizing professional survey services. High cost if utilizing professional survey services
12 | DNS abuse | CCTRT | Place this recommendation in “Pending” status. The Board directs ICANN org to facilitate community efforts to develop a definition of “abuse” to inform further action on this recommendation. To negotiate amendments to address DNS Security Abuse measures, a common understanding of what “abuse” means must first be reached. | 15 | ICANN Org should, in its discussions with registrars and registries, negotiate amendments to the Registrar Accreditation Agreement and Registry Agreements to include provisions aimed at preventing systemic use of specific registrars or registries for DNS Security Abuse. With a view to implementing this recommendation as early as possible, and provided this can be done, then this could be brought into effect by a contractual amendment through the bilateral review of the Agreements. In particular, ICANN should establish thresholds of abuse at which compliance inquiries are automatically triggered, with a higher threshold at which registrars and registries are presumed to be in default of their agreements. If the community determines that ICANN org itself is ill-suited or unable to enforce such provisions, a DNS Abuse Dispute Resolution Policy (DADRP) should be considered as an additional means to enforce policies and deter against DNS Security Abuse. Furthermore, defining and identifying DNS Security Abuse is inherently complex and would benefit from analysis by the community, and thus we specifically recommend that the ICANN Board prioritize and support community work in this area to enhance safeguards and trust due to the negative impact of DNS Security Abuse on consumers and other users of the Internet. | Pending | High++ | Moderate | High | high priority, medium difficulty
13 | DNS Abuse | CCTRT | [This action pertains to a portion of the recommendation language - refer to bold text.] Place these two elements of the recommendation in “Pending status” and directs ICANN org to conduct a gap analysis of the study suggested by the CCT-RT compared to existing collection effort to inform usefulness of the study, and to inform whether establishing future ongoing data collection would be meaningful. The analysis should take into account the work that the org is already performing, such as Contractual Compliance audits. Additionally, the outcome of the implementation of Recommendation 1 will inform the Board’s decision on next steps and whether this recommendation can be adopted to move into costing discussion phase of implementation. | 16 | Further study the relationship between specific registry operators, registrars, and DNS Security Abuse by commissioning ongoing data collection, including but not limited to, ICANN Domain Abuse Activity Reporting (DAAR) initiatives. For transparency purposes, this information should be regularly published, ideally quarterly and no less than annually, in order to be able to identify registries and registrars that need to come under greater scrutiny, investigation, and potential enforcement action by ICANN organization. Upon identifying abuse phenomena, ICANN should put in place an action plan to respond to such studies, remedy problems identified, and define future ongoing data collection. | Pending | High++ | Moderate | High | high priority, medium difficulty
14 | DNS Abuse | CCTRT | [This action pertains to a portion of the recommendation language - refer to bold text.] Place this recommendation in “Pending” status. The Board notes that this recommendation contains elements that are outside of ICANN org’s role (i.e. amendments to contractual agreements), while other elements of this recommendation are costly and will require community input for prioritization and cost/benefit analysis (i.e. data collection). Furthermore, the Board agrees that anti-abuse measures are very important and notes that ICANN org has already implemented initiatives to that end; namely, DAAR, Identifier Technology Health Indicators, and Spec 11(3)(B). The Board directs ICANN org to perform an analysis of the work/initiatives already underway to determine any gaps in work currently in progress and what work recommendation entails. The Board will then review the results of the analysis and determine the best action on this recommendation, insofar as it falls within the ICANN Board or org’s remit. Additionally, the outcome of the implementation of Recommendation 1 will inform the Board’s decision on next steps and whether this recommendation can be adopted to move into costing discussion phase of implementation. | 20 | Assess whether mechanisms to report and handle complaints have led to more focused efforts to combat abuse by determining: (1) the volume of reports of illegal conduct in connection with the use of the TLD that registries receive from governmental and quasi-governmental agencies; (2) the volume of inquires that registries receive from the public related to malicious conduct in the TLD; (3) whether more efforts are needed to publicize contact points to report complaints that involve abuse or illegal behavior within a TLD; and (4) what actions registries have taken to respond to complaints of illegal or malicious conduct in connection with the use of the TLD. Such efforts could include surveys, focus groups, or community discussions. If these methods proved ineffective, consideration could be given to amending future standard Registry Agreements to require registries to more prominently disclose their abuse points of contact and provide more granular information to ICANN. Once this information is gathered, future review teams should consider recommendations for appropriate follow up measures. | Pending | High++ | Moderate | High | high priority, medium difficulty
15 | DNS Abuse | CCTRT | [This action pertains to a portion of the recommendation language - refer to bold text.] Place this recommendation in “Pending” status. The Board notes that this recommendation contains elements that are outside of ICANN org’s role (i.e. amendments to contractual agreements), while other elements of this recommendation are costly and will require community input for prioritization and cost/benefit analysis (i.e. data collection). Furthermore, the Board agrees that anti-abuse measures are very important and notes that ICANN org has already implemented initiatives to that end; namely, DAAR, Identifier Technology Health Indicators, and Spec 11(3)(B). The Board directs ICANN org to perform an analysis of the work/initiatives already underway to determine any gaps in work currently in progress and what work recommendation entails. The Board will then review the results of the analysis and determine the best action on this recommendation, insofar as it falls within the ICANN Board or org’s remit. Additionally, the outcome of the implementation of Recommendation 1 will inform the Board’s decision on next steps and whether this recommendation can be adopted to move into costing discussion phase of implementation. | 23 | ICANN should gather data on new gTLDs operating in highly-regulated sectors to include the following elements: - A survey to determine: 1) the steps registry operators are taking to establish working relationships with relevant government or industry bodies; and 2) the volume of complaints received by registrants from government and regulatory bodies and their standard practices to respond to those complaints. - A review of a sample of domain websites within the highly-regulated sector category to assess whether contact information to file complaints is sufficiently easy to find. - An inquiry to ICANN Contractual Compliance and registrars/resellers of highly regulated domains seeking sufficiently detailed information to determine the volume and the subject matter of complaints regarding domains in highly regulated industries. - An inquiry to registry operators to obtain data to compare rates of abuse between those highly-regulated gTLDs that have voluntarily agreed to verify and validate credentials to those highly-regulated gTLDs that have not. - An audit to assess whether restrictions regarding possessing necessary credentials are being enforced by auditing registrars and resellers offering the highly-regulated TLDs (i.e., can an individual or entity without the proper credentials buy a highly-regulated domain?). To the extent that current ICANN data collection initiatives and compliance audits could contribute to these efforts, we recommend that ICANN assess the most efficient way to proceed to avoid duplication of effort and leverage current work. | Pending | High+ | Moderate | Medium | high priority, low difficulty | There may considerable cost associated with this implementation.
16 | DNS Abuse | CCTRT | Place the recommendation in “Pending” status and request ICANN org to identify where there is a gap between work currently in progress and what the recommendation entails. Once the gap analysis is completed, ICANN org will share the findings with the community to ensure alignment on next steps and any changes that need to be made. This analysis will inform the Board’s decision on next steps and whether this recommendation can be adopted to move into costing discussion phase of implementation. Additionally, the outcome of the implementation of Recommendation 1 will inform the Board’s decision on next steps and whether this recommendation can be adopted to move into costing discussion phase of implementation. | 24 | a. Determine whether ICANN Contractual Compliance should report on a quarterly basis whether it has received complaints for a registry operator’s failure to comply with either the safeguard related to gTLDs with inherent governmental functions or the safeguard related to cyberbullying. b. Survey registries to determine: 1) whether they receive complaints related to cyberbullying and misrepresenting a governmental affiliation; and 2) how they enforce these safeguards. | Pending | High | Minimal | Medium | high priority, low difficulty
17 | Applicant Support (?) | CCTRT | Accept the recommendation. The Board accepts the recommendation and directs ICANN org to provide the Board with a report on related engagement, noting that if the community wishes to have more resources dedicated to this activity, this should be addressed in the next budget cycle. Given the interdependency between this recommendation and recommendation 29, as both recommendations rely upon the undefined term “Global South”, the Board notes that the New gTLD Subsequent Procedures PDP WG could take on, should they choose to do so, defining the term “Global South” for this purpose in coordination with ICANN org, its engagement teams, and geographic regions definitions to create a workable definition, or agreeing on another term to describe underserved or underrepresented regions or stakeholders in coordination with ICANN org. | 30 | Expand and improve outreach into the Global South. | Approved | High+ | Significant | Medium | high priority for ALAC, high difficulty
18 | Applicant Support | CCTRT | Accept contingent on the recommendation from the New gTLD Subsequent Procedures PDP WG that the pro bono assistance program continue. | 31 | The ICANN organization to coordinate the pro bono assistance program. | Approved | High | Moderate | Medium | high priority for ALAC, already adopted? Note: nothing formally organized by ICANN itself.
19 | Metrics Applicant Support (?) | CCTRT | Note the recommendation and pass the recommendation through to the noted community groups for their consideration. Given the interdependency between this recommendation and recommendation 30, as both recommendations rely upon the same undefined term “Global South”, the Board notes that the New gTLD Subsequent Procedures PDP WG could take on, should they choose to do so, defining the term “Global South” in coordination with ICANN org, its engagement teams, and geographic regions definitions to create a workable definition, or agreeing on another term to describe underserved or underrepresented regions or stakeholders in coordination with ICANN org. | 29 | Set objectives/metrics for applications from the Global South. | Referred to another group | High | Moderate | Medium | high priority for ALAC, medium difficulty; | Noting the specific recommendations out of the SubPro WG
20 | Registration Data (is this still applicable?) | RDS/WHOIS2 | The Board places this recommendation in pending status until completion of Board action on the EPDP Phase 2, priority 2 topics.The Board will consider the recommendation after evaluating the outcomes of the EPDP Phase 2. | R5.1 | The Accuracy Reporting System, which was instituted to address concerns regarding RDS (WHOIS) contact data accuracy, has demonstrated that there is still an accuracy concern and therefore such monitoring must continue. ICANN organization should continue to monitor accuracy and/or contactability through either the ARS or a comparable tool/methodology. [RT: High] | Pending | High++ | Significant | High | Pending EPDP Phase 2, 2a GNSO Data Accuracy Scoping Team
21 | Registration Data (is this still applicable?) | RDS/WHOIS2 | The Board places this recommendation in pending status until completion of Board action on the EPDP Phase 2, priority 2 topics.The Board will consider the recommendation after evaluating the outcomes of the EPDP Phase 2. | R10.1 | The Board should monitor the implementation of the PPSAI. If the PPSAI policy does not become operational by 31 December 2019, the ICANN Board should ensure an amendment to the 2013 RAA (or successor documents) is proposed that ensures that the underlying registration data of domain name registrations using Privacy/Proxy providers affiliated with registrars shall be verified and validated in application of the verification and validation requirements under the RAA unless such verification or validation has already occurred at the registrar level for such domain name registrations. [RT: Low] | Pending | High++ | Minimal | High | Pending Board analysis of EPDP Phase 2. Why that is is unclear. EPDP made it clear that there is no relevance to PPSAI.
22 | Metrics | RDS/WHOIS2 | The Board approves this recommendation, recognizing the work currently underway, in alignment with ATRT3. | R15.1 | The ICANN Board should ensure that implementation of RDS-WHOIS2 Review Team recommendations is based on best practice project management methodology, ensuring that plans and implementation reports clearly address progress, and applicable metrics and tracking tools are used for effectiveness and impact evaluation. [RT: Medium] | In progress | High++ | Other (Full details in Column J) |  | This is an aspirational recommendation that the tracking and reporting on the implementations should accurately record what was done to address the recommendation. Such reporting must not be mainly an effort to "tick off boxes". One would hope that this should be a standard business practice.
23 | Applicant Support | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-01A | Any expansion of the New gTLD Program must be beneficial to all stakeholders. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
24 | Metrics | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-01B | Program Objectives must be sufficiently reviewed and particularized to enable formulation of suitable metrics for effective evaluation beyond just general consumer choice, and Domain Name System (DNS) marketplace competition aspects. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
25 | DNS abuse | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-01C | Any expansion of the domain namespace must not compromise the stability, security and resiliency of the DNS. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
26 | Metrics DNS abuse | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-02A | The Competition, Consumer Trust, and Consumer Choice Review Team (CCTRT) Report of 2018 focused on two things: intention (goals, objectives) and data, therefore the relevant recommendations represent important inputs. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
27 | DNS Abuse | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-02B | Our concerns remain over the actions (or lack thereof) by the SubPro WG with respect to CCTRT Recommendations #14, #15, #16 (to do with DNS Security Abuse) and #29, #31 and #32 (to do with the Applicant Support Program), resulting in deficiencies which we hope the ICANN Board will shepherd the community and ICANN Org in addressing. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
28 | ?? | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-02C | Our concerns also remain over the seemingly lack of policy direction in respect of CCTRT Recommendation #12(1) (to do with user expectation regarding the relationship of content of a gTLD to its name), an omission which we hope the ICANN Board will consider addressing. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
29 | DNS Abuse CCTRT Recs Applicant Support (?) | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-02D) | While noting ICANN Board’s action on the CCTRT recommendations through its resolutions of 1 March 2020 and 22 October 2020, we strongly advise the ICANN Board to ensure that all prerequisite and high priority CCTRT recommendations are implemented, at the latest, prior to the launch of the next round. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
30 | DNS abuse | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-03A | The ALAC deems the SubPro WG’s approach of Recommendation 9.15 (which is to defer the issue of DNS Abuse mitigation solely to a wider ICANN community effort or “holistic approach”) as foregoing a valuable opportunity to modernize existing contracts with Registries and Registrars in order to contractually compel more immediate, increased efforts to stem ‘abuse’ (as defined by the contracted parties themselves). | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
31 | DNS abuse | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-03B | The ALAC opines that a new application round represents a carrot and a more immediate avenue to draw contracted parties to negotiate improvements to their own DNS Abuse mitigation efforts; absent this incentive, such improvements are likely perceived as merely expensive new regulation. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
32 | DNS abuse | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-03C | Notwithstanding, the ALAC believes that the landscape of DNS Abuse continues to evolve and that anti-abuse measures must be continuously updated, if not widened, to also recognize and address new forms of harm being perpetrated by bad actors. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
33 | DNS abuse | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-03D | Therefore, if the ICANN Board sought to agree with the suggested “holistic approach”, then the ALAC strongly urges the Board to also ensure that not only must those community discussions take place promptly, but that they be completed with outcomes put in place prior to the launch of the next round of applications for New gTLDs. To this end, we believe it is imperative for the ICANN Board consider the following inputs: o Prior ALAC Advice on DNS Abuse; o The SSR2 Final Report recommendations touching on contracts, compliance, and transparency around DNS Abuse; o The SSAC’s proposition in SAC114 Recommendation 3 regarding best practices for mitigation of the domain name abuse; o The SSAC’s proposal in SAC115 for a Common Abuse Response Facilitator to streamline abuse reporting and minimizing of abuse victimization, as well as the call to ensure a much wider community participation in broadening the definition of DNS Abuse to one that is not merely confined to the perspectives of contracted parties; and o An expected proposal for concrete action on DNS Abuse Mitigation arising from the work being undertaken by the GAC Public Safety Working Group (PSWG). | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
34 | DNS abuse | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-04A | We noted the ICANN Board’s expressed concern that ICANN may end up enforcing contract provisions that lie outside its remit. However, the ALAC opines that any need to minimize ICANN regulation that falls outside its remit must not displace the exigency for all provisions in contract with ICANN to be enforceable and to be enforced by ICANN Contractual Compliance. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
35 | DNS abuse | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-04B | Any provision that ICANN does not intend to enforce should not appear in contracts with Registries and/or Registrars. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
36 | PIC/RVCs | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-04C | Should a jurisdictionally competent dispute resolution procedure determination or ruling of unenforceability (on whatever grounds) be served on ICANN, the ICANN Board must take action to remedy such unenforceability, by preserving, where feasible, the original intention of the affected PIC or RVC through negotiation with all impacted contracted parties or other actions. Such actions could, if necessary, include Bylaw amendments. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
37 | PIC/RVCs (?) | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-04D | The ALAC notes that the ICANN Bylaws Article 1, Section 1.1(c) reads “ICANN shall not regulate (i.e., impose rules and restrictions on) services that use the Internet's unique identifiers or the content that such services carry or provide, outside the express scope of Section 1.1(a)”. The parenthetical expression clearly says that ICANN cannot impose its own rules or restrictions in regard to content. There is therefore no restriction on ICANN enforcing commitments made by TLD operators in their contracts with ICANN that are in the pursuit of their own business interests. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
38 | PIC/RVCs | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-04E | The ALAC believes that SubPro WG’s Affirmation 41.1 and Recommendation 41.2 are to apply equally to PICs and RVCs; and recommends that the ICANN Board direct that ICANN Contractual Compliance’s role in publishing more information on compliance action to encompass information on standards and thresholds for assessing registry practices, including guidelines on how each threshold is derived and applied to determine compliance or noncompliance of a PIC or an RVC for purposes of imposing sanctions and/or triggering/effecting Registry Agreement termination. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
39 | PIC/RVCs | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-04F | At the time that PICs were first introduced, the ALAC was assured that they would be enforceable by Contractual Compliance and not solely through PIC Dispute Resolution Procedures (PICDRPs). PICDRPs require that the entity initiating the dispute must show measurable harm. It should not be necessary to show harm to have contracts enforced and the Board must ensure that the original commitment is honored. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
40 | PIC/RVCs | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-04G | As such, the ALAC recommends that the Board instigate a review of the PICDRP to allow for complaints against any alleged registry violation of a PIC or RVC to be taken up and determined not only where the complainant is able to show evidence of significant harm suffered (as is currently required) but also on the grounds of foreseeable harm to themselves or even a third party. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
41 | IDNs | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-05A | The ALAC remains convinced that any expansion of the new gTLD market must actively and effectively facilitate the inclusion of the next billion Internet end-users, i.e. those who depend on Internationalized Domain Names (IDNs) and IDN-emails and that Universal Acceptance (UA) is key in ensuring this outcome. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
42 | IDNs | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-05B | Therefore, while the ALAC recommends that the ICANN Board lead the pursuit of greater action towards UA-adoption through specific measures such as, including a metric on UA adoption by third parties as a measure of success for the New gTLD Program, and encouraging increased promotion for UA-readiness by contracted parties and with new applicants. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
43 | NCAP | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-06A | The ALAC supports the ICANN Board’s continued keen interest in the outcome of the SSAC’s Name Collision Analysis Project (NCAP) and its impact on Subsequent Procedures and the future rounds of the New gTLD Program. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
44 | NCAP | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-06B | We join the SSAC in recommending that the ICANN Board, prior to authorizing the addition of new gTLDs to the root zone, receive and consider the results of the NCAP, pursuant to Board Resolution 2017.11.02.30. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
45 | NCAP | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-06C | Further, we strongly advocate for the recommendations of SSAC resulting from the NCAP Studies 2 and 3 (as approved by the ICANN Board) to be implemented prior to the launch of the next round of applications for New gTLDs; or in the alternative, that delegation of any applied-for strings which pose a risk of name collisions be withheld until the NCAP studies are completed and recommendations are addressed in implementation, retrospectively for the next round. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
46 | Closed Generics | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-07 | In the present absence of consensus policy recommendations by SubPro WG with respect to Closed Generics, the ALAC advises the ICANN Board to direct ICANN Org to suspend any processing or acceptance of any applications for Closed Generics until such time consensus policy is adopted on how to address applications for Closed Generics which serve a global public interest. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
47 | Metrics Applicant Support | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-08A | The ALAC finds the Applicant Support Program (ASP) to be another area for which a lack of concrete policy guidance and evaluation metrics. While the SubPro has made some recommendations to improve the ASP, the evident absence of specific goals hinders proper evaluation of program objectives and performance. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
48 | Applicant Support Auctions | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-08B | We also question the wisdom of leaving many key aspects for development by a Dedicated Implementation Review Team (IRT) – such as addressing a risk of gaming, assessment of willful gaming and penalties to deter the gaming, and development of the Bid Credit for Applicant Support qualifiers – since these would conceivably involve questions of policy where the community’s input would prove crucial. Faced with this situation, we call for priority for ALAC membership in the Dedicated IRT. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
49 | Applicant Support | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-08C | From an implementation standpoint, we strongly advise the ICANN Board to direct ICANN Org, firstly, to secure a larger fund to meaningfully support the ASP in the next round, and secondly, to take a more active coordinating role in the ASP pro-bono assistance mechanism. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
50 | Auctions | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-09A | The ALAC continues to strongly oppose not only allowing private actions in subsequent procedures but also the use of a second-price, sealed bid auction instead of the Vickrey auction solution as the mechanism to resolve contention sets. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
51 | Auctions | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-09B | We share the Board’s concerns towards an applicant’s ability to ‘shuffle funds between private auctions’. This ability for a loser to apply proceeds from one private auction to fund their other private auctions only really benefits incumbent multi-TLD registry operators or multiple-string applicants, and clearly disadvantages single-TLD/niche applicants. With ongoing and increasing consolidation of the domain name industry, allowing private auctions will likely exacerbate the advantage for merged contracted parties, leading to less competition among registries. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
52 | Auctions | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-09C | Thus, we believe there should be a ban on private auctions. Also, by mandating ICANN only auctions, the proceeds of any such ICANN auctions can at least be directed for uses in pursuit of public interest, such as was determined through the CCWG on Auction Proceeds. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
53 | Auctions Applicant Support | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-09D | We also believe that the use of a bona fide intent affirmation – whether for all applicants or otherwise – where factors for establishing a lack of bona fide intent are too subjective, and without deterrence through penalty, serves little purpose. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
54 | Auctions Applicant Supportt | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-09E | As for the proposed Contention Resolution Transparency Requirements framework, we do not agree with the protections for disclosing applicants and advise the Board to ensure that all terms of every concluded private resolution be disclosed to ICANN Org (subject to a nondisclosure commitment by ICANN Org where necessary) as data to support and inform future policy work. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
55 | Community Priority Evaluation (CPEs) | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-10 | The ALAC applauds the SubPro WG’s inclusion of many of the At-Large suggestions to reform and improve the CPE process, evaluation criteria procedures and guidelines in the SubPro Final Report. However, the SubPro WG recommendations fell short on 2 counts for which we call on the ICANN Board to redress:- o Implementation Guidance 34.4 fails to address an unreasonable impediment to proving both “awareness and recognition of the community members” for CPE Criterion 1- A; the allowance made only in respect of the “recognition of community members” aspect ignores the conjunctive “and” in Criterion 1-A, such that a worthy community applicant would still forfeit valuable points where “awareness of the community members” is also not measurable. o Implementation Guidance 34.12 fails to stipulate that the shortlisting and selection of CPE provider(s) by ICANN Org be subject to community input as a proactive measure for selecting the most suitable CPE Provider for subsequent procedures in order to avoid a repeat of the widespread criticisms resulting from the CPE evaluations for the 2012 round of applications. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
56 | Geographic Names at the top level | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-11A | Despite the welcomed retention of much of the 2012 AGB implementation relating to Geographic Name at the Top Level (and their adoption as new consensus policy in place of the much less favourable ones in the GNSO 2007 Consensus Policy), the ALAC remains concerned over the insufficient support within the community for the need to respect and take into consideration the voice of stakeholders to future applications for strings matching many names with geographical meaning. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
57 | Applicant Support | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-11B | We ask the ICANN Board to consider the public interest ramifications and serious potential consequences in allowing applications for Non-Capital City Name strings which do not clearly allude to and/or commit applicants to whether the TLD will be used primarily for purposes associated with that city name. We opine that stronger preventive protection for such strings is merited to prevent unintended consequences. Therefore, we reiterate our call for applications for strings which match the names of non-capital cities meeting specified criteria to be accompanied by letters of support/non-objection from relevant local governmental/public authorities irrespective of the applicant’s declared use of the TLD. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
58 | Geographic Names at the Top Level | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-11C | The ALAC also asks that the ICANN Board consider directing ICANN Org to provide a Notification Tool exclusively to GAC Members who wish to be informed of any applications for strings matching any names with geographical meaning as submitted by participating GAC Members under any established conditions or criteria. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
59 | Applicant Support | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-11D | Lastly, we are disappointed at the lack of community-wide support for an ICANN Org-provided opt-in update system for interested parties to automatically keep them informed on application(s) for specified string(s), a tool we see simply as a logical extension of SubPro WG’s Implementation Guidance 20.5. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
60 | Community Priority Evaluation (CPEs) | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-12A | The 2012 AGB Sections 3.2.2 and 3.2.2.4 appear to suggest that the ALAC is required to prove 2 elements to qualify for standing for a community objection. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
61 | Community Priority Evaluation (CPEs) | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-12B | It is incomprehensible that the ALAC, while on the one hand, funded by ICANN Org to file objections, should have any of its Community Objections, which would be derived through a bottom-up participative process, be dismissed on the ground of a ‘lack of standing’ to file such objections. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
62 | Community Priority Evaluation (CPEs) | ALAC Advice - SubPro | Progress pending the New gTLD Subsequent Procedures Final Report | R-12C | Therefore, the ALAC strongly recommends that it be granted, under no uncertain terms, automatic standing to file Community Objections in Subsequent Procedures and in future rounds of the New gTLD Program. | Phase 2 ¦ Understand Request |  |  |  | Phase 2 Update: The ICANN Board and Org are currently reviewing and considering this advice. In December 2022, ICANN org delivered the New gTLD Subsequent Procedures Operational Assessment to the Board, which identified the ALAC's advice as an item that may need a decision or action be taken before the next round is to proceed. On 16 March 2023, the Board adopted 98 recommendations contained in the New Generic Top-Level Domain (gTLD) Subsequent Procedures (SubPro) Policy Development Process Final Report (Final Report). The Board's 16 March 2023 resolution acknowledged the ALAC's contributions on the Final Report, which was used to inform the Board's deliberations on the Final Report recommendations. The Board continues to review and consider the ALAC advice to determine whether there are actionable items that may require Board action now that the Board has taken action on a substantial number of SubPro policy recommendations. The Board anticipates that this exercise will be completed in the first half of 2023 and that a response to the advice would come before the Board takes action on the remaining SubPro policy recommendations.
63 | DNS abuse | ALAC Advice - DNS abuse Rec 1 | 10Oct20: As stated in the Board's response to DNS Abuse related recommendations from SSR2, the Board has asked ICANN Org's DNS Security Threat Mitigation Program and the DNS abuse Board Caucus group to consider all of the pending advice and recommendations and develop a strategic and holistic approach. This process is underway and not yet complete. 11Apr20: ICANN received confirmation of understanding 27Jan20: ICANN sent the following understanding to the ALAC for review. Understanding: ICANN org understands ALAC to advise the Board to direct ICANN org to establish a clear definition of “abuse” that is within ICANN’s remit. We assume that any such definition would, without limitation, include harmful activity insofar as they intersects with the DNS and involves the use of malware, botnets, phishing, pharming, and spam (when it serves as a delivery mechanism for the other forms of DNS abuse). ICANN org further understands ALAC to advise the Board to direct org to clarify the “purposes and applications of ""abuse"" before further work is done to define DNS abuse.” We are unsure, however, what ALAC’s reference to “purposes and applications” of abuse is intended to mean and request clarification on this point. Is ALAC's advice to identify the characteristics of abuse (e.g., behavior that affects the DNS in specified ways) that would be within ICANN’s remit? If so, ICANN org also understands ALAC to advise that once the scope and characteristics of abuse within ICANN’s remit is identified, a determination should be made whether abuse definitions used by outside sources can serve as references for the ICANN community, or whether a new, outcomes-based nomenclature could be useful (including impersonation, fraud, or other types of abuse) to accurately describe problems being addressed. ICANN received ALAC: DNS Abuse on 10 January 2020 and is currently reviewing. | R-1 | Establish a clear definition of DNS Abuse. The GNSO has already produced consensus definitions of “abuse” and “malicious use of domain names” that are more expansive. According to that definition, “abuse” is an action that: 1) Causes actual and substantial harm, or is a material predicate of such harm; and 2) Is illegal or illegitimate, or is otherwise considered contrary to the intention and design of a stated legitimate purpose, if such a purpose is disclosed. The GNSO also recognized that “malicious use of domain names” include, but are not limited to: 1) spam, 2) malware distribution, 3) online child sexual exploitation and imagery abuse, 4) phishing, 5) botnet command-and-control. ICANN should clarify the purposes and applications of “abuse” before further work is done to define DNS abuse. Once those purposes are identified, ICANN should determine whether abuse definitions used by outside sources can serve as references for the ICANN community, or whether a new, outcomes-based nomenclature could be useful (including impersonation, fraud, or other types of abuse) to accurately describe problems being addressed. | Phase 3 ¦ Evaluate & Consider |  |  |  | ICANN org understands ALAC to advise the Board to direct ICANN org to establish a clear definition of “abuse” that is within ICANN’s remit. We assume that any such definition would, without limitation, include harmful activity insofar as they intersect with the DNS and involves the use of malware, botnets, phishing, pharming, and spam (when it serves as a delivery mechanism for the other forms of DNS abuse). ICANN org further understands ALAC to advise the Board to direct org to clarify the “purposes and applications of ""abuse"" before further work is done to define DNS abuse.” We are unsure, however, what ALAC’s reference to “purposes and applications” of abuse is intended to mean and request clarification on this point. Is ALAC's advice to identify the characteristics of abuse (e.g., behavior that affects the DNS in specified ways) that would be within ICANN’s remit? If so, ICANN org also understands ALAC to advise that once the scope and characteristics of abuse within ICANN’s remit is identified, a determination should be made whether abuse definitions used by outside sources can serve as references for the ICANN community, or whether a new, outcomes-based nomenclature could be useful (including impersonation, fraud, or other types of abuse) to accurately describe problems being addressed.
64 | DNS abuse | ALAC Advice - DNS abuse Rec 2 | 10Oct20: As stated in the Board's response to DNS Abuse related recommendations from SSR2, the Board has asked ICANN Org's DNS Security Threat Mitigation Program and the DNS abuse Board Caucus group to consider all of the pending advice and recommendations and develop a strategic and holistic approach. This process is underway and not yet complete. 11Apr20: ICANN received confirmation of understanding 27Jan20: ICANN sent the following understanding to the ALAC for review. Understanding: ICANN org understands ALAC to advise the Board to direct ICANN org to prohibit Contracted Parties from rate limiting WHOIS (eventually RDAP) requests or to require Contracted Parties to simplify the process of whitelisting. ICANN understands that ALAC believes that these changes would facilitate improved reporting on the rate of abuse in the registration ecosystem that falls within ICANN’s remit. ICANN also understands that ALAC advises the Board to cause ICANN to require Contracted Parties to adopt a uniform and timely access framework for publicly available registrant data, but requests further clarification as to ALAC’s expectations in this regard. Does the ALAC recommendation refer to something beyond universal adoption of RDAP and implementation of policies developed by the EPDP? With respect to implementation of this recommendation, and taking into account that ALAC is empowered to initiate discussions leading to the creation of a PDP, ICANN org understands that ALAC advises the Board either to (i) initiate a PDP process by calling for an Issues Report or (ii) cause ICANN Org to enter into voluntary negotiations with Contracted Parties to prohibit rate limiting or simplify the white-listing process and to adopt a uniform and timely framework for access to publicly available registrant data. ICANN received ALAC: DNS Abuse on 10 January 2020 and is currently reviewing. | R-2 | Cease rate limiting WHOIS (eventually RDAP) or simplify the process of whitelisting, so that it can report on the registration ecosystem. Adopt a uniform and timely access framework for publicly available registrant data. | Phase 3 ¦ Evaluate & Consider |  |  |  | ICANN org understands ALAC to advise the Board to direct ICANN org to prohibit Contracted Parties from rate limiting WHOIS (eventually RDAP) requests or to require Contracted Parties to simplify the process of whitelisting. ICANN understands that ALAC believes that these changes would facilitate improved reporting on the rate of abuse in the registration ecosystem that falls within ICANN’s remit. ICANN also understands that ALAC advises the Board to cause ICANN to require Contracted Parties to adopt a uniform and timely access framework for publicly available registrant data, but requests further clarification as to ALAC’s expectations in this regard. Does the ALAC recommendation refer to something beyond universal adoption of RDAP and implementation of policies developed by the EPDP? With respect to implementation of this recommendation, and taking into account that ALAC is empowered to initiate discussions leading to the creation of a PDP, ICANN org understands that ALAC advises the Board either to (i) initiate a PDP process by calling for an Issues Report or (ii) cause ICANN Org to enter into voluntary negotiations with Contracted Parties to prohibit rate limiting or simplify the white-listing process and to adopt a uniform and timely framework for access to publicly available registrant data.
65 | DNS abuse | ALAC Advice - DNS abuse Rec 3 | 10Oct20: As stated in the Board's response to DNS Abuse related recommendations from SSR2, the Board has asked ICANN Org's DNS Security Threat Mitigation Program and the DNS abuse Board Caucus group to consider all of the pending advice and recommendations and develop a strategic and holistic approach. This process is underway and not yet complete. 11Apr20: ICANN received confirmation of understanding. 27Jan20: ICANN sent the following understanding to the ALAC for review. Understanding: ICANN org understands ALAC to advise the Board to direct ICANN org to establish low thresholds for identifying bad actors. We interpret this to mean that ALAC advises the Board to direct ICANN org to use DAAR to identify operators with high concentrations of malware, botnets, phishing, pharming, and spam (when it serves as a delivery mechanism for the other forms of DNS abuse) and other abusive behaviors within ICANN’s remit once, with respect to the latter, agreement is reached on the scope and characteristics of abuse within ICANN’s remit (either through Consensus Policy development or through voluntary contract negotiations between ICANN and Contracted Parties). ICANN also understands that ALAC advises the Board to direct ICANN org to identify and acquire data needed to publish more actionable DAAR data and to identify registrars that sponsor or registries containing high concentrations of domain registrations engaged in such behaviors. ICANN received ALAC: DNS Abuse on 10 January 2020 and is currently reviewing. | R-3 | Direct ICANN Org to establish low thresholds for identifying bad actors. Direct ICANN Org to publish more actionable Domain Abuse Activity Reporting (DAAR) data: identifying the operators with high concentrations of abuse against whom onward action ought to be contemplated. | Phase 3 ¦ Evaluate & Consider |  |  |  | ICANN org understands ALAC to advise the Board to direct ICANN org to establish low thresholds for identifying bad actors. We interpret this to mean that ALAC advises the Board to direct ICANN org to use DAAR to identify operators with high concentrations of malware, botnets, phishing, pharming, and spam (when it serves as a delivery mechanism for the other forms of DNS abuse) and other abusive behaviors within ICANN’s remit once, with respect to the latter, agreement is reached on the scope and characteristics of abuse within ICANN’s remit (either through Consensus Policy development or through voluntary contract negotiations between ICANN and Contracted Parties). ICANN also understands that ALAC advises the Board to direct ICANN org to identify and acquire data needed to publish more actionable DAAR data and to identify registrars that sponsor or registries containing high concentrations of domain registrations engaged in such behaviors.
66 | DNS abuse | ALAC Advice - DNS abuse Rec 4 | 10Oct20: As stated in the Board's response to DNS Abuse related recommendations from SSR2, the Board has asked ICANN Org's DNS Security Threat Mitigation Program and the DNS abuse Board Caucus group to consider all of the pending advice and recommendations and develop a strategic and holistic approach. This process is underway and not yet complete. 11Apr20: ICANN received confirmation of understanding 27Jan20: ICANN sent the following understanding to the ALAC for review. Understanding: ICANN org understands ALAC to advise the Board to provide an explicit mandate to ICANN Contractual Compliance to regularly use the audit function to root out “systemic” abuse; not to regulate content, but to proactively exercise enforceability. We interpret this to mean that the ALAC is advising the Board to direct ICANN org to do so now with respect to malware, botnets, phishing, pharming, and spam (when it serves as a delivery mechanism for the other forms of DNS abuse) and, once agreement is reached on the scope and characteristics of abuse within ICANN’s remit (either through Consensus Policy development or through voluntary contract negotiations between ICANN and Contracted Parties), other such behaviors. We understand that the ALAC is advising the Board to direct ICANN org to undertake regular audits of compliance with resulting obligations. ICANN received ALAC: DNS Abuse on 10 January 2020 and is currently reviewing. | R-4 | Provide an explicit mandate to ICANN Contractual Compliance to regularly use the audit function to root out “systemic” abuse; not to regulate content, but to proactively exercise enforceability. | Phase 3 ¦ Evaluate & Consider |  |  |  | ICANN org understands ALAC to advise the Board to provide an explicit mandate to ICANN Contractual Compliance to regularly use the audit function to root out “systemic” abuse; not to regulate content, but to proactively exercise enforceability. We interpret this to mean that the ALAC is advising the Board to direct ICANN org to do so now with respect to malware, botnets, phishing, pharming, and spam (when it serves as a delivery mechanism for the other forms of DNS abuse) and, once agreement is reached on the scope and characteristics of abuse within ICANN’s remit (either through Consensus Policy development or through voluntary contract negotiations between ICANN and Contracted Parties), other such behaviors. We understand that the ALAC is advising the Board to direct ICANN org to undertake regular audits of compliance with resulting obligations.
67 | DNS abuse | ALAC Advice - DNS abuse Rec 5 | 10Oct20: As stated in the Board's response to DNS Abuse related recommendations from SSR2, the Board has asked ICANN Org's DNS Security Threat Mitigation Program and the DNS abuse Board Caucus group to consider all of the pending advice and recommendations and develop a strategic and holistic approach. This process is underway and not yet complete. 11Apr20: ICANN received confirmation of understanding 27Jan20: ICANN sent the following understanding to the ALAC for review. Understanding: ICANN org understands ALAC to advise the Board to direct ICANN org to prohibit Contracted Parties from processing registrations where the payor is or the method of payment belongs to an individual or entity other than the registrant, unless such payment methods have been approved in advance of registration. With respect to implementation of this recommendation, and taking into account that ALAC is empowered to initiate discussions leading to the creation of a PDP, ICANN Org understands that ALAC advises the Board either to (1) initiate a PDP by calling for an Issue Report on this topic or (ii) cause ICANN Org to enter into voluntary negotiations with Contracted Parties to implement ALAC’s advice. ICANN received ALAC: DNS Abuse on 10 January 2020 and is currently reviewing. | R-5 | Do not process registrations with “third party” payments, unless they have been approved prior to the request. | Phase 3 ¦ Evaluate & Consider |  |  |  | ICANN org understands ALAC to advise the Board to direct ICANN org to prohibit Contracted Parties from processing registrations where the payor is or the method of payment belongs to an individual or entity other than the registrant, unless such payment methods have been approved in advance of registration. With respect to implementation of this recommendation, and taking into account that ALAC is empowered to initiate discussions leading to the creation of a PDP, ICANN Org understands that ALAC advises the Board either to (1) initiate a PDP by calling for an Issue Report on this topic or (ii) cause ICANN Org to enter into voluntary negotiations with Contracted Parties to implement ALAC’s advice.
68 | DNS abuse | ALAC Advice - DNS abuse Rec 6 | 10Oct20: As stated in the Board's response to DNS Abuse related recommendations from SSR2, the Board has asked ICANN Org's DNS Security Threat Mitigation Program and the DNS abuse Board Caucus group to consider all of the pending advice and recommendations and develop a strategic and holistic approach. This process is underway and not yet complete. 11Apr20: ICANN received clarification for questions provided 27Jan20: ICANN sent the following clarifying questions to the ALAC for review. Clarifying Questions: ICANN org requests clarification of this ALAC advice. Does ALAC advise the Board to direct ICANN org to cause Contracted Parties to obligate registrants to comply with an acceptable use policy that prohibits the registration and/or use of domain name for criminal or otherwise abusive purposes? Alternatively, does ALAC advise the Board to direct ICANN org to obligate Contracted Parties to take specified steps with respect to registrations used in the course of criminal or otherwise abusive conduct? If not, please clarify ALAC’s advice. With respect to implementation of this recommendation, and taking into account that ALAC is empowered to initiate discussions leading to the creation of a PDP, ICANN org understands that ALAC advises the Board either to (1) initiate a PDP by calling for an Issue Report on this topic (ii) or cause ICANN org to enter into voluntary negotiations with Contracted Parties to implement ALAC’s advice. If this understanding is incorrect, what is ALAC’s recommendation with respect to development and adoption of an “anti-crime, anti-abuse” Acceptable Use Policy (AUP) that includes enforcement? ICANN received ALAC: DNS Abuse on 10 January 2020 and is currently reviewing. | R-6 | Adopt an “anti-crime, anti-abuse” Acceptable Use Policy (AUP) and include enforcement. | Phase 3 ¦ Evaluate & Consider |  |  |  | With respect to implementation of this recommendation, and taking into account that ALAC is empowered to initiate discussions leading to the creation of a PDP, ICANN org understands that ALAC advises the Board either to (1) initiate a PDP by calling for an Issue Report on this topic (ii) or cause ICANN org to enter into voluntary negotiations with Contracted Parties to implement ALAC’s advice.
69 | DNS abuse | ALAC Advice - DNS abuse Rec 7 | 10Oct20: As stated in the Board's response to DNS Abuse related recommendations from SSR2, the Board has asked ICANN Org's DNS Security Threat Mitigation Program and the DNS abuse Board Caucus group to consider all of the pending advice and recommendations and develop a strategic and holistic approach. This process is underway and not yet complete. 11Apr20: ICANN received confirmation of understanding 27Jan20: ICANN sent the following understanding to the ALAC for review. Understanding: ICANN org understands ALAC to advise the Board to direct ICANN org to compel Contracted Parties to adhere to industry-wide good behavior, for example, by increasing per domain transaction fees for registrars that continually demonstrate high abuse rates. With respect to implementation of this recommendation, ICANN org understands that ALAC advises the Board to cause ICANN org to enter into voluntary negotiations with Contracted Parties regarding (i) pricing and (ii) industry best practices. We interpret “abuse” in this context to refer, for the time being, to harmful activity insofar as it intersects with the DNS and involves the use of malware, botnets, phishing, pharming, and spam (when it serves as a delivery mechanism for the other forms of DNS abuse). We understand that the scope of this could expand once agreement has been reached (either through Consensus Policy development or through voluntary contract negotiations between ICANN and Contracted Parties) on the scope and characteristics of “abuse” within ICANN’s remit. ICANN received ALAC: DNS Abuse on 10 January 2020 and is currently reviewing. | R-7 | Compel industry-wide good behavior: for ex. by increasing per domain transaction fees for registrars that continually demonstrate high abuse rates. | Phase 3 ¦ Evaluate & Consider |  |  |  | ICANN org understands ALAC to advise the Board to direct ICANN org to compel Contracted Parties to adhere to industry-wide good behavior, for example, by increasing per domain transaction fees for registrars that continually demonstrate high abuse rates. With respect to implementation of this recommendation, ICANN org understands that ALAC advises the Board to cause ICANN org to enter into voluntary negotiations with Contracted Parties regarding (i) pricing and (ii) industry best practices. We interpret “abuse” in this context to refer, for the time being, to harmful activity insofar as it intersects with the DNS and involves the use of malware, botnets, phishing, pharming, and spam (when it serves as a delivery mechanism for the other forms of DNS abuse). We understand that the scope of this could expand once agreement has been reached (either through Consensus Policy development or through voluntary contract negotiations between ICANN and Contracted Parties) on the scope and characteristics of “abuse” within ICANN’s remit.
70 | DNS abuse | ALAC Advice - DNS abuse Rec 8 | 10Oct20: As stated in the Board's response to DNS Abuse related recommendations from SSR2, the Board has asked ICANN Org's DNS Security Threat Mitigation Program and the DNS abuse Board Caucus group to consider all of the pending advice and recommendations and develop a strategic and holistic approach. This process is underway and not yet complete. 10Oct20: As stated in the Board's response to DNS Abuse related recommendations from SSR2, the Board has asked ICANN Org's DNS Security Threat Mitigation Program and the DNS abuse Board Caucus group to consider all of the pending advice and recommendations and develop a strategic and holistic approach. This process is underway and not yet complete. 10Oct20: As stated in the Board's response to DNS Abuse related recommendations from SSR2, the Board has asked ICANN Org's DNS Security Threat Mitigation Program and the DNS abuse Board Caucus group to consider all of the pending advice and recommendations and develop a strategic and holistic approach. This process is underway and not yet complete. 10Oct20: As stated in the Board's response to DNS Abuse related recommendations from SSR2, the Board has asked ICANN Org's DNS Security Threat Mitigation Program and the DNS abuse Board Caucus group to consider all of the pending advice and recommendations and develop a strategic and holistic approach. This process is underway and not yet complete. 11Apr20: ICANN received confirmation of understanding 27Jan20: ICANN sent the following understanding to the ALAC for review. Understanding: ICANN org understands ALAC to advise the ICANN Board to direct ICANN org to enter into voluntary contract negotiations with Contracted Parties to implement the above advise, and to include clear enforcement language to facilitates ICANN Contractual Compliance to enforce. ICANN org further understands ALAC to advise the ICANN Board to direct ICANN org to ensure that ICANN Contractual Compliance has the tools it will need to enforce the output of any relevant Consensus Policy and/or voluntary contract negotiations. ICANN received ALAC: DNS Abuse on 10 January 2020 and is currently reviewing. | R-8 | Implement the above in agreements/contracts, with clear enforcement language for ICANN Contractual Compliance to adopt.5 Convene a discussion between the Contracted Parties and ICANN Compliance to finally resolve what additional tools might be needed by Compliance. | Phase 3 ¦ Evaluate & Consider |  |  |  | ICANN org understands ALAC to advise the ICANN Board to direct ICANN org to enter into voluntary contract negotiations with Contracted Parties to implement the above advise, and to include clear enforcement language to facilitates ICANN Contractual Compliance to enforce. ICANN org further understands ALAC to advise the ICANN Board to direct ICANN org to ensure that ICANN Contractual Compliance has the tools it will need to enforce the output of any relevant Consensus Policy and/or voluntary contract negotiations.
Note on G4: Is "approved" implemented?
Note on G6: In Column F, which category do we approve? (Referred to another group)- do we keep ?
Note on C24: Jonathan, how do you wish to handle the "in progress"? Do you want to leave them in case they must be completed before a New Round Opens?

## Data Validation List
Y | None | Y | GNSO Council
N | IRT / Applicant Guidebook | N | IRT
P | Opening of applications | ? | ICANN Board
| Delegation |  | Any other group