Desired Outcome

- General understanding of scope, interdependencies, dependencies and resource needs for phase 2

- Develop and agree on general approach and timeline for phase 2

Day 1—Saturday 9 March 2019

| Timing | Topic |
| --- | --- |
| 10.45 – 11.00 | Arrival at the Meeting Room |
| 11.00 – 11.30 | Welcome / Introductions - Update on Council deliberations on phase 1 and instructions in relation to phase 2 - Outline of Agenda and Objectives for the week |
| 11.30 – 12.15 | Tour de Table – commitments, objectives and expectations for phase 2 - A representative of each group will share the group’s commitments, objectives and expectations for phase 2 |
| 12.15 – 13.30 | Lunch Break |
| 13.30 – 14.15 | Overview of topics included in phase 2 1) System for Standardized Access to Non-Public Registration Data, 2) Annex - Important Issues for Community Consideration a 3) Issues deferred from EPDP Phase I |
| 14.15 – 15.30 | Brainstorming exercise - Identify a rapporteur for each whiteboard (staff, chairs?) - Ask everyone to go around the room and write down their thoughts on the different questions. Questions would include: - Working methods: what time are you willing/able to commit to this effort on a weekly basis? Should there be any chance to the working methods that have been used in phase 1? What would be a realistic timeline for the EPDP Team to deliver its Initial Report for phase 1? - What are the dependencies for each of the topics in phase 2? Who is responsible for these dependencies? - How/when should legal memos be reviewed? - What resources are needed for the EPDP Team to deliver on phase 1 in a reasonable timeframe? Think about internal / external expertise, F2F time, mediation, etc. - Rapporteur to report back on main themes / common view points |
| 15.30 – 16.30 | Plenary Session - Aim to reach preliminary agreement on possible approach, timing, resources and dependencies for each strand of work - Aim to reach preliminary agreement on the working methods for phase 2 (# of meetings, duration, etc.) - Aim to reach preliminary agreement on a possible target date for delivery of the Initial Report, assuming alignment with Council expectations as well as resources identified. |
| 16.30 – 17.00 | Implementation Status Update (GDD) |
| 17.00 – 18.30 | Social Gathering |

Day 2—Sunday 10 March 2019

| Timing | Topic |
| --- | --- |
| 17.00 – 18.30 | Engagement Session with the Technical Study Group on Access to Non-Public Registration Data - Opportunity to learn more about the scope, status and next steps of the TSG and how it intersects with the EPDP Team’s phase 2 deliberations |

Day 3—Wednesday 13 March 2019

| Timing | Topic |
| --- | --- |
| 10.30 – 12.00 | Phase 1 implementation brainstorming session |

Day 4—Thursday 14 March 2019

| Timing | Topic |
| --- | --- |
| 8.30 – 10.15 | Wrap up session - Review of draft work plan and approach coming out of Saturday’s session - Consider further input that may have been gathered throughout the week, including Council input from weekend sessions as well as engagement session with TSG - Confirm next steps and next meeting |