## Slide 1: CSC Effectiveness Review
CSC Effectiveness Review Team
March 2019
ICANN64

## Slide 2: Need for Review of Effectiveness Review
“Effectiveness of the CSC shall be reviewed two years after the first meeting of the CSC; and then every three years thereafter” (Bylaws)
The method of review is determined by the ccNSO and GNSO
CSC established as one of the post IANA Stewardship Transition entities
  conducted its first meeting on 6 October 2016
CSC charter revised in June 2018
  Concurrence with the soon-to-be IANA Naming Function Review

## Slide 3: Method of Effectiveness Review
Avoid potential overlap between CSC Effectiveness review and IANA Naming Function Review (IFR)
  Scope IFR review the performance of PTI in performing the IANA Naming Function, which includes among others oversight role of CSC
Review is to quick and fact-based that allows short duration
  Building on results of CSC Charter Review
The method of Effectiveness review to be determined by the ccNSO and GNSO:
  ccNSO and GNSO Councils adopted Template for review September 2018.
  Two members each to conduct CSC Effectiveness Review
  Liaisons from CSC, Expert observers PTI and ICANN Org
Findings of the Review to be adopted by both the GNSO and ccNSO Councils input to the IFR
  Aligns with Board resolution on IFR

## Slide 4: Scope of Review: limited
Consider the Effectiveness of the CSC in carrying out its mission as defined in its charter.
  The recent CSC Charter Review concluded that the CSC is both working well and is non-controversial
Method of assessing effectiveness
  Review Team developed and will use relevant performance indicators and related measures of effectiveness in carrying its tasks as listed in charter.
  Draw on the recently concluded CSC Charter Review
  Awareness of work of CSC by Registries and broader communities

## Slide 5: Measures
Metric | Assessment (see Report) | Outcome
CSC monitors the performance of the IANA Naming Function against SLAS |  | Achieved
CSC analyses monthly reports provided by PTI and publishes their findings on monthly basis |  | Achieved
CSC follows up IF any performance issues identified |  | Achieved
Where appropriate, the CSC to request a review or change of SLA |  | Achieved

## Slide 6: Measures (contd.)
Metric | Assessment (See Report) | Outcome
Where appropriate the CSC undertakes remedial action to address poor performance in accordance with the Remedial Action Procedures |  | Not Applicable
When remedial action by CSC has not resolved the poor performance, CSC is authorised to escalate issues to the ccNSO and GNSO for consideration |  | Not Applicable
CSC has an effective procedure to track complaints |  | Partially Achieved

## Slide 7: Measures (contd.)
Metric | Assessment (see Report) | Outcome
CSC will consult annually with PTI & ICANN, primary customers, the ICANN community about the performance of PTI |  | Achieved
CSC, in consultation with the registries, may discuss with PTI & ICANN ways to enhance the provision of IANA’s operational services |  | Achieved
Where ICANN and PTI have been responsible for implementing changes, CSC confident of appropriately |  | Achieved
CSC is providing a liaison to IFRT |  | Achieved

## Slide 8: Measures (contd.)
Metric | Assessment (see Report) | Outcome
CSC is providing a liaison to: the SFRT |  | Not Applicable
Meeting Attendance of CSC Members |  | Achieved
Meeting Attendance of CSC Members |  | Not Achieved

## Slide 9
major finding
CSC is operating effective
concern
How to ensure cohesion of the CSC and quality of membership in future?

## Slide 10: Recommendations
To ensure cohesion of the CSC and quality of membership:
  CSC to develop induction programme for new members & liaisons
  CSC to develop mapping of skills & experience and
  Appointing organisations should take mapping into account in their selection
CSC to provide attendance records regularly (at least in May every year) to appointing organisations
CSC to document how it deals with complaint individual PTI customer
  CSC role is very limited: it does not get involved in the individual complaint and this should be clearly stated.

## Slide 11: Review Process
Adoption and establishing CSC Effectiveness Review (September 2018)
Interviews with the CSC and the PTI to determine whether the CSC is fit for purpose and effective
Public session at ICANN 63
Public consultation Initial Report (16 January 2019-25 February 2019)
Submission Final Report to ccNSO & GNSO Councils (1 March 2019)
  If Report adopted, to be recommended to the IANA Naming Function Review Team for their consideration