Review Team Milestones schedule

| Schedule Date | Milestone | Date of Completion | Comments |
| --- | --- | --- | --- |
| September 2018 | Adoption Template for Review | Completed 12 September 2018 | Propose terms of template for review to ccNSO and GNSO Councils to seek support and determine the method of the CSC Effectiveness Review and appoint the Review Team |
| September-October 2018 | Preparatory consultation with CSC and PTI | Completed | - Informal consultations September 2018 |
| October 2018 | Consultation and review | Completed 26 October | - 1 October 2018 kick-off review - Public Consultation (open session) including interview CSC and PTI at ICANN63 - Consultation with direct customers (ccTLD, gTLD operators, others) at ICANN63 |
| November- 14 December 2018 | Report on findings & recommendations, if any |  | Preparation draft report, including recommendations, if any, by 14 December 2018 + public comment announcement. |
| 18 December 2018- 15 February 2019 | Public comment & Staff report |  | Need for Public comment period, at least 40 days. Includes additional week of 1 week seasonal holidays + staff report comments (5 days) finalization of report post public comment. Question: Seek separate input from CSC, PTI and ICANN Org on draft report? |
| 11- 22 February | Finalization Final Report |  | RT to finalize report based on public comment. Question: Seek separate input from CSC, PTI and ICANN Org on final report? |
| 25 February |  |  | - Publication and submission Final Report to ccNSO and GNSO Councils for adoption according to their own rules and procedures - Following the adoption of the report by the ccNSO and GNSO Councils, the review team mandate ends. - Submission adopted Final Report to IFRT (jointly by ccNSO and GNSO Councils) |