| Change Area Requested | 1st Reading | 2nd Reading | Outcome | Comments |
| --- | --- | --- | --- | --- |
| Community Mechanism Escalation Process (Recommendation #2) and Board Removal (Recommendation #4): The CWG-Stewardship recognizes that the escalation processes need to happen in a timely manner but they must also allow sufficient time to accommodate the diverse and complex makeup of SOs and ACs. | 7 January – Escalation Timeframes 5 January –Board Removal | 14 January – Escalation timeframes 12 January & 19 January –Board Removal | ✔On escalation: removed the Conference Call stage and extended timeframes for SO/AC decision (21 day cycles with the longest possible time totaling 70 days). ✔On Board Removal: Added requirements for dialogue and for a written rationale for Director removal. The CCWG concluded and instructed legal counsels to develop language for pre-service letters. |  |
| Budget (Recommendation #4): […] however, we require that the CCWG-Accountability proposal or the implementation process address the matters that are not sufficiently specified in the Third Draft Proposal (i.e., those relating to budget transparency, grounds for rejection of a budget/plan, timing of budget preparation and development of the caretaker budget, each of which were described in the Second Draft Proposal). In addition, we note, that the CWG-Stewardship (or a successor implementation group) is required to develop a proposed process for the IANA Functions Operations-specific budget review. We require that the proposal specifically acknowledge this. | 7 January | 14 January | ✔Following comments from CWG-Stewardship, the budget document received additional edits. The latest document is available here, but there are still some items that need to be cleaned up before considered final. |  |
| Separation Process (Recommendation #4): The community’s ability to reject ICANN Board decisions on Special IFR/SCWG recommendations, which would include the selection of a new IANA Functions Operator or any other separation process will meet the CWG-Stewardship requirements, provided that (i) the final version of the CCWG-Accountability proposal provide that the right to reject can be exercised an unlimited number of times | 14 January | 21 January | ✔On Separation Process, no comments in first reading, so changes expected for second reading. Below is an overview of the separation process proposal for the first reading (see page 24): - Clarification that separation process applies only to domain name function of IANA. - Unlimited right to reject Board decisions relating to reviews of IANA Functions |  |
| IRP (Recommendation #7): As we noted in our comment letter to the Second Draft Proposal, the Third Draft Proposal does not explicitly address the CWG-Stewardship requirement that an independent review process be available for claims relating to actions or inactions of PTI. | 12 January | 19 January | ✔Agreement to move forward with a combination of solutions to address the IRP scope issue with PTI: include general provision regarding ICANN’s obligation to cause the PTI to fulfill its obligations (the failure to do so would give rise to a standard IRP) and text to address SLA failures, etc. with an operational (rather than constitutional) standard of review. |  |