CWG – Forward Plan to ICANN 53

| Meeting Schedule | Agenda | Deliverables | Draft Proposal |
| --- | --- | --- | --- |
| 19 May Meeting | Proposed Agenda for 19/05 1. Opening Remarks 2. Public comment a. FAQ update b. Translations c. Update on comments received 3. Design Team Updates a. DT-F b. DT-SR / DT-N c. Other? 5. Punch List Review 6. Forward planning 7. AOB a. No call on Thursday 8. Closing Remarks | - Finalize list of open items and dedicate meeting time to each item | - Out for public comment |
| CCWG-ACCT 19 May Meeting |  |  |  |
| Close of Public Comment on 20 May |  |  |  |
| 26 May Meeting | Proposed Agenda for 26/05 - Opening Remarks - Initial review of Public Comment - Response to ICG on CWG Timeline - Review of Section IV draft - AOB - Closing Remarks | - Review and analyze the public comment period; Incorporate feedback from submissions received - Response to ICG (regarding NTIA letter for timeline adjustments) | - Section IV draft |
| CCWG-ACCT 26 May Meeting |  |  |  |
| 28-29 May Intensive Meetings | - Review and analyze the public comment period; Incorporate feedback from submissions received - Review sections IV, V, VI of the proposal |  |  |
| 28 May Call #1 | - Comments received on (thematic section 1) - PTI Board composition and parameters (as a Public Benefit Corporation with an internal Board) | - Finalize CWG-Stewardship position on PTI Board |  |
| 28 May Call #2 | - Comments received on (thematic section 2) - Section IV | - Finalize Section IV |  |
| 28 May Call #3 |  | - (none) |  |
| 29 May Call #4 | - Comments received on (thematic section 3) - Section V | - Finalize Section V |  |
| 29 May Call #5 | - Comments received on (thematic section 4) - Section VI | - (none) |  |
| 29 May Call #6 |  | - Finalize Section VI |  |
| 2 June Meeting | Proposed Agenda for 02/06 - Opening Remarks - Sign-off on final proposal - AOB - Closing Remarks | - Obtain CWG-Stewardship sign off for the Proposal (1st reading) | - FINALIZE, including: - Section IV - Section V - Section VI |
| CCWG-ACCT 2 June Meeting |  |  |  |
| CCWG-ACCT Close of Public Comment on 3 June |  |  |  |
| 4 June Meeting | Proposed Agenda for 04/06 - Opening Remarks - Sign-off on CWG Final Report/Proposal - AOB - Closing Remarks | - Final Proposal | - FINAL |
| Submit Proposal to SO/ACs (8 June) | - Proposal needs to have sign-off and support from each of the Chartering Organizations - Submit to other SO/ACs as a courtesy (RSSAC and ASO) but be clear that they are not Chartering Organizations |  |  |
| 9 June Meeting | Proposed Agenda for 09/06 - Opening Remarks - Prepare Materials for Webinar(s) - Prepare Materials for ICANN 53 - AOB - Closing Remarks | - Webinar materials - Provide any additional support to SO/ACs where needed | - Final |
| CCWG-ACCT 9 June Meeting |  |  |  |
| 10 June Webinar | Briefing on Final Proposal | - Support for final proposal | - Final |
| 11 June Meeting | Proposed Agenda for 11/06 - Opening Remarks - Update on Chartering Organization discussions and outreach - Prepare Materials for ICANN 53 - AOB - Closing Remarks | - Provide any additional support to SO/ACs where needed - Ensure (to the extent possible) community-wide consensus on the Final Proposal | - Final |
| 16 June Meeting | Proposed Agenda for 16/06 - Opening Remarks - Prepare Materials for ICANN 53 - AOB - Closing Remarks | - Agree on materials and schedule/plan for ICANN53 | - Final |
| CCWG-ACCT 16 June Meeting |  |  |  |
| 18 June Meeting | Proposed Agenda for 18/06 - Opening Remarks - Prepare Materials for ICANN 53 - AOB - Closing Remarks | - (none) | - Final |
| ICANN 53 (21-25 June) | ICANN53 will focus on the Transition, and there will be many sessions. Below are the two CWG-Stewardship slots: - Engagement session on Monday afternoon - Working session on Thursday morning | - Gather community support for the proposal | - Final |
| ICANN 53 (21-25 June) CCWG-ACCT | - Meeting on Friday before meeting - ‘Town Hall’ on Monday morning - Engagement session on Wednesday afternoon - Working session on Thursday morning | - Compile feedback on 1st draft | - Preparing draft for 2nd PC |
| Submit Proposal to ICG (25 June) |  |  |  |