## Sheet1
Action Item Title | Action Item Description | Action due before proposal sent to NTIA | Action due during implementation before Contract expiry | Group/org responsible for implementing action item | Group/org responsible for OVERSIGHT of item | Dependencies for this item to be successfully completed
NUMBERS Proposal
A1: Contract/SLA between RIRs and ICANN | Section P2.III.A.3: Service Level Agreement with the IANA Numbering Services Operator of the combined proposal, develop and finalise SLA to be exchanged between RIRs and ICANN, to be signed by both parties. |  | i. First draft (done) ii. Second draft (done) iii. Negotiations (started) iv. Final version - ETA tbd v. Signature - ICANN and the five RIRs - ETA tbd | RIRs are responsible for implementation. | The CRISP Team is responsible for ensuring implementation is consistent with the number community proposal.
A2: Review Committee for IANA Numbers Functions | Section P2.III.A.4: Establishment and set up of the Review Committee, and complete appointment of its members. |  | i. NRO to finalise charter (done) ii. Each RIR to finalise detailed appointment methods iii. Each RIR to appoint members | RIRs are responsible for implementation. | The CRISP Team is responsible for ensuring implementation is consistent with the number community proposal.
A3: IPR | Section P2.III.A.2: IPR related to the provision of the IANA services remains with the community, identify the holder of IPR and exchange appropriate agreements by the parties involved. |  | i. All OCs to agree on the principles for the holder of IPR ii. All OCs to agree on IPR holder iii. New organisation to be set up, or changes made to how IETF Trust works (if necessary) iv. Agreements between OCs and IPR holder v. Agreement between IPR holder and IANA functions operator | RIRs are responsible for preparing implementation for all Numbers related items. If IETF Trust is to house IPR, the IETF Trust Trustees will have responsibilities for getting OC agreements on policies, etc. | The CRISP Team is responsible for ensuring implementation is consistent with the number community proposal. | IPR resolution/implementation requires coordination across all three Operating Communities.
A4: NTIA Criteria - on-going support | Further considerations to support continuation to uphold the NTIA criteria in the future (Q.10 from the ICG) | Consider if additional actions needed |  | Each RIR to consider. | The CRISP Team is responsible for ensuring implementation is consistent with expectations.
A5: PTI | Ensure PTI is implemented as expected | Ensure PTI will be consistent with what the number community has agreed with the Names OC | Ensure PTI is consistent with what the number community has agreed with the Names OC | The CRISP Team is responsible for ensuring implementation is consistent with the Number Community proposal. | The CRISP Team is responsible for ensuring implementation is consistent with the Number Community proposal.
PROTOCOL PARAMETERS
A6: SLA | Annual SLA - updated |  | The updated SLA has been agreed by the IAB/IETF and ICANN. Awaiting signing . | IAOC | IAB
A7: PTI | Ensure PTI is implemented as expected | Ensure PTI will be consistent with what the Protocol Parameter community has agreed with the Names OC. IETF/IAB allows sub-contracting to PTI. | Ensure PTI is consistent with what the number community has agreed with the Names OC | IAB | The IAB is responsible for ensuring implementation is consistent with the Protocol Parameter Community proposal.
A8: IPR | IPR related to the provision of the IANA services remains with the community, identify the holder of IPR and exchange appropriate agreements by the parties involved. |  | "i. All OCs to agree on the principles for the holder of IPR ii. All OCs to agree on IPR holder iii. New organisation to be set up, or changes made to how IETF Trust works (if necessary) iv. Agreements between OCs and IPR holder v. Agreement between IPR holder and IANA functions operator" | IAB If IETF Trust is to house IPR, the IETF Trust Trustees will have responsibility for getting OC agreements on policies, etc. | IAB | IPR resolution/implementation requires coordination across all three Operating Communities.