Version 1 – NTIA Based Calendar Timeline

Version 2 – Monthly Based Timeline

Task List:

- Form Contract Co. (CC)

  - Draft CC bylaws

  - Draft Contract between Contract Co. and ICANN

  - Incorporate not-for-profit

  - Staff with personnel

- Form Multistakeholder Periodic Review Team (MRT)

  - Define processes and inter-operability to CC, CSC, IAP.

  - Elect members

- Form Customer Standing Committee (CSC)

  - Define process and inter-operability to MRT

  - Create escalation procedures for CSC

  - Elect members

- Form Independent Review Panel (IAP)

  - Define processes and inter-operability to MRT & CC

  - Establish binding arbitration process

  - Contract independent arbitration organization

- Draft changes to ICANN Bylaws/AoC where necessary

- Public Comment Period

- Implement IANA automation of transactions other than reassignment/re-delegation

- Finalize all documentation post public comment and complete leftover tasks of organization(s) setup

- Conduct IANA Security review and stress test

- Implement Track1 CCWG-Accountability

- Sign Contract

- Conduct formal transition from NTIA to groups