## Slide 1
CWG – NTIA Stewardship of IANA Transition
Project Timeline
22 22 October 2014

## Slide 2
Key Milestones
27 Nov 2014 | Complete CWG deliberations to develop Draft Transition Proposal
01 Dec 2014 | Publish Draft Transition Proposal for public comment and submit to chartering organizations for consideration
08 Dec 2014 | Complete webinar outreach
22 Dec 2014 | Close of Public Comment Forum on Draft Transition Proposal / Summary of report of Public Comments
19 Jan 2015 | Finalize Transition Proposal and submit to Chartering Organizations
30 Jan 2015 | Adoption by chartering organizations of final transition proposal
31 Jan 2015 | Submission of Final Transition Proposal to ICG

## Slide 3
CWG Stewardship Timeline 2014-2015
2014
2015
Dec
Oct
Feb
Sep
Nov
Jan
Charter Adopted
CWG Deliberations Conclude
Publish Draft Proposal
  Public Comment Closes (21)
  Proposal OK by Charter Orgs
  Submit Final Proposal to ICG
Publish Final
Proposal
  Webinars