| Sunday |  | Monday |  | Tuesday |  | Wednesday | Thursday |  | Friday |  | Saturday |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 1 | 2 |  | 3 |  | 4 |  |
| APRIL 2015 |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  |
|  |  |  |  | CWG IANA 17:00 UTC |  |  |  |  | DEADLINE for DTs to provide content |  |  |  |
| 12 |  | 13 |  | 14 |  | 15 | 16 |  | 17 |  | 18 |  |
|  |  | Intensive working days – Preparing final proposal |  | Intensive working days – Preparing final proposal |  |  |  |  | CWG IANA 11:00 UTC |  |  |  |
| 19 |  | 20 |  | 21 |  | 22 | 23 |  | 24 |  | 25 |  |
|  |  | Start of Public Comment for 30 days |  | CWG IANA 17:00 UTC |  | Tentative: Webinar | CWG IANA 11:00 UTC Tentative: Webinar |  |  |  |  |  |
| 26 |  | 27 |  | 28 |  | 29 | 30 |  |  |  |  |  |
|  |  |  |  | CWG IANA 17:00 UTC |  |  | CWG IANA 11:00 UTC |  |  |  |  |  |
| Sunday | Monday |  | Tuesday |  | Wednesday |  |  | Thursday |  | Friday |  | Saturday |  |
|  |  |  |  |  |  |  |  |  |  | 1 |  | 2 |  |
| MAY 2015 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | 4 |  | 5 |  | 6 |  |  | 7 |  | 8 |  | 9 |  |
|  |  |  | CWG IANA 17:00 UTC |  |  |  |  | CWG IANA 11:00 UTC |  |  |  |  |  |
| 10 | 11 |  | 12 |  | 13 |  |  | 14 |  | 15 |  | 16 |  |
|  |  |  | CWG IANA 17:00 UTC |  |  |  |  | CWG IANA 11:00 UTC |  |  |  |  |  |
| 17 | 18 |  | 19 |  | 20 |  |  | 21 |  | 22 |  | 23 |  |
|  |  |  | CWG IANA 17:00 UTC |  | Close of Public Comment |  |  | CWG IANA 11:00 UTC |  |  |  |  |  |
| 24 | 25 |  | 26 |  | 27 |  |  | 28 |  | 29 |  | 30 |  |
| 31 Intensive Weekend Weekend |  |  | CWG IANA 17:00 UTC |  |  |  |  | CWG IANA 11:00 UTC |  |  |  | Intensive Weekend 30-31 May |  |

| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 |
| JUNE 2015 |  | CWG IANA 17:00 UTC |  | CWG IANA 11:00 UTC |  |  |
| 7 | 8 | 9 | 10 | 11 | 12 | 13 |
|  | Deliver Names Proposal to SOs/ACs | CWG IANA 17:00 UTC |  | CWG IANA 11:00 UTC |  |  |
| 14 | 15 | 16 | 17 | 18 | 19 | 20 |
|  |  | CWG IANA 17:00 UTC |  | CWG IANA 11:00 UTC |  |  |
| 21 | 22 | 23 | 24 | 25 | 26 | 27 |
| ICANN 53 Buenos Aires | ICANN 53 Buenos Aires | ICANN 53 Buenos Aires | ICANN 53 Buenos Aires | ICANN 53 Buenos Aires Deliver Names Proposal to ICG |  |  |
| 28 | 29 | 30 |  |  |  |  |