## Sheet1
Action Item Title | Action Item Description | Action due before proposal sent to NTIA | Action due during implementation before Contract expiry | Group/org responsible for implementing action item | Group/org responsible for OVERSIGHT of item | Dependencies for this item to be successfully completed
NUMBERS Proposal
A1: Contract/SLA between RIRs and ICANN | Section P2.III.A.3: Service Level Agreement with the IANA Numbering Services Operator of the combined proposal, develop and finalise SLA to be exchanged between RIRs and ICANN, to be signed by both parties. |  | i. First draft (done) ii. Second draft (done) iii. Negotiations (started) iv. Final version - ETA tbd v. Signature - ICANN and the five RIRs - ETA tbd | RIRs are responsible for implementation. | The CRISP Team is responsible for ensuring implementation is consistent with the number community proposal.
A2: Review Committee for IANA Numbers Functions | Section P2.III.A.4: Establishment and set up of the Review Committee, and complete appointment of its members. |  | i. NRO to finalise charter (done) ii. Each RIR to finalise detailed appointment methods iii. Each RIR to appoint members | RIRs are responsible for implementation. | The CRISP Team is responsible for ensuring implementation is consistent with the number community proposal.
A3: IPR | Section P2.III.A.2: IPR related to the provision of the IANA services remains with the community, identify the holder of IPR and exchange appropriate agreements by the parties involved. |  | i. All OCs to agree on the principles for the holder of IPR ii. All OCs to agree on IPR holder iii. New organisation to be set up, or changes made to how IETF Trust works (if necessary) iv. Agreements between OCs and IPR holder v. Agreement between IPR holder and IANA functions operator | RIRs are responsible for preparing implementation for all Numbers related items. If IETF Trust is to house IPR, the IETF Trust Trustees will have responsibilities for getting OC agreements on policies, etc. | The CRISP Team is responsible for ensuring implementation is consistent with the number community proposal. | IPR resolution/implementation requires coordination across all three Operating Communities.
A4: NTIA Criteria - on-going support | Further considerations to support continuation to uphold the NTIA criteria in the future (Q.10 from the ICG) | Consider if additional actions needed |  | Each RIR to consider. | The CRISP Team is responsible for ensuring implementation is consistent with expectations.
A5: PTI | Ensure PTI is implemented as expected | Ensure PTI will be consistent with what the number community has agreed with the Names OC | Ensure PTI is consistent with what the number community has agreed with the Names OC | The CRISP Team is responsible for ensuring implementation is consistent with the Number Community proposal. | The CRISP Team is responsible for ensuring implementation is consistent with the Number Community proposal.
PROTOCOL PARAMETERS
A6: SLA | Annual SLA - updated |  | The updated SLA has been agreed by the IAB/IETF and ICANN. Awaiting signing . | IAOC | IAB
A7: PTI | Ensure PTI is implemented as expected | Ensure PTI will be consistent with what the Protocol Parameter community has agreed with the Names OC. IETF/IAB allows sub-contracting to PTI. | Ensure PTI is consistent with what the number community has agreed with the Names OC | IAB | The IAB is responsible for ensuring implementation is consistent with the Protocol Parameter Community proposal.
A8: IPR | IPR related to the provision of the IANA services remains with the community, identify the holder of IPR and exchange appropriate agreements by the parties involved. |  | "i. All OCs to agree on the principles for the holder of IPR ii. All OCs to agree on IPR holder iii. New organisation to be set up, or changes made to how IETF Trust works (if necessary) iv. Agreements between OCs and IPR holder v. Agreement between IPR holder and IANA functions operator" | IAB If IETF Trust is to house IPR, the IETF Trust Trustees will have responsibility for getting OC agreements on policies, etc. | IAB | IPR resolution/implementation requires coordination across all three Operating Communities.
NAMES
A9: Resolution of the IANA IPR location and organisation |  | No action prior to delivery to NTIA |  | CWG-Stewardship | ICG? | Collaboration of the CWG, IETF & NRO
A10: Formation of PTI (including PTI Board of Directors) | CWG-Stewardship Proposal Reference: III.A, ¶ 97; III.A.i, ¶107-114 | No action prior to delivery to NTIA |  | CWG-Stewardship & ICANN | ICG? | Approval by ICANN Board & NTIA
A11: Transfer of staff & resources to PTI | CWG-Stewardship Proposal Reference: III.A, ¶ 97 | No action prior to delivery to NTIA |  | ICANN | CWG-Stewardship and/or ICG? | #2: Formation of PTI #4: Development of ICANN/PTI Contract #5: Execution of ICANN/PTI Contract #8: Development of PTI Operating Plan & Budget #9: Approval of PTI Operating Plan & Budget #10: Establishment of the CSC
A12: Development of ICANN/PTI Contract | CWG-Stewardship Proposal Reference: III.A, ¶ 97; III.A.i, ¶115-116; IV.B, ¶181; Annex E; Annex S | No action prior to delivery to NTIA |  | ICANN | CWG-Stewardship and/or ICG? | #2: Formation of PTI #15: Finalization & implementation of SLEs
A13: Execution of ICANN/PTI Contract | CWG-Stewardship Proposal Reference: III.A, ¶ 97 | No action prior to delivery to NTIA |  | ICANN & PTI | CWG-Stewardship and/or ICG? | #4: Development of ICANN/PTI Contract
A14: Change in Root Zone Maintainer relationship to remove NTIA role | CWG-Stewardship Proposal Reference: III.A, ¶ 97 | No action prior to delivery to NTIA |  | NTIA, ICANN & Verisign | NTIA & CWG-Stewardship and/or ICG?
A15: Revision of Root Zone file change process | CWG-Stewardship Proposal Reference: III.A.i, ¶ 104; III.A.iii, ¶147-157; ¶158 2); ¶158 3); IV.A, ¶169-178 | No action prior to delivery to NTIA |  | NTIA, ICANN & Verisign | NTIA & CWG-Stewardship and/or ICG? | #6: Change in Root Zone Maintainer relationship to remove NTIA role
A16: Setup of Standing Committee | CWG-Stewardship Proposal Reference: III.A.iii, ¶155 | No action prior to delivery to NTIA |  | ICANN | Community? | Approval by NTIA
A17: Development of PTI Operating Plan & Budget | CWG-Stewardship Proposal Reference: III.A.i, ¶ 104; III.A.iii, ¶161-163; Appendices P & Q | No action prior to delivery to NTIA |  | ICANN & PTI | Community
A18: Approval of PTI Operating Plan & Budget | CWG-Stewardship Proposal Reference: III.A.i, ¶ 104 | No action prior to delivery to NTIA |  | TBD | CWG-Stewardship and/or ICG? | Final CCWG-Accountability recommendations
A19: Establishment of the CSC | CWG-Stewardship Proposal Reference: III.A.i, ¶ 105; III.A.ii, ¶128-132; Annex G | No action prior to delivery to NTIA |  | CWG-Stewardship | ICG? | Approval by NTIA
A20: Establishment of issue resolution mechanisms to ensure that problems are resolved effectively | CWG-Stewardship Proposal Reference: III.A.i, ¶ 105 | No action prior to delivery to NTIA |  | CWG-Stewardship | ICG? | #10: Establishment of the CSC
A21: Establishment of a multistakeholder IANA Function Review (IFR) | CWG-Stewardship Proposal Reference: III.A.i, ¶ 105; III.A.i, ¶117-127 | No action prior to delivery to NTIA | Also needed 2 years after transition | CWG-Stewardship | ICG?
A22: Confirmation that the CWG-Stewardship dependencies on the CCWG-Accountability are met | CWG-Stewardship Proposal Reference: III.A.i, ¶ 106 | Confirm that the CWG-Stewardship dependencies on the CCWG-Accountability are met |  | CWG-Stewardship | ICG? | Final CCWG-Accountability recommendations
A23: Development of a work plan for testing & implementing SLEs | CWG-Stewardship Proposal Reference: III.A.ii, ¶133-138; Annex H | No action prior to delivery to NTIA |  | ICANN | CWG-Stewardship | Availability & approval of resources
A24: Finalization & implementation of SLEs | CWG-Stewardship Proposal Reference: III.A.ii, ¶133-138; Annex H | No action prior to delivery to NTIA |  | CWG-Stewardship & ICANN | ICG? | #14: Development of work plan for testing & implementing SLEs Approval of work plan and resources by ICANN
A25: Definition of an IANA Separation Process | CWG-Stewardship Proposal Reference: III.A.ii, ¶142-143; Annex L | No action prior to delivery to NTIA |  | CWG-Stewardship | ICG?
A26: Modification of the IANA function transition framework as needed | CWG-Stewardship Proposal Reference: III.A.ii, ¶146-146; Annex M | No action prior to delivery to NTIA |  | CWG-Stewardship & ICANN | ICG?
A27: Determination of whether any statutory waivers are needed from the USG and, if so, obtain them | CWG-Stewardship Proposal Reference: II.A.iv, ¶164-165 | No action prior to delivery to NTIA |  | CWG-Stewardship, ICANN, NTIA | ICG? | Assistance from NTIA
A28: Draft of changes to the ICANN Bylaws | See Sidley documents (to be provided) | No action prior to delivery to NTIA |  | CWG-Stewardship, ICANN, Sidley | ICG?
A29: Approval of changes to the Bylaws |  | No action prior to delivery to NTIA |  | ICANN Board | Community | #19: Drafting of changes to the Bylaws