Draft Work Plan – new gTLD Auction Proceeds Drafting Team – 28 March 2016

| Action | Target Date | Whom | Status / Notes |
| --- | --- | --- | --- |
| Develop a set of key milestones for DT | 31 March 2016 | DT Leadership & Staff | First draft produced |
| Review public comments and identify items which should be considered in relation to the development of the Charter | 31 March 2016 | Erika Mann, Russ Mundy | Template provided to Erika and Russ on 21 March |
| Provide briefing note on legal and fiduciary constraints (i.e. applicant guidebook, applicable law etc.) that would need to be taken into account by the DT and subsequent CCWG. | 31 March 2016 | Samantha Eisner |  |
| Identify key questions for different sections of the charter and circulate these to the mailing list to stimulate discussion and input | 31 March 2016 | Staff |  |
| DT Meeting #3 – draft agenda: - Discuss review of public comments - Review briefing note on legal and fiduciary restraints - Assign sections of charter to volunteers to develop draft language and/or identify further key questions | 31 March 2016 | All |  |
| DT Meeting #4 – draft agenda: - Discuss and review input on key questions for different sections of the charter - Discuss and review draft language for different sections of the charter | 14 April 2016 | All |  |
| DT Meeting #5 – draft agenda: - Continue discussion and review of input on key questions for different sections of the charter - Continue discussion and review draft language for different sections of the charter | 28 April 2016 | All |  |
| DT Meeting #5 – draft agenda: - Continue discussion and review of input on key questions for different sections of the charter - Continue discussion and review draft language for different sections of the charter | 12 May 2016 | All |  |
| DT Meeting #6 – draft agenda: - Finalize discussion and review of input on key questions for different sections of the charter - Finalize discussion and review of draft language for different sections of the charter | 26 May 2016 | All |  |
| DT Meeting #7 – draft agenda: - Sign off on draft CCWG Charter for submission to ICANN SO/ACs - Agree on specific questions or issues that will require input from ICANN SO/ACs, if any | 9 June 2016 | All |  |
| ICANN Meeting #56 – ICANN SO/ACs to review and discuss draft CCWG charter and provide feedback to DT | 27-30 June 2016 | ICANN SO/ACs |  |
| DT Meeting #8 – draft agenda: - Review feedback from ICANN SO/ACs and agree on next steps (i.e. additional meetings to address comments / input and/or finalization of CCWG charter for consideration by ICANN SO/ACs) | 14 July 2016 | All |  |
| Consideration of CCWG Charter for adoption by ICANN SO/ACs | TBC (at the latest by ICANN57) |  |  |