## Slide 1: Board Readiness
For Council Meeting
11 Jun 2025

## Slide 2: Team Members
Jennifer Chung
Justine Chew
Prudence Malinki
Susan Payne
Kurt Pritz
Thomas Rickert

## Slide 3: Mission / Scope
Perform a study that will inform the improvement or creation of policy development practices that will improve the Board readiness of GNSO policy recommendations,
Board readiness is measured by the likelihood that GNSO policy recommendations will be readily adopted by the ICANN Board.
where

## Slide 4
Compile & organise set of rejected recommendations
Develop sets of questions for Board
Develop sets of questions for staff
Develop sets of questions for PDP participants
Develop sets of questions for PDP chairs
Identify causal relationships bet. gaps & rejections
Identify possible improvements
Conduct interviews
Feedback / Report / Feedback
General Scheme
Pause after initial interviews to compile findings and evaluate process & interview questions

## Slide 5: Some Program Notes
Each interviewee receives an information packet providing:
  An introduction to the program
  A brief, historical summary of the PDP
  A summary of the Board’s reasoning for rejecting recommendations
  A list of question to be asked
Interviewees are advised that,
  with their permission, interviews are recorded so notes can be verified but then the recording is destroyed
  additional questions may be added depending upon the responses
Interviewees are afforded the opportunity to review and amend the meeting notes before reports are written
There are several feedback loops incorporated into the program to verify findings and conclusions

## Slide 6: Status
PDP | Information Packets | Invitation Sent | Interviews | Synthesis
Registration Data Phase I | completed | completed | completed | completed
Registration Data Phase II | completed | completed | completed | completed
Subsequent Procedures | completed | completed |  | 
13 Interviews:
2 Board Members,
2 PDP Chairs,
6 WG Members,
3 ICANN Staff Members
Compiled findings
Drafted preliminary recommendations

## Slide 7: Schedule
June 17 – July 18: complete interviews
July 21 – Aug 1: report compilation
Aug 4 – Aug 22: feedback from participants
Aug 22 – Sep 5: final report
Sep 18: discuss at GNSO Council meeting

## Slide 8: Discussion Points in Draft Report
The findings recognise value in Board collaboration as part of the PDP but balance that against preserving the bottom-up nature of the process
The Board liaison role in that process is still not certain and will vary across PDPs; which duties should be required?
Rejections might occur because the PDP objectives (e.g., reaching consensus) differ from the Board objectives (e.g., compliance with the Bylaws, its fiduciary duty).
The PDP team and Board often operate with different sets of information, e.g.,
  implementation, operation & cost details
  staff reports, GAC & ALAC inputs
  legal advice
Managing the responsibilities and roles of the GAC and ALAC both in the PDP and in giving advice to the Board
The efficacy of the representative vs the open PDP models

## Slide 9: Thank You