**Proposed work plan – priority 2 items and phase 1 remaining issues**

*13 February 2019*

| **Date** | **What** | **Topic** |
| --- | --- | --- |
| 18 February 2020 | Legal Committee Meeting | * Consider EPDP Team input & finalize priority 2 questions for submission to legal counsel   [**Feasibility of unique contacts to have a uniform anonymized email address**](https://docs.google.com/document/d/1meyuNRsq4sMOI6pefJk4jZevaKUsTkVf8_XyW1tRaiA/edit)(priority 2)   * EPDP Legal Committee to review legal guidance and make recommendation for next steps to EPDP Team. |
| 20 February 2020 | EPDP Team Meeting | [**Display of information of affiliated vs. accredited privacy / proxy providers**](https://docs.google.com/document/d/1izpX2C-RrfAdRgRDwBO9tQuJIBA9Xt38p1MTJgQNDGI/edit)(priority 2)   * EPDP Team to review ICANN Org feedback and consider Support Staff proposed recommendation |
| 25 February 2020 | Automation Use Cases Small Team | * Small team to further review and consider possible automation use cases (priority 1 – SSAD) |
| 27 February 2020 | EPDP Team Meeting | [**Data retention**](https://docs.google.com/document/d/1xlw1N7omlgPKjag_FnOy03NRvByol8IaJma5zNPkWaY/edit?usp=sharing)(priority 2)   * EPDP to review ICANN Org feedback and consider whether updates are needed to phase 1 data retention recommendation. * At a minimum, the EPDP Team would need to reconfirm its original recommendation, which was adopted on an interim basis, that registration data must be retained for a period of fifteen months following the life of the registration plus three months to implement the deletion, i.e., 18 months.   [**Feasibility of unique contacts to have a uniform anonymized email address**](https://docs.google.com/document/d/1meyuNRsq4sMOI6pefJk4jZevaKUsTkVf8_XyW1tRaiA/edit)(priority 2)   * Consider legal committee recommendation |
| 3 March 2020 | Legal Committee Meeting | [**City field redaction**](https://docs.google.com/document/d/1rdtRLaNm5DiWR_EPei4Oi64FaDauIXEQhnF2Lm_NxbI/edit)(priority 2)   * Legal committee to review and analyze legal advice received on this topic and recommend next steps to the EPDP Team, which could include modification of the phase 1 recommendation, maintaining phase 1 recommendation as is, and/or additional legal guidance to help inform a determination on whether or not the recommendation should be modified. |
| 7 March 2020 | ICANN67 Cancun  Full day EPDP Team meeting (8:30 – 18:30 local time) | Second / final reading:   * Feasibility of unique contacts to have a uniform anonymized email address * Data retention * City field redaction (consider legal committee recommendation)   Further consider:   * Automation Use Cases – small team recommendations * [**Potential OCTO Purpose**](https://docs.google.com/document/d/174PSGgWB-UTTcqIA-NndIVDkP6WR701tzwjDsozVRXM/edit) (awaiting ICANN Org response) * [**Accuracy and WHOIS Accuracy Reporting System**](https://docs.google.com/document/d/1pS9Pibanj-Hp6LztZpeERtxdoLsnp4y_-do0vU5VJuw/edit) (consider ICANN Org / GNSO Council correspondence) |
| 8 March 2020 | ICANN67 Cancun  Hold for Legal Committee meeting, if necessary  (17:00 – 18:30 local time) | Consider any outstanding legal committee questions / issues |
| 9 March 2020 | ICANN67 Cancun  Open House Session - Community Q & A  (10.30 – 12.00 local time) | Open house session to allow for anyone interested to ask questions about SSAD Initial Report and provide feedback to EPDP Team (note, this is not a replacement for the public comment forum – any input to be formally considered by the EPDP Team will need to be provided through the forum as well) |
| 12 March 2020 | ICANN67 Cancun  EPDP Team wrap up session  (15.15 – 16.45 local time) | * Final reading of items from 7 March session, if necessary * Confirm action items & next steps |
| 19 March 2020 | EPDP Team meeting, if necessary | * Final reading of remaining priority 2 items |
| 20 March 2020 | Publication for review by EPDP Team of proposed Initial Report addendum on priority 2 items | * Review Initial Report addendum on priority 2 items which is to be published for public comment |
| 23 March 2020 | Closing date of public comment forum on SSAD Initial Report |  |
| 24 March 2020  Note: last possible day to hold 40-day PCP on priority 2 items and incorporate into Final Report | EPDP Team Meeting | * Close out any remaining priority 2 items and confirm next steps, including publication for public comment of Initial Report addendum on priority 2 items * Overview of comments submitted on SSAD Initial Report and discuss approach for reviewing input |
| 26 March 2020 | EPDP Team Meeting | * Commence review of public comments |
| April 2020  (frequency of meetings dependent on # of comments received) | EPDP Team Meetings | * Continue review of public comments |
| 3 May 2020 | Closing date of public comment forum on Initial Report addendum on priority 2 items |  |
| May 2020  (frequency of meetings dependent on # of comments received – possibility of intense EPDP Team call week 11-15 May) | EPDP Team Meetings | * Conclude to final agreements, prepare Final Report, consensus call |
| 11 June 2020 |  | * Submit Final Report to GNSO Council (14 June = GNSO Council Motions and Docs Deadline) |