## Slide 1: EPDP Phase 2a Update to GNSO Council
24 March 2021

## Slide 2: Council Instruction
[a]t the latest 3 months after reconvening, the Chair of the EPDP Team and GNSO Council Liaison to the EPDP will report back to the GNSO Council on the status of deliberations. Based on this report, which is expected to include an update on progress made and the expected likelihood of consensus recommendations, the GNSO Council will decide on next steps, which could include providing additional time for the EPDP to finalize its recommendations or termination of the EPDP if it is clear that no progress is being made or consensus is unlikely.

## Slide 3: Background
&
Whether any updates are required to the EPDP Phase 1 recommendation on this topic (“Registrars and Registry Operators are permitted to differentiate between registrations of legal and natural persons, but are not obligated to do so“);
What guidance, if any, can be provided to Registrars and/or Registries who differentiate between registrations of legal and natural persons
Differentiation between Legal & Natural Person Data
Feasibility of unique contacts to have a uniform anonymized email address
Whether or not unique contacts to have a uniform anonymized email address is feasible, and if feasible, whether it should be a requirement.
If feasible, but not a requirement, what guidance, if any, can be provided to Contracted Parties who may want to implement uniform anonymized email addresses.
Two topics from phase 1 & 2 for further review by EPDP Team

## Slide 4: Achievements to date
Confirmation of Chair (Keith Drazek), Vice-Chair (Brian Beckham), GNSO Council Liaison (Philippe Fouquart)
Leadership Confirmation
Review of all relevant background information (e.g. legal advice, ICANN org study) and identification of clarifying questions
Review of all relevant information
Identification of proposals for possible guidance to Contracted Parties who choose to distinguish between legal and natural person data
Development of Proposals for possible Guidance
Definitions
Development of definitions in relation to feasibility of unique contacts
Legal Questions
Submission of follow up legal questions to external legal Counsel
Notes: Icons or text are editable, change/add to your preference.

## Slide 5: Remaining work items
Guidance
Agree and finalize guidance for Contracted Parties that want to distinguish between legal and natural person data
Legal
Consider responses to legal follow up questions [add expected timing of responses] and determine how this impacts views on Council assigned questions on both topics
Initial Report
Agree on responses to Council assigned questions for inclusion in the Initial Report
Consensus Designations
Determine consensus designations for proposed recommendations to be included in the Initial Report

## Slide 6: EPDP Phase 2A - Summary Timeline
Jul
Aug
Sep
Oct
2020
Mar
Feb
Jan
2021
Dec
Nov
4
1
5
6
Project Management, Workplan,
& Factsheet
1
EPDP-P2A Legal vs. Natural Deliberations
2
Construct Initial Report
4
EPDP-P2A Unique Contacts
Deliberations
3
Public Comment on Initial Report
5
Review of Public Comment & Submission of Final Report
May
2019
Jun
Apr
6
0
Council Consideration of Final Report
7
8
Public Comment during
Board Consideration
8
9
Board Consideration
9
24 Mar 2021
24 Mar
ICANN69
ICANN70
Project Start:
4 Mar 2019
3
7
Placeholder
0
1) Update to GNSO Council on probability to achieve consensus recommendations
May
Complete: 40%
Status:
Health:
Jul
Aug
Sep
Oct
Jun
ICANN71
2
Behind Schedule
24 Mar – Status to Council (1)
Nov
Dec
Jan
2021
31 Aug - FR
Target
31 May – IR
Target
Notes: As communicated to the GNSO Council at the end of January 2021

## Slide 7: Chair & Liaison Assessment & Proposed Approach
EPDP Team had a slower than anticipated start
Although it may be difficult to come to consensus on all issues, it is important that the group is allowed the time as committed to in its timeline to develop an Initial Report
There is a possibility that some additional time may be needed due to external dependency on responses to legal questions by external legal counsel
Expectation is that by 20 May GNSO Council Meeting a more specific update can be provided by Chair and Council Liaison on the likelihood of consensus recommendations