Proposed work plan – priority 2 items and phase 1 remaining issues

4 March 2020

| Date | What | Topic |
| --- | --- | --- |
| 18 February 2020 | Legal Committee Meeting | - Consider EPDP Team input & finalize priority 2 questions for submission to legal counsel Feasibility of unique contacts to have a uniform anonymized email address (priority 2) - EPDP Legal Committee to review legal guidance and make recommendation for next steps to EPDP Team. |
| 20 February 2020 | EPDP Team Meeting | Display of information of affiliated vs. accredited privacy / proxy providers (priority 2) - EPDP Team to review ICANN Org feedback and consider Support Staff proposed recommendation |
| 25 February 2020 | Automation Use Cases Small Team | - Small team to further review and consider possible automation use cases (priority 1 – SSAD) |
| 27 February 2020 | EPDP Team Meeting | Data retention (priority 2) - EPDP to review ICANN Org feedback and consider whether updates are needed to phase 1 data retention recommendation. - At a minimum, the EPDP Team would need to reconfirm its original recommendation, which was adopted on an interim basis, that registration data must be retained for a period of fifteen months following the life of the registration plus three months to implement the deletion, i.e., 18 months. |
| 3 March 2020 | Legal Committee Meeting | City field redaction (priority 2) - Legal committee to review and analyze legal advice received on this topic and recommend next steps to the EPDP Team, which could include modification of the phase 1 recommendation, maintaining phase 1 recommendation as is, and/or additional legal guidance to help inform a determination on whether or not the recommendation should be modified. |
| 5 March 2020 | EPDP Team Meeting | Feasibility of unique contacts to have a uniform anonymized email address (priority 2) - Consider legal committee recommendation City field redaction (priority 2) - Consider legal committee recommendation Potential OCTO Purpose (priority 2) - Consider org input |
| 10 March 2020 | Virtual ICANN67 Cancun EPDP Team meeting (tentative 9:00 – 11:00 local time (14:00 – 16:00 UTC) | Second / final reading: - Display of information of affiliated vs. accredited proxy / privacy providers - Data retention Automation Use Cases - Review remaining use cases (not yet reviewed by small team) Purpose 2 - Review EPDP Team feedback & updated language from Volker / Brian |
| 12 March 2020 | Virtual ICANN67 Cancun EPDP Team meeting (tentative 10:45 – 12:45 local time local time (15:45 – 17:45 UTC) | Second / final reading: - Feasibility of unique contacts to have a uniform anonymized email address - City field redaction Accuracy and WHOIS Accuracy Reporting System (consider ICANN Org / GNSO Council correspondence) |
| 17 March 21020 | EPDP Team meeting | Second / final reading: - Purpose 2 - Potential OCTO Purpose - Automation Use Cases (note, prior to the meeting groups will be asked to indicate their support or lack thereof of including use cases in Final Report – focus will be on those where there is sufficient support or indication of ability to find support) |
| 18 March 2020 | Legal Committee Meeting | - Territorial Scope - Review of B&B feedback on Legal vs. Natural follow-up and Initial Report follow-up (if applicable) |
| 19 March 2020 | EPDP Team meeting | - Final reading of remaining priority 2 items |
| 20 March 2020 | Publication for review by EPDP Team of proposed Initial Report addendum on priority 2 items | - Review Initial Report addendum on priority 2 items which is to be published for public comment |
| 23 March 2020 | Closing date of public comment forum on SSAD Initial Report |  |
| 24 March 2020 Note: last possible day to hold 40-day PCP on priority 2 items and incorporate into Final Report | EPDP Team Meeting | - Close out any remaining priority 2 items and confirm next steps, including publication for public comment of Initial Report addendum on priority 2 items - Overview of comments submitted on SSAD Initial Report and discuss approach for reviewing input |
| 26 March 2020 | EPDP Team Meeting | - Commence review of public comments |
| April 2020 (frequency of meetings dependent on # of comments received – possible F2F/high intensity meetings 29 April – 3 May) | EPDP Team Meetings | - Continue review of public comments |
| 3 May 2020 | Closing date of public comment forum on Initial Report addendum on priority 2 items |  |
| May 2020 (frequency of meetings dependent on # of comments received – possible F2F/ high intensity meetings 13-17 May) | EPDP Team Meetings | - Conclude to final agreements, prepare Final Report, consensus call |
| 11 June 2020 |  | - Submit Final Report to GNSO Council (14 June = GNSO Council Motions and Docs Deadline) |