## Slide 1
IGO/INGO Identifiers Protection
Policy Implementation
Implementation Review Team Meeting | 25 August 2016

## Slide 2: Agenda
Project
Status
Gating Items for Public Comment
Project Scope Tracking Chart Review
Protected Identifier List
Policy Language Document
Next Steps
1
2
3
4
5
6
Notes: This is a stylized agenda slide for your presentation.
To delete a box, if there are too many boxes, click the edge of the box, ensure the entire box is highlighted, then DELETE.
To update the numbers and text, click inside the circle for the numbers or in the box for the text, revise the text.

## Slide 3
2015
Dec
Oct
Sep
Nov
2016
Feb
Apr
Jan
Aug
Dec
Oct
Jun
Jul
Sep
Nov
Mar
May
ICANN 56 (B)
ICANN 57 (C)
Feb
Jan
Mar
2017
ICANN 54
Current Timeline Assumptions for Implementation
Apr
Aug
Oct
Jun
Jul
Sep
Nov
May
Dec
ICANN 59 (B)
ICANN 60 (C)
ICANN 58 (A)
ICANN 55 (A)
Drafting of Implementation Plan
Finalization of Implementation Plan with IRT
Public Comments on Draft Implementation Plan
Announcement
Policy Effective Date
Implementation by Affected Parties & ICANN
IRT Meetings

## Slide 4: Implementation Plan Status
Secure Initial Authoritative Lists of Identifiers and Required Data
  RCRC, IOC, INGO Identifiers – Complete
  INGOs Contact Data – Complete
  IGOs Identifiers – seeking ”up to two languages” from GAC
    Letter to GAC submitted on 17 June 2016
    Information expected by October 2016
Define List Update Process
  INGO – in development working with UNDESA
  IGO/IOC/RCRC – defined in draft CP
Develop Systems and Processes
  Full name reservation process
    Use current system/process
  90-day claims system in design
    ICANN staff to review/evaluate proposal from the current TMCH system vendor

## Slide 5: Required Deliverables for Key Milestones
Implementation Plan Release for Public Comment (target August 2016)
  INGO: 90-day claims solution defined
  List update process defined
  Draft consensus policy language document
  Sample Protected Identifier Lists page on IRT wiki page
Announce Policy Effective Date (target February 2017)
  Protected Identifier List posted
    IGO list: up to two language from GAC
    IOC List
    RCRC List
    INGO List: ECOSOC
  INGO: MoU with UNDESA for ECOSOC list & Contact list
  Claims system designed and ready to implement
  Final Consensus Policy Language
Policy Effective Date (6 months from announcement)
  The Policy Language posted
  Claims system operational

## Slide 6: Policy Recommendation Scope Tracking
Org | Board Resolution (A): “Not Inconsistent” Implementation Authorized | Board Res (B) GNSO differing GAC Implementation Not Authorized
RCRC | Reserve Full Names; Top & Second levels In UN6 languages with Exception Procedure: Red Cross, Red Crescent, Red Crystal, Red Lion & Sun | 189 National RC Societies: permanent protection & 90-days claims? Full name only vs acronyms also for ICRC and IFRC, etc?
IOC | Reserve Full Names; Top & Second levels in UN6+German, Greek, & Korean with Exception Procedure: OLYMPIC and OLYMPIAD | N/A
IGO | Reserve Full Names; Top & Second levels Up to 2 languages with Exception Procedure: GAC List | Protection for Acronyms? 90-days claims? Access to Curative rights (PDP)?
INGO | Reserve Full Names; Top level with Exception Procedure: ECOSOC General List English only 90-days Claims for Full Names; Second level: ECOSOC General and Special Lists English only | N/A

## Slide 7: Protected Identifiers Lists
“Protected Identifiers Lists” is currently posted on the IRT Community Wiki page. Permanent home is intended to be icann.org. For Public Comment, it may moved to icann.org
The lists are similar but different from the IOC, Red Cross, and IGO reserved names for new gTLDs on icann.org: https://www.icann.org/sites/default/files/packages/reserved-names/ReservedNames.xml
The list to be used for both Top and Second Level and Reservation and Claims.
This list is to be maintained as simple lists to be used as reference from AGB, Policy and Contacts.
Treatment of the list is specified elsewhere such as AGB, RA, etc.

## Slide 8: Draft Consensus Policy Language
Review of the Draft Consensus Policy Language Document

## Slide 9: Next Steps for Implementation Team
Publish Draft Consensus Policy Language for Public Comment with an announcement; 45 days, September – October 2016
MoU with USDESA
Request English Full Name only for ECOSOC from UNDESA
90-day claims system proposal evaluation/design
Receive two language IGO names from GAC and update the Protected Identifier List
Next scheduled Meetings
  IRT calls monthly: September 29, October 27 or as needed
  ICANN 57 Session request submitted; likely the week of the 7th November
IRT Community wiki page
https://community.icann.org/pages/viewpage.action?pageId=54694212

## Slide 10
Back up slides
Notes: Breakup your presentation, divide it into sections. This is especially useful if most of your presentation is text.

## Slide 11: IGO/INGO Identifier Lists Update Process
INGO
  List Authority: ECOSOC List – UNDESA
  Annual updated list provided by UNDESA to ICANN
  ICANN provides the updated list to Claims system
IGO
  List Authority: GAC
  GAC may provide updated list “time to time” per policy recommendation
  ICANN updates the reservation list upon receipt
RCRC
  No policy recommendation language received regarding updates
  Follow the same process as IGO
IOC
  No policy recommendation language received regarding updates
  Follow the same process as IGO

## Slide 12: Engage with ICANN
Reach me at:
Email: dennis.chang@icann.org
Website: icann.org
Thank You and Questions
gplus.to/icann
weibo.com/ICANNorg
flickr.com/photos/icann
slideshare.net/icannpresentations
twitter.com/icann
facebook.com/icannorg
linkedin.com/company/icann
youtube.com/user/icannnews
Notes: You can adjust the email/web address to whichever email or web address is best suited to your presentation. This should be your final slide.

## Slide 13: Project Background
This Policy Development Process (PDP) was initiated to develop policy recommendations for the provision of protection for identifiers of certain International Governmental Organizations (IGOs) and International Non-Governmental Organizations (INGOs), including the Red Cross/Red Crescent Movement (RCRC) and the International Olympic Committee (IOC).
The PDP Working Group completed its work in November 2013 and its consensus recommendations were approved by the GNSO Council. In April 2014, the ICANN Board adopted those of the PDP recommendations that were “not inconsistent” with GAC advice received on the topic, and requested more time to consider the remaining, inconsistent recommendations.
The adopted recommendations relate to protection at the top and second level for specific RCRC, IOC and IGO names (with an Exception Procedure to be designed for the affected organizations), and a 90-days Claims Notification process at the second level for certain INGO acronyms.

## Slide 14: Implementation Review Team
This Policy Implementation Review Team session at ICANN56 is open to public
Community is invited to learn about this policy implementation project, ask questions and provide inputs to the Implementation Team
Implementation Project Team consists of ICANN Staff and Implementation Review Team (IRT)
Implementation Review Team is made up of community volunteers:
  Jean-François Vanden Eynde – Nameshield Registry Brian Cimbolic – PIR Crystal Ondo - Donuts David Maher – PIR
  Petter Rindforth - Fenix Legal KB
  Lori Schulman - INTA Mike Rodenbaugh - Rodenbaugh Law Jim Bikoff - SGR LLP Holly Lance - SGR LLP

## Slide 15: INGOs Identifiers Labels and Contact Data
Reminder of Policy Recommendation Scope (PDP Final Report §3.4)
Scope 1 Identifiers: ECOSOC List (General Consultative Status) (Language: English only)
Scope 2 Identifiers: ECOSOC List (Special Consultative Status) (Language: English only)
Implementation
Labels will be listed in an authoritative document (TBD) to serve implementation of protection at the Top Level (ineligible for delegation) and at the 2nd Level (90-day Claims)
Implementation Challenges/Progress
ICANN Staff established contact with UNDESA CSO Net (ECOSOC list manager)
We received the ECOSOC list with contract information in Excel format
Drafted a MoU detailing the use of the data and update; currently in IPT review
Next steps: Conference with USDESA to discuss the agreement to be documented then follow up with the MoU

## Slide 16: INGOs Identifiers: ECOSOC List
Total 3582 identifiers on the list
144 are of General Consultative status
Information received include:
  Official name
  English name if official name isn’t in English
  Address
  Phone
  Email
  Fax
  URL
  Consultative status

## Slide 17: INGOs Identifiers implementation plan
Sample “Official Names” from the list
  AARP
  AVSI Foundation
  ANAJA (L'Eternel a répondu)
  Association for Progressive Communications (APC)
  CIVICUS – World Alliance for Citizen Participation
  Institut international pour la paix, la justice et les droits de l'Homme- IIPJDH
  International Association “Znanie”
Implementation plan:
  Use the names exactly as provided by UNDESA
  No ICANN evaluation, adjustment or normalization
  Treat ECOSOC list received as the authoritative list

## Slide 18: IGO Scope 1 Identifiers Labels
Reminder of Policy Recommendation Scope (PDP Final Report §3.3)
Scope 1 Indentifiers: GAC List (22 March 2013) - Full Name (Up to two languages)
Protected at the top-level (ineligible for delegation)
Protected at the 2nd level (reservation with exception procedure)
Implementation
Labels will be listed on the Reserved Names List (2nd level) https://www.icann.org/resources/pages/reserved-2013-07-08-en
This list will also serve as reference for future application rounds (Top-level)
Implementation steps
The 22 March 2013 GAC List contains Full Names of the IGO in English only
IPT is working to gather ”up to two languages;” The 2nd language is optional
Letter sent to GAC on 17 June 2016 with the request
Next steps: IPT is following up with ICANN GAC support team

## Slide 19: Why is this important?
Issues related to whether certain international organizations such as IGOs, the RCRC and the IOC should receive special protection for their names at the top level and second level in the domain name system have been raised throughout the development of the 2012 New gTLD program.
In the PDP launched by the GNSO Council, the scope of organizations was expanded to also consider International Non-Governmental Organizations (INGOs) other than the RCRC and IOC.
All these organizations perform important public interest or humanitarian work and have reported that cyber-squatting and related abuse of domain names identical or confusingly similar to their names and acronyms could significantly impact their missions and resources

## Slide 20: Current Activities on IGO/INGOs Protections
IGO/INGO Identifiers Protection Policy Implementation (GDD, IRT)
IGO/INGO Currative Rights Protection Mechanism PDP WG (GNSO)
Protection of IGO/INGO Indentifiers in All gTLDs PDP WG
20 Nov. 2013
GNSO Council Resolution
30 Apr. 2014 Board Resolution
5 June 2014 GNSO Resolution Initiation of PDP
Reconciliation of GNSO Recommendation Differing from GAC Advice (Board)
Today
This Policy Implementation Project is focused on the
“GNSO Recommendations Not Inconsistent with GAC Advice”
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.