Proposed Reconvened WG Timeline:

| 07 June | Next meeting of the Reconvened WG (possible start of consensus call) |
| --- | --- |
| 14 June | Reconvened WG meeting if required |
| 18 June | Start of Public Comment Period |
| 23-28 June | ICANN62 |
| 18 July | Close of Comment Period (30 days per Council resolution)** |
| 19 July | Reconvened WG meeting to review comments and prepare Final Report |
| 26 July | Reconvened WG meeting to review comments and prepare Final Report |
| 28 July | Close of Comment Period (40 days per standard) |
| 02 August | Reconvened WG meeting to review comments and prepare Final Report |
| 06 August | GNSO Council’s Documents and Motion deadline / Send Final Report |
| 16 August | GNSO Council meeting |

** Note that the Council resolution that kicked off this effort mentions a (30) day public comment period.  However, the standard is (40) days. With ICANN62 occurring we will be challenged by hosting a (30) day period given ICANN meeting and travel and US holiday.  In the past, shorter comment periods during meetings has been met with resistance.  Conducting a (40) day period only leaves the WG with one standard scheduled meeting before the Council’s Motion and Documents deadline.

The WG will need to make a decision as to how long the forum should last and depending on the decision, the WG may have to adjust its meeting schedule (perhaps meet twice in one week) to fully review comments and prepare the final report by 06 August.

Confirmed Members for Consensus Call:

- Thomas Rickert

- Stephane Hankins

- Lucie Laplante

- Chuck Gomes

- Crystal Ondo

- David Maher

- Giacomo Mazzone

- Heather Forrest

- Christopher Lamb

- Osvaldo Novoa

- Jorge Cancio

- Greg Shatan

- James Bikoff

- Mike Rodenbaugh

***those that did not respond will be demoted to Observer