## Recommendations_Issues Mapping
| PRINCIPLES | Policy and Implementation Satisfactory? | Implementation Satisfactory | Policy adjustments/clarifications | Implementation Guidance | Other Considerations
A | New generic top-level domains (gTLDs) must be introduced in an orderly, timely and predictable way. | Yes | Issues: changes introduced late in the process, everything took longer than expected, digital archery/application prioritization issues, name collision, changes to the registry agreement, etc. | N/A | See Below
B | Some new generic top-level domains should be internationalised domain names (IDNs) subject to the approval of IDNs being available in the root. | Yes | Implementation still obstructed by lack of Universal Acceptance; | N/A | See Below
C | The reasons for introducing new top-level domains include that there is demand from potential applicants for new top-level domains in both ASCII and IDN formats. In addition the introduction of new top-level domain application process has the potential to promote competition in the provision of registry services, to add to consumer choice, market differentiation and geographical and service-provider diversity. | Yes (Does this rationale still exist or is this something that needs to be tested) | Question: Did implementation accomplish or discourage these goals? | N/A | See Below | - The Implementation Advisory Group for Competiion, Consumer Trust, and Consumer Choice (IAG-CCT) concluded its work in Sept 2014, with the Board to take up the matter in 2015
D | A set of technical criteria must be used for assessing a new gTLD registry applicant to minimise the risk of harming the operational stability, security and global interoperability of the Internet. | Yes | Question: Were the rights technical criteria assessed to accomplish this policy goal? | N/A | See Below
E | A set of capability criteria for a new gTLD registry applicant must be used to provide an assurance that an applicant has the capability to meets its obligations under the terms of ICANN's registry agreement. | Yes | Same as above. | N/A | See Below
F | A set of operational criteria must be set out in contractual conditions in the registry agreement to ensure compliance with ICANN policies. | Yes | Same as above. | N/A | See Below
G | The string evaluation process must not infringe the applicant's freedom of expression rights that are protected under internationally recognized principles of law. | Yes | Here is where GAC objections, community processes, required reservation of strings, etc. accomplished this goal or not. | N/A | See Below
| Recommendations | Policy and Implementation Satisfactory? | Implementation Satisfactory? -JJN Notes | Policy adjustments/clarifications | Implementation Guidance | Other Considerations
1 | ICANN must implement a process that allows the introduction of new top-level domains. | No Yes | No | N/A | N/A | Overarching concerns that the overall policy development may want to take into account: Considerations - How can staff ensure that processes, policies, and procedures be finalized and not change after launch? - How can additional participation in the implementation and execution phases of the program be encouraged from the community (e.g., ALAC, GAC)? GAC Advice was supposed to be against individual applications, not classes of applications. Could have mandated verification of registrants in highly regulated industries. - Is the AGB the right implementation of the GNSO recommendations? Is it too cumbersome, confusing, divisible into different sections (for applicants, back end providers, historical info, etc.)? Notable Issues - Missed deadlines, inconsistent timelimes - Program changes after launch (priority draw, name collisions, PICs, etc.)
The evaluation and selection procedure for new gTLD registries should respect the principles of fairness, transparency and non-discrimination.
All applicants for a new gTLD registry should therefore be evaluated against transparent and predictable criteria, fully available to the applicants prior to the initiation of the process. Normally, therefore, no subsequent additional selection criteria should be used in the selection process.
2 | Strings must not be confusingly similar to an existing top-level domain or a Reserved Name. | No Yes | No | DG Considerations - Plurals may cause user confusion - Is string confusion less impactful in certain cases (e.g., two private us TLDs)? Identified in Board Resolution - String Similarity | DG Considerations - Were string contention mechanisms effective in resolving contention? - Were string contention results consistent and effective in preventing consumer confusion? - Can string similarity resolution methods be improved or substituted for new mechanisms, such as allowing string change, alternate string? - Is auction right mechanism of last resort? - Were results of string similarity consistent? - Should registrants, independant objector, or others have standing to file objection under string confusion?
3 | Strings must not infringe the existing legal rights of others that are recognized or enforceable under generally accepted and internationally recognized principles of law. | No Yes | No | DG Considerations - Were objections processing and outcomes consistent with the GNSO Recommendations? | See Notes | Several principles described in the recommendations were combined under objections. Should the recommendations be grouped as such? Some overall concerns include: - Prohibitively high fees to access - Lack of rules around objection consolidation - Lack of appeal mechanism - Review role, functions, and powers of Independent objector - Review objection grounds and the conditions for qualification - Outcomes perceived as inconsistent - Release of decisions perceived as inconsistent - Consider having an oversight body or mechanism over body
Examples of these legal rights that are internationally recognized include, but are not limited to, rights defined in the Paris Convention for the Protection of Industry Property (in particular trademark rights), the Universal Declaration of Human Rights (UDHR) and the International Covenant on Civil and Political Rights (ICCPR) (in particular freedom of expression rights).
4 | Strings must not cause any technical instability. | No Yes | No | DG Considerations - Were criteria adequate to prevent strings from causing technical instability? Notable Issues - Name Collisions. Identified in Board Resolution - Name collision |  | The GNSO Council, as of 28 January, came to the conclusion that policy work on the name collision issue was premature: http://gnso.icann.org/en/correspondence/robinson-to-namazi-28jan15-en.pdf
5 | Strings must not be a Reserved Word. | No Yes | No, implementation was updated by GAC advice, name collision, etc. Was not predictable, reliable, timely or orderly. | DG Considerations - Were the Reserved Names rules exhaustive and properly constructed? - How can the rules around Geographic names be improved? Update documentation requirements (i.e., Informed Consent). Better established geographic names restrictions (AMAZON, PATAGONIA). Full country names should be allowable since no other outlet currently, GAC shouldn't speak for the countries. Geographic indicators for certain products (e.g., wine, cheese) and determine whether standard should apply to 2nd level registrations - Suggested changes to string criteria (e.g., allow special characters, 2 letter TLDs, single letter TLDs, etc.)
6 | Strings must not be contrary to generally accepted legal norms relating to morality and public order that are recognized under international principles of law. | No Yes | No. |  |  | See notes related to Recommendation 3 as there were not specific issues related to Recommendation 6
Examples of such principles of law include, but are not limited to, the Universal Declaration of Human Rights (UDHR), the International Covenant on Civil and Political Rights (ICCPR), the Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW) and the International Convention on the Elimination of All Forms of Racial Discrimination, intellectual property treaties administered by the World Intellectual Property Organisation (WIPO) and the WTO Agreement on Trade-Related Aspects of Intellectual Property (TRIPS).
7 | Applicants must be able to demonstrate their technical capability to run a registry operation for the purpose that the applicant sets out. | No Yes | No (We also need to consider the issue of technical accreditations for back-end providers to make the process much more efficient, less expensive, and less redundant). | DG Considerations - Were Financial and Technical criteria designed properly to allow applicants to demonstrate their capabilities while allowing evaluators to validate their capabilities? Notable Issues - Were questions more focused on bureaucratic requirements rather than rooted in realities of running a registry? | DG Considerations - Did lack of clarity in questions increase need for clarifying questions?
8 | Applicants must be able to demonstrate their financial and organisational operational capability. | No Yes | No. In addition to the COI, there needs to be assessment of the relationshi between the criteria that was used and the true ability to run a registry. |  | DG Considerations - Was the Continued Operations Instrument the right mechanism to demonstrate finanicla capability? | Issues related to Recommendation 7 apply to Recommendation 8
9 | There must be a clear and pre-published application process using objective and measurable criteria. | No Yes | No (See Notes in Column F) |  | DG Considerations - The clarifying question process seems to have been developed on the fly and changed as the program progressed. The clarifying question process should have strict rules about what changes are allowed as certain changes may have material effects on related applications and processes. - Change request process seems to have been developed on the fly and changed as the program progressed. - How can the program better adhere to timelines and deadlines better, for staff, applicants, and providers - How can applicant management mechanisms be strengthened? Customer support should be more consistent in timing and content. - Can direct communications between applicants and GAC, providers, etc. be established?
10 | There must be a base contract provided to applicants at the beginning of the application process. | No Yes | No. In fact the base contract was amended on multiple occassions after the applications process started and in fact fter the applications were submitted. ICANN added the Unilateral Right to amend a number of provisions made early applicnts sign agreements that contained place holders for future resolutions (eg., GAC Advice, reserved strings, name collision, etc.) Policy was the right policy...implementation was sub-optimal. This is in addition to Column F. |  | Considerations - Did the base contract properly balance market certainty and flexibility to accommodate a rapidly changing market place? - Does a single base contract make sense for all types of registries? - Should the RA be available in multiple languages? - Clarify rules to prevent potential abuse of Spec 13 by generic TLDs - Establish requirements for selling and maintaing premium-names. - Are public interest commitments (PICs) sufficient to protect the interests of Internet users? - Premium Pricing - Rules are insufficiently clear and thus open to interpretation and abuse. Greater certainty required on what is permissible around the designation of names as premium, where they are trademarked terms, and on limits as to numbers - Does Article 7.7a of the registry agreement replicate the one size fits all issues present in other aspects of the RA and risk impacting certain types of parties inequitably?
11 | [Replaced with Recommendation 20 and Implementation Guideline P and inserted into Term of Reference 3 Allocation Methods section] | N/A
12 | Dispute resolution and challenge processes must be established prior to the start of the process. | No Yes | No. Changes to processes, rules, and uncertain criteria plauged the resolution and challenge processes. This is in addition to the Accountability mechanisms, lack of appeals, etc. |  | DG Considerations - Accountability mechanisms were abused. A quick-look process may help fend off abuse. Ombudsman processes and timelines need to be formalized. - Lack of redress options? - Spurious activities aimed at community applicants. Supporters were contacted, misled. Subsequent round applicants will find it harder to gain support. In addition, the CRITERIA for prevailing in these challenges needs to be better defined BEFORE the start of the APPLICATION period.
13 | Applications must initially be assessed in rounds until the scale of demand is clear. | No (JJN - This is one of the policies that needs to be assessed again) |  | DG Considerations - Has scale of demand been made clear that the concept of rounds be eschewed in favor of another mechanism? Notable Issues - Does the concept of rounds affect demand and consumer behavior - Are there factors beyond demand that should impact the type of application acceptance mechanism?
14 | The initial registry agreement term must be of a commercially reasonable length. | Yes | Yes
15 | There must be renewal expectancy. | Yes | Yes
16 | Registries must apply existing Consensus Policies and adopt new Consensus Policies as they are approved. | Yes | Yes
17 | A clear compliance and sanctions process must be set out in the base contract which could lead to contract termination. | Yes | This should be assessed with the community to see if this was implemented in a clear and concise, predictable manner.
18 | If an applicant offers an IDN service, then ICANN's IDN guidelines must be followed. | Yes |  | DG Considerations - Did the implementation for IDNs not take into proper account the findings from the IDN WG?
19 | Registries must use only ICANN accredited registrars in registering domain names and may not discriminate among such accredited registrars. | No (This is another policy that must be re-analyzed given current market conditions) | No. Development and implementation of Code of Conduct, Spec 13, etc. was not predictable and criteria is still unclear on enforcement. Also unclear what problems we are trying to solve and whether provisions are addressing those issues. | DG Considerations - Are economic studies still relevant? Is the Code of Conduct still relevant? What are the interests we are trying to promote and/or protect against? Can they be accomplished in other ways? |  | GNSO Council resolution acknowledging that Specification 13 is inconsistent with Recommendation 19: http://gnso.icann.org/en/council/resolutions#201405 Identified in Board Resolution - Registry agreement terms
20 | An application will be rejected if an expert panel determines that there is substantial opposition to it from a significant portion of the community to which the string may be explicitly or implicitly targeted. | No |  |  |  | See notes related to Recommendation 3 as there were not specific issues related to Recommendation 20
| IMPLEMENTATION GUIDELINES | Policy and Implementation Satisfactory? | Implementation Satisfactory? | Policy adjustments/clarifications | Implementation Guidance | Other Considerations
IG A | The application process will provide a pre-defined roadmap for applicants that encourages the submission of applications for new top-level domains. | No Yes | No (See Column F) |  | DG Considerations - Can the application process take advantage of economies of scale and accreditation programs? For instance, could an accreditation program be created for back-end operators, escrow providers, etc.? Would accreditation programs change how the application questions are asked? - Review backgroung check process from an effectiveness perspective as well as from a privacy standpoint. - How can systems used to support the New gTLD Program be made more robust and user friendly? Systems include TAS, Digital Archery, Centralized Zone Data Service) - Is the nondiscriminatory treatment as it applies to registries (see Section 3 of ICANN ByLaws) integrated into the program appropriately? - Is ICANN's conflict of interest framework effective and is it enforced appropriately?
IG B | Application fees will be designed to ensure that adequate resources exist to cover the total cost to administer the new gTLD process. | No Yes | No. Need to analyze ICANN methodology for "cost recovery" and what expenses were included. Litigation reserve was also extremely excessive? |  | DG Considerations - How can payment processing be improved? Can invoices be issued? Can signed agreements be supported?
Application fees may differ for applicants.
IG C | ICANN will provide frequent communications with applicants and the public including comment forums. | Yes | See Column F | N/A | Need to analyze the types of communicationn and customer support. Was it too one sided? Were applicant implementation knowledge base answers easily findable? Was information freely available? Was there an efficient way for customer concerns to be addressed? Were the webinars sufficient?
IG D | A first come first served processing schedule within the application round will be implemented and will continue for an ongoing process, if necessary. | No (Not sure if this was followed at all). Is policy still relevant? |  |  | DG Considerations - No application queuing methodology developed beforehand. Was queuing process actually followed? Many applications were processed quicker with lower priority than with higher priority numbers.
Applications will be time and date stamped on receipt.
IG E | The application submission date will be at least four months after the issue of the Request for Proposal and ICANN will promote the opening of the application round. | Yes |  | N/A | This may have been good for the last round? But do we need 4 months again? Shorter? Longer? Rolling process?
IG F* | If there is contention for strings, applicants may: | Yes (This needs to be analyzed in my opinion) Are these still relevant?) | Need to look at priority process and whether it led to efficient resolution? | N/A | N/A
i) resolve contention between them within a pre-established timeframe
ii) if there is no mutual agreement, a claim to support a community by one party will be a reason to award priority to that application. If there is no such claim, and no mutual agreement a process will be put in place to enable efficient resolution of contention and;
iii) the ICANN Board may be used to make a final decision, using advice from staff and expert panels.
IG H* | Where an applicant lays any claim that the TLD is intended to support a particular community such as a sponsored TLD, or any other TLD intended for a specified community, that claim will be taken on trust with the following exceptions: | No Yes |  | DG Considerations - Was the overall approach related to communities contrary to the recommendations? Identified in Board Resolution - Community considerations | DG Considerations - How can the Community Priority Evaluation (CPE) be improved? - Is CPE susceptible to gaming? - Is the panel rendering consistent outcomes? - How can the issue of CPE rules and/or guidelines for evaluators being developed after publication of the AGB be prevented? - Was the concern of gaming gamed such that the rules may have eliminated legitimate community-based applicants? - NEED TO LOOK AT CLAIMS ABOUT THE EVALUATORS AND EVLUATION PROCESS AND LENGTH OF TIME IT TOOK TO START AND RESOLVE CPE.
(i) the claim relates to a string that is also subject to another application and the claim to support a community is being used to gain priority for the application; and
(ii) a formal objection process is initiated.
Under these exceptions, Staff Evaluators will devise criteria and procedures to investigate the claim.
Under exception (ii), an expert panel will apply the process, guidelines, and definitions set forth in IG P.
IG H | External dispute providers will give decisions on objections. | Yes |  | N/A | N/A
IG I | An applicant granted a TLD string must use it within a fixed timeframe which will be specified in the application process. | No |  |  | DG Considerations - Was adequate time allowed for rollout of TLD? Review of when recurring fees are due to ICANN, such as after in root zone and available to mkt.
IG J | The base contract should balance market certainty and flexibility for ICANN to accommodate a rapidly changing market place. | Yes |  | N/A | N/A
IG K | ICANN should take a consistent approach to the establishment of registry fees. | Yes |  | N/A | N/A
IG L | The use of personal data must be limited to the purpose for which it is collected. | Yes |  | N/A | N/A
IG M | ICANN may establish a capacity building and support mechanism aiming at facilitating effective communication on important and technical Internet governance functions in a way that no longer requires all participants in the conversation to be able to read and write English. | Yes |  | N/A | N/A
IG N | ICANN may put in place a fee reduction scheme for gTLD applicants from economies classified by the UN as least developed. | No Yes | No. I think we are saying that the policy was good, but that our implementation was poor. But I may be interpreting wrong. | Identified in Board Resolution - Applicant support program | DG Considerations - Review why there was limited usage of the Applicant Support Program process. Did the measures intended to prevent gaming of the mechanism end up discouraging possible applicants? Were processes changed after the final AGB was released? Was there adequate outreach for the Applicant Support Program? - Was there an overall lack of outreach for the new gTLD program in Developing Countries? - Would a round dedicated to applicants from Developing Countries further participation from those regions? - What level of ownership does staff have over implementation guidelines? - Should unsuccessful applications for support be protected in subsequent rounds to prevent them being dragged into auctions by more resource-endowed applicants? If so, how should such protections be provided.
IG O | ICANN may put in place systems that could provide information about the gTLD process in major languages other than English, for example, in the six working languages of the United Nations. | SOMETHING HAPPENED HERE. IG O IS FINE THE WAY IT IS HERE. IG P SHOULD BE SEPARATED OUT AND MADE CLEAR THAT THIS NEEDS TO BE ANALYZED (BOTH THE POLICY AND IMPLEMENTATION BASED ON THE CPE AND OBJECTION PROCESS) |  | N/A | N/A
IG P* | The following process, definitions and guidelines refer to Recommendation 20. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| Process |  |  | N/A | N/A
|  |  |  | N/A | N/A
| Opposition must be objection based. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| Determination will be made by a dispute resolution panel constituted for the purpose. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| The objector must provide verifiable evidence that it is an established institution of the community (perhaps like the RSTEP pool of panelists from which a small panel would be constituted for each objection). |  |  | N/A | N/A
|  |  |  | N/A | N/A
| Guidelines |  |  | N/A | N/A
|  |  |  | N/A | N/A
| The task of the panel is the determination of substantial opposition. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| a) substantial – in determining substantial the panel will assess the following: signification portion, community, explicitly targeting, implicitly targeting, established institution, formal existence, detriment |  |  | N/A | N/A
|  |  |  | N/A | N/A
| b) significant portion – in determining significant portion the panel will assess the balance between the level of objection submitted by one or more established institutions and the level of support provided in the application from one or more established institutions. The panel will assess significance proportionate to the explicit or implicit targeting. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| c) community – community should be interpreted broadly and will include, for example, an economic sector, a cultural community, or a linguistic community. It may be a closely related community which believes it is impacted. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| d) explicitly targeting – explicitly targeting means there is a description of the intended use of the TLD in the application. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| e) implicitly targeting – implicitly targeting means that the objector makes an assumption of targeting or that the objector believes there may be confusion by users over its intended use. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| f) established institution – an institution that has been in formal existence for at least 5 years. In exceptional cases, standing may be granted to an institution that has been in existence for fewer than 5 years. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| Exceptional circumstances include but are not limited to a re-organization, merger or an inherently younger community. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| The following ICANN organizations are defined as established institutions: GAC, ALAC, GNSO, ccNSO, ASO. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| g) formal existence – formal existence may be demonstrated by appropriate public registration, public historical evidence, validation by a government, intergovernmental organization, international treaty organization or similar. |  |  | N/A | N/A
|  |  |  | N/A | N/A
| h) detriment – the objector must provide sufficient evidence to allow the panel to determine that there would be a likelihood of detriment to the rights or legitimate interests of the community or to users more widely. |  |  | N/A | N/A
IG Q | ICANN staff will provide an automatic reply to all those who submit public comments that will explain the objection procedure. | Yes |  | N/A | N/A
IG R | Once formal objections or disputes are accepted for review there will be a cooling off period to allow parties to resolve the dispute or objection before review by the panel is initiated. | Yes - We may want to re-analyze this to see whether the cooling off period actually achieved anything? |  | N/A | N/A

## Potential New Policy Work
High Level Topic | Notable Issues | Notes
Review of Rights Protection Mechanisms (at the 2nd level) | Efforts should be coordinated - perhaps consider providing list of issues for the Rights Protection Mechanisms issue report request. As such, list not provided here. | - Public comment open on a staff Rights Protection Mechanisms Review: https://www.icann.org/public-comments/rpm-review-2015-02-02-en. Report touches on Trademark Clearinghouse, Sunrise Period, Trademark Claims Service, Uniform Rapid Suspension, and Post-Delegation Dispute Resolution Procedures - Request for a Preliminary Issue report on the "current state of all rights protection mechanisms (RPMs) implemented for both existing and new gTLDs, including but not limited to the UDRP and the URS..." This request has been postponed until October 2015 allows for a more adequate time period to collect data. Identified in Board Resolution - Rights protections at the second level
Should different application tracks for different TLD types (e.g., closed, open, community restricted, brand, single registrant/registry, closed generic, etc.) be considered? | - Does the one-size-fits-all application and review process hamper innovation? Things than can be considered include allowing for different application process, requirements, fees, contractual requirement etc. - Should closed (in the sense of 3rd party registrations available or not) TLDs be allowed, in particular for generics? - Should limits on the number of applications by one applicant/group be considered? - Should the application fee amounts be made variable based on the application track or other variable mechanism? Should fees be reduced for identical applications? | Identified in Board Resolution - Special case considerations
Should the registrar to registry relationship become more standardized and regulated? | - Establish response time requirements for registrar to registry accreditation requests - Create an unified accreditation process similar to something like the Automated Registrar Onboarding System (AROS) - Standardize RRA agreements - Clarify the requirement of non-discriminatory access to registry services. Sunrise notice requirement expanded to availability of complete accreditation documentation and agreements at the time of the sunrise notice to allow timely accreditation. More transparency in contracting (NDAs, RRA, side letters, etc.). Ry requirements to disclose all promotional programs offered to registrars. Requirement for provision of RAA in English non-binding reference copy .
Identified in Board Resolution - Public interest guidance
Identified in Board Resolution - IGO/INGO Protections
Include elements from staff paper
Include elements from Board paper