## Current Timetable
Description Tasks | Final Issue Report | Final Issue Report | Task Number | Priority No | Start Date | Finish Date | Days to complete
| Cross Reference | Page No |  | ( By start date ) |  |  | Days Allotted
Draft requests for constituencies |  |  | 1 |  | 2016-09-02 | 2016-10-12 | 28
Seek Input from SO / AC |  |  | 2 |  | 2016-10-13 | 2016-12-02 | 35
Integrate Input from All the Following : |  |  | 3 |  | 2016-12-05 | 2017-01-20 | 28
Reserve Names | 4.3.1 |  | 4 |  | 2016-08-15 | 2017-02-10 | 120
Registrant Protections | 4.3.2 |  | 5 |  | 2016-08-29 | 2016-12-07 | 70
TLD Rollout | 4.3.6 |  | 6 |  | 2016-09-12 | 2016-11-04 | 40
IGO / NGO Procedures | 4.3.10 |  | 7 |  | 2016-10-03 | 2016-11-29 | 40
Closed Generics | 4.3.11 |  | 8 |  | 2016-10-03 | 2017-01-19 | 70
Contractual Compliance | 4.3.4. |  | 9 |  | 2016-10-17 | 2016-12-13 | 40
Global Public Interest | 4.3.9 |  | 10 |  | 2016-11-01 | 2017-02-17 | 70
Consider Preliminary Input: |  |  | 11 |  | 2016-11-01 | 2017-02-17 | 70
2 nd Level RPM's | 4.3.7 |  | 12 |  | 2016-09-02 | 2017-03-02 | 101
Liaise with RPMs |  |  | 13 |  | 2016-09-02 | 2016-09-16 | 70
Consider Preliminary Input: |  |  | 14 |  | 2016-11-01 | 2017-02-03 | 70
Registrar Non Discrimination | 4.3.5. |  | 15 |  | 2016-11-01 | 2017-01-20 | 50
Consider Preliminary Input: |  |  | 16 |  | 2016-11-01 | 2017-01-20 | 50
Registry / Registrar | 4.3.8 |  | 17 |  | 2016-11-01 | 2017-01-20 | 50
Consider Preliminary Input: |  |  | 18 |  | 2016-11-01 | 2017-01-20 | 50
Base Registry Agreement | 4.3.2. |  | 19 |  | 2017-01-16 | 2017-04-28 | 120
Consider Preliminary Input: |  |  | 18 |  | 2017-01-16 | 2017-04-28 | 120