## Sheet1
| Start Date | End Date
Overall WT 3
Objections | 2016-09-27 | 2017-01-31
Look at all the objections that were filed, how they turned out, | 2016-09-27 | 2016-12-15
Role of Independent Objector | 2016-12-01 | 2017-01-31
Consider preliminary inputs from CCT-RT. Conclude in Phase 2. | TBD | TBD
New gTLD Applicant Freedom of Expression | 2017-01-15 | 2017-02-28
Communuty Applications (Community Priority Evaluations) | 2017-02-28 | 2017-04-01
Consider preliminary inputs from CCT-RT. Conclude in Phase 2. | TBD | TBD
String Similarity (Evaluations) | 2017-03-21 | 2017-04-28 | `
Develop list of string similarity outcomes (e.g., plurals). Include auctions, | 2017-03-21 | 2017-04-28
Consider preliminary inputs from CCT-RT. Conclude in Phase 2. | TBD | TBD
Accountability Mechanisms | April 4, 207 | 2017-04-28
*Draft Request for Constituency Comment* | TBD | TBD
*Seek Input From SO/AC/SG/Cs* | TBD | TBD
*Integrate Input from SO/AC/SG/Cs* | TBD | 2017-04-28
* Deferred in order to co-ordinate with other WTs and Full Group at request of chairs