PPSAI – Updated Work Plan

21 October 2014
	DATE
	EVENT
	TOPIC/ACTION
	WHO

	7 Oct 2014
	WG Meeting
	Continue deliberations on Category A Main Issues
	WG

	10 Oct 2014
	WG F2F Facilitated Session
	Discuss selected high-priority topics (Transfer, Relay, Reveal)
	WG

	15 Oct 2014
	WG F2F Meeting – ICANN51 in LA
	Provide status update to ICANN community


	WG

	28 Oct 2014
	WG Meeting
	Review outcome of 10 Oct Facilitated Session; complete discussion on Relay; continue deliberations on Reveal
	WG

	4 Nov 2014
	WG Meeting
	Agree on preliminary conclusions for Category F Reveal; commence deliberations on Category G Termination
	WG

	11 Nov 2014
	WG Meeting
	Discussion with LEA/DPA; continue deliberations on Category G Termination 
	WG

	18 Nov 2014
	WG Meeting
	Discussion with LEA/DPA; agree on preliminary conclusions for Category G Termination
	WG

	25 Nov 2014
	WG Meeting
	Review all preliminary conclusions A-G
	WG

	2 Dec 2014
	WG Meeting
	Review all preliminary conclusions A-G
	WG

	9 Dec 2014
	WG Meeting
	Review all preliminary conclusions A-G
	WG

	16 Dec 2014
	WG Meeting (if needed)
	
	WG

	19 Dec 2014
	
	Circulate draft Initial Report
	Staff

	6 Jan 2015
	WG Meeting
	Review draft Initial Report 
	WG

	13 Jan 2015
	WG Meeting
	Agree on draft Initial Report
	WG

	19 Jan 2015
	Document Deadline for ICANN 52
	Publish Initial Report for public comment
	Staff

	20 Jan 2015
	Posting of Initial Report
	Initial public comment period opens
	Staff

	12 Feb 2015
	WG F2F Meeting – ICANN52 in Marrakech
	Presentation of Initial Report to community for feedback
	WG

	14 Mar 2015
	End of Public Comment Period
	Public comment forum closes
	Staff

	17 Mar 2015
	WG Meeting
	Commence review of public comments received (note that WG meetings may resume before this date if the Chairs determine that sufficient comments have been received to allow for WG discussion)
	WG

	24 Mar 2015
	WG Meeting
	Continue review of public comments received
	WG

	31 Mar 2015
	WG Meeting
	Continue review of public comments received
	WG

	7 Apr 2015
	WG Meeting
	Finalize review of public comments received
	WG

	10 Apr 2015
	
	Circulate draft Final Report (taking into account relevant public comments received and WG input)
	Staff

	14 Apr 2015
	WG Meeting
	Review draft Final Report
	WG

	21 Apr 2015
	WG Meeting
	Review draft Final Report
	WG

	28 Apr 2015
	WG Meeting
	Conclude review of and finalize Consensus Call for Final Report
	WG/Chairs

	15 May 2015
	
	Submit Final Report to GNSO Council
	Chairs/Staff/Council Liaison

	June 2015
	ICANN53
	
	


