PPSAI – Proposed Work Plan

14 February 2014
	Target Date
	What
	Deliverable / Topic for Discussion
	Who

	4 Feb 2014 
	WG Meeting
	Review draft work plan

Review latest grouping of charter questions
	WG

	11 Feb 2014
	WG Meeting
	Finalize initial work plan & grouping of charter questions
Review proposed agenda & desired outcomes of Singapore face-to-face meeting 
	WG

	18 Feb 2014
	WG Meeting
	Approve initial work plan
Review status of GNSO Whois Privacy/Proxy Studies

Commence deliberations on Category I Question 2
	WG

	25 Feb 2014 
	WG Meeting 
	Agree on preliminary conclusions on Category I Question 2

	WG

	28 Feb 2014
	Deadline for SG/C/SO/AC Input

Deadline EWG Survey
	Staff to review information received and collate information per charter / sub-questions for WG review and consideration.
	Staff

	4 March 2014 
	WG Meeting
	Review information obtained by staff in relation to terms and conditions of P/P services affiliated with 2013 RAA accredited registrars


	WG

	11 March 2014
	WG Meeting
	Finalize review of information obtained by staff in relation to terms and conditions of P/P services affiliated with 2013 RAA accredited registrars

Identify any additional research / data gathering that needs to be undertaken in relation to the charter questions

Review and update Work Plan, as necessary
	WG

	18 March 2014
	WG Meeting
	Commence deliberations on Category II Maintenance

	WG

	26 March 2014
	WG F2F Meeting – ICANN meeting in Singapore
	Provide status update to ICANN community
Agenda: TBC
	WG

	8 April 2014
	WG Meeting
	Continue deliberations on Category II Maintenance
	WG

	15 April 2014
	WG Meeting
	Continue deliberations on Category II Maintenance
	WG

	22 April 2014
	WG Meeting
	Agree on preliminary conclusions for Category II Maintenance
	WG

	29 April 2014
	WG Meeting
	Commence deliberations on Category III Registration 
	WG

	6 May 2014
	WG Meeting
	Continue deliberations on Category III Registration
	WG

	13 May 2014
	WG Meeting
	Continue deliberations on Category III Registration
	WG

	20 May 2014
	WG Meeting
	Agree on preliminary conclusions for Category III Registration
	WG

	27 May 2014
	WG Meeting
	Commence deliberations on Category IV Contact 
	WG

	3 June 2014
	WG Meeting
	Continue deliberations on Category IV Contact
	WG

	10 June 2014
	WG Meeting
	Continue deliberations on Category IV Contact
	WG

	17 June 2014
	WG meeting
	Agree on preliminary conclusions for Category IV Contact
	WG

	25 June 2014
	WG F2F Meeting – ICANN meeting in London
	Provide status update to ICANN community

Agenda: TBC
	WG

	8 July 2014
	WG Meeting
	Review & update work plan, as necessary

Commence deliberations on Category V Relay
	WG

	15 July 2014
	WG Meeting
	Continue deliberations on Category V Relay
	WG

	22 July 2014
	WG Meeting
	Continue deliberations on Category V Relay
	WG

	29 July 2014
	WG Meeting
	Agree on preliminary conclusions for Category V Relay
	WG

	5 August 2014
	WG Meeting
	Commence deliberations on Category VI Reveal
	WG

	12 August 2014
	WG Meeting
	Continue deliberations on Category VI Reveal
	WG

	19 August 2014
	WG Meeting
	Continue deliberations on Category VI Reveal
	WG

	26 August 2014
	WG Meeting
	Agree on preliminary conclusions for Category VI Reveal
	WG

	2 Sept2014
	WG Meeting
	Commence deliberations on Category VII Termination 
	WG

	9 Sept 2014
	WG Meeting 
	Continue deliberations on Category VII Termination
	WG

	16 Sept 2014
	WG Meeting 
	Continue deliberations on Category VII Termination
	WG

	23 Sept 2014
	WG Meeting
	Agree on preliminary conclusions for Category VII Termination 
	WG

	30 Sept 2014
	WG Meeting
	Commence deliberations on remainder of Category I Main Issues
	WG

	7 Oct 2014
	WG Meeting
	Continue deliberations on remainder of Category I Main Issues
	WG

	14 Oct 2014
	WG F2F Meeting – ICANN meeting in LA
	Provide status update to ICANN community

Agenda: TBC
	WG

	28 Oct 2014
	WG Meeting
	Continue deliberations on remainder of Category I Main Issues
	WG

	4 Nov 2014
	WG Meeting
	Agree on preliminary conclusions for remainder of Category I Main Issues
	WG

	11 Nov 2014
	WG Meeting
	Review preliminary conclusions on Charter questions
	WG

	18 Nov 2014
	WG Meeting
	Continue review of preliminary conclusions on Charter questions
	WG

	25 Nov 2014
	WG Meeting
	Discuss preparation of Initial Report
	WG

	2 Dec 2014
	WG Meeting
	Continue preparation of Initial Report
	WG

	9 Dec 2014
	WG Meeting
	Continue preparation of Initial Report
	WG

	16 Dec 2014
	WG Meeting
	Agree on Initial Report
	WG

	5 Jan 2015
	
	Publish Initial Report for public comment
	Staff

	6 Jan 2015
	WG Meeting
	Review Work Plan; determine if additional research or new tasks are necessary 
	WG

	13 Jan 2015
	
	
	

	20 Jan 2015
	
	
	


