PPSAI – Proposed Work Plan

5 February 2014
	Target Date
	What
	Deliverable / Topic for Discussion
	Who

	4 Feb 2014 
	WG Meeting
	Review draft work plan

Review latest grouping of charter questions
	WG

	11 Feb 2014
	WG Meeting
	Finalize initial work plan & grouping of charter questions
Review proposed agenda & desired outcomes of Singapore face-to-face meeting 
	WG

	18 Feb 2014
	WG Meeting
	Review information obtained by staff in relation to review of terms and conditions of P/P services affiliated with 2013 RAA accredited registrars

	WG

	25 Feb 2014 
	WG Meeting 
	Finalize review of information obtained by staff in relation to review of terms and conditions of P/P services affiliated with 2013 RAA accredited registrars

Identify any additional research / data gathering that needs to be undertaken in relation to the charter questions


	WG

	28 Feb 2014
	Deadline for SG/C/SO/AC Input

Deadline EWG Survey
	Staff to review information received and collate information per charter / sub-questions for WG review and consideration.
	Staff

	4 March 2014 
	WG Meeting
	Commence deliberations on Category I Main Issues
	WG

	11 March 2014
	WG Meeting
	Continue deliberations on Category I Main Issues
	WG

	18 March 2014
	WG Meeting
	Continue deliberations on Category I Main Issues
	WG

	26 March 2014
	WG F2F Meeting – ICANN meeting in Singapore
	Provide status update to ICANN community
Agenda for WG F2F Meeting: TBC

	WG

	8 April 2014
	WG Meeting
	Review & update work plan, as necessary

A  Agree on preliminary conclusions for Category I Main Issues
	WG

	15 April 2014
	WG Meeting
	Commence deliberations on Category II Maintenance
	WG

	22 April 2014
	WG Meeting
	Continue deliberations on Category II Maintenance
	WG

	29 April 2014
	WG Meeting
	Continue deliberations on Category II Maintenance 
	WG

	6 May 2014
	WG Meeting
	Agree on preliminary conclusions for Category II Maintenance
	WG

	13 May 2014
	WG Meeting
	Commence deliberations on Category III Registration
	WG

	20 May 2014
	WG Meeting
	Continue deliberations on Category III Registration
	WG

	27 May 2014
	WG Meeting
	Continue deliberations on Category III Registration 
	WG

	3 June 2014
	WG Meeting
	Agree on preliminary conclusions for Category III Registration
	WG

	10 June 2014
	WG Meeting
	Commence deliberations on Category IV Contact
	WG

	17 June 2014
	WG meeting
	Continue deliberations on Category IV Contact
	WG

	25 June 2014
	WG F2F Meeting – ICANN meeting in London
	Provide status update to ICANN community

Agenda: TBC
	WG

	8 July 2014
	WG Meeting
	Review & update work plan, as necessary

Continue deliberations on Category IV Contact
	WG

	15 July 2014
	WG Meeting
	Agree on preliminary conclusions for Category IV Contact
	WG

	22 July 2014
	WG Meeting
	Commence deliberations on Category V Relay
	WG

	29 July 2014
	WG Meeting
	Continue deliberations on Category V Relay
	WG

	5 August 2014
	WG Meeting
	Continue deliberations on Category V Relay
	WG

	12 August 2014
	WG Meeting
	Agree on preliminary conclusions for Category V Relay
	WG

	19 August 2014
	WG Meeting
	Commence deliberations on Category VI Reveal
	WG

	26 August 2014
	WG Meeting
	Continue deliberations on Category VI Reveal
	WG

	2 Sept2014
	WG Meeting
	Continue deliberations on Category VI Reveal
	WG

	9 Sept 2014
	WG Meeting 
	Agree on preliminary conclusions for Category VI Reveal
	WG

	16 Sept 2014
	WG Meeting 
	Review preliminary conclusions on Charter questions
	WG

	23 Sept 2014
	WG Meeting
	Review conclusions on Charter questions

Review & update work plan, as necessary
	WG

	30 Sept 2014
	WG Meeting
	[if necessary] Commence discussions on Category VII Termination
	WG

	7 Oct 2014
	WG Meeting
	[if necessary] Continue discussions on Category VII Termination
	WG

	14 Oct 2014
	WG F2F Meeting – ICANN meeting in LA
	Provide status update to ICANN community

Agenda: TBC
	WG

	28 Oct 2014
	
	
	


