UPDATED WORK PLAN – updated 25 APRIL 2017

(Note: ** denotes the 4th rotational meeting time of 0300 UTC)

| DATE/MEETING TIME | SUBJECT | DISCUSSION TOPICS | ACTION BY: |
| --- | --- | --- | --- |
| 1 March 2017 | TMCH review | - Review TMCH Charter questions (Category 3) against STI recommendations, AGB and other Program Documentation - Review proposed meeting agendas for ICANN58 | All |
| 8 March 2017 | Pre-ICANN Meeting Week | - No meeting | Chairs & staff to confirm presentation materials for ICANN58 |
| 11-16 March 2017 | ICANN58 | For intensive 3-hour F2F session: - 1-hour discussion with Deloitte - Continue review of TMCH Charter questions (Categories 1-2 and possibly Categories 3-6) against STi recommendations, AGB, Program Documentation? - Discuss which, if any, TMCH Charter questions can be considered closed for the time being, and which require additional work and/or discussion? - Form Sub Teams to begin process of refining Sunrise & Claims Charter questions? For Open Community Session: - Brief presentation of status of TMCH review for community feedback - Invite community feedback on how to refine Sunrise & Claims Charter questions | All |
| 22 March 2017 | Post-ICANN Meeting Week | - No meeting |  |
| 29 March 2017 (90 minutes) | TMCH review Sunrise & Claims Charter questions review (Sub Team) | - Review community feedback from ICANN58 - Complete discussions from F2F session at ICANN58 | All Form Sunrise/Claims Charter Sub Teams |
| 5 April 2017 (90 minutes) | TMCH review Sunrise & Claims Charter questions review (Sub Team) | - Review Analysis Group’s Final Report | All (staff to invite Greg Rafert from Analysis Group to join the call) Sunrise/Claims Charter Sub Team meeting |
| 12 April 2017 (90 minutes) | TMCH review Sunrise & Claims Charter questions review (Sub Team) | - Review any remaining open questions from TMCH review | All Sunrise/Claims/Private Protections Sub Team meeting |
| 19 April 2017 (90 minutes?) | Sunrise/Claims scoping | NO WORKING GROUP MEETING (deadline for submitting proposals on open TMCH questions) | Sunrise/Claims Sub Team meeting |
| ** 26 April 2017 (90 minutes) | TMCH open questions discussion Sunrise & Claims scoping | - Sub Teams to present progress report to full WG - WG to discuss any proposals received on remaining open TMCH questions | All Sunrise/Claims |
| 3 May 2017 (90 minutes) | Sunrise, Claims & Private Protections scoping | - Complete discussion of TMCH open questions - Commence discussion of initial Sub Team proposals for Charter questions on Sunrise and Claims | All Sub Teams |
| 17 May 2017 (90 minutes) | Sunrise, Claims & Private Protections scoping | - Finalize Sunrise & Claims Charter questions - Agree on proposed “mini Work Plans” from the Sunrise & Claims Sub Teams - [if ready] review proposed questions from Private Protections Sub Team | All Sub Teams |
| 24 May 2017 (120 minutes) | Sunrise review | - Commence Sunrise review | All |
| ** 31 May 2017 (90 minutes) | Sunrise review | - Continue Sunrise review | All |
| 7 June 2017 (90 minutes) | Sunrise review | - Continue Sunrise review |  |
| 14 June 2017 (120 minutes) | Prep for ICANN59 | - Continue Sunrise review - Agree on community discussion points for ICANN59 and (if planned) F2F intensive session | All |
| 21 June 2017 | Pre-ICANN59 Meeting Week | - No meeting | Chairs & staff to confirm presentation materials for ICANN59 |
| 26-29 June 2017 | ICANN59 | - F2Fmeeting (complete initial Sunrise review and commence Claims review; discuss Private Protections) | All |
| 5 July 2017 | Post-ICANN Meeting Week | - No meeting |  |
| 12 July 2017 | Claims review Form Sub Team to refine Charter questions for URS | - Review feedback from ICANN59 - Continue Claims review | All |
| 19 July 2017 | Claims review | - Continue Claims review | All URS Charter Sub Team meeting |
| 26 July 2017 | Claims review/Private Protections discussion | - Continue Claims review - Discuss Private Protections | All URS Charter Sub Team meeting |
| ** 2 August 2017 | Claims review/Private Protections discussion | - Conclude initial Claims review - Continue discussion of Private Protections | All URS Charter Sub Team meeting |
| 9 August 2017 | Stock taking: TMCH and associated RPMs | - Evaluate overall progress and conclusions from TMCH, Sunrise and Claims review | All URS Charter Sub Team meeting |
| 16 August 2017 | URS Overview | - Overview presentation of URS and introduction of Charter questions | All URS Charter Sub Team meeting |
| 23 August 2017 | URS review scoping | - Discuss Sub Team proposal for refined URS Charter questions | All |
| ** 30 August 2017 | URS review scoping | - Discuss and agree on refined URS Charter questions | All |
| 6 September 2017 | URS review | - Finalize approach to URS review | All |
| 13 September 2017 | URS review | - Commence URS review | All |
| 20 September 2017 | URS review | - Continue URS review | All |
| ** 27 September 2017 | URS review | - Continue URS review | All |
| 4 October 2017 | URS review | - Continue URS review |  |
| 11 October 2017 | URS review | - Continue URS review | All |
| 18 October 2017 | URS review | - Agree on points to be raised to community at ICANN60 and (if planned) agenda for ICANN60 F2F intensive session | All |
| 25 October 2017 | Pre-ICANN60 Meeting Week | - No meeting | Chairs & staff to confirm presentation materials for ICANN60 |
| 28 Oct – 3 Nov 2017 | ICANN60 | - (possible) intensive F2F meeting (conclude initial URS review?) - Open community discussion on URS | All |
| 8 November 2017 | Post-ICANN Meeting Week | - No meeting |  |
| 15 November 2017 | URS review/General | - Review community feedback from ICANN60 - Review preliminary conclusions on URS | All |
| 22 November 2017 | Day before Thanksgiving (US holiday) | - No meeting |  |
| 29 November 2017 | Finalize Phase 1 | - Agree on Phase 1 recommendations | All |
| 6 December 2017 | Finalize Phase 1 | - Agree on Phase 1 recommendations |  |
| 13 December 2017 | Finalize Phase 1 - Staff to circulate draft Initial Report containing agreed recommendations | - Commence discussion of draft Initial Report | All; staff |
| 20 December 2017 | Finalize Phase 1 | - Continue discussion of draft Initial Report | All |
| Week of 27 December 2017 | ICANN offices closed | - No meeting |  |
| 3 January 2018 | Finalize Phase 1 | - Finalize discussion of draft Initial Report | All |
| 15 January 2018 | Finalize Phase 1 and open public comment forum - Staff to circulate proposed finalized Initial Report | - Public comment forum opens | Staff |
| 24 February 2018 | Close of public comment period | - NOTE: WG may hold meetings to review public comments received before this date - Staff to circulate (and update, as needed) Public Comment Review Tool |  |
| 28 February 2018 | Review Phase 1 Report | - Discuss public comments received on Phase 1 Report | All |
| 7 March 2018 | Pre-ICANN Meeting Week | - No meeting | Chairs & staff to confirm presentation materials for ICANN61 |
| 10-15 March 2018 | F2F at ICANN61 | - Discuss public comments received and proposed WG responses with community | All |
| 21 March 2018 | Post-ICANN Meeting Week | - No meeting |  |
| 28 March 2018 | Review Phase 1 Report | - Continue discussion of public comments received | All |
| 4 April 2018 | Review Phase 1 Report | - Continue discussion of public comments received | All |
| 11 April 2018 | Review Phase 1 Report - Staff to circulate updated report before this meeting | - Review updated recommendations based on public comments accepted by the WG | All; staff |
| 18 April 2018 | Review Phase 1 Report | - Finalize updated Phase 1 Report | All |
| 25 April 2018 | Review Phase 1 Report | - Finalize Phase 1 Report - Submit Phase 1 Report to GNSO Council | All; chairs & staff |
| CONCLUSION OF PHASE ONE – COMMENCE PHASE TWO |  |  |  |
| 2 May 2018 | UDRP overview | - Overview presentation of UDRP and Charter questions | All |
| 9 May 2018 | UDRP outreach | - Discuss outreach letter/questions to ICANN SO/AC/SG/Cs | All (Sub Team may be formed to develop initial draft letter) |
| 16 May 2018 | UDRP outreach | - Agree on outreach letter/questions | All |
| 23 May 2018 | UDRP review scoping | - Commence discussion of Charter questions | All |
| 30 May 2018 | UDRP review scoping | - Continue discussion of Charter questions | All |
| 6 June 2018 | UDRP review scoping | - Agree on discussion items with community for ICANN62 | All |
| 13 June 2018 | Pre-ICANN Meeting Week | - No meeting | Chairs & staff to confirm presentation materials for ICANN62 |
| 18-21 June 2018 | F2F at ICANN62 | - Seek community input on Charter questions to be reviewed for the UDRP | All |
| 27 June 2018 | Post-ICANN Meeting Week | - No meeting |  |
| 4 July 2018 | US holiday (4th of July) | - No meeting |  |
| 11 July 2018 | UDRP review scoping | - Review community input from ICANN62 | All |
| 18 July 2018 | UDRP review scoping | - Agree on questions to be reviewed | All |
| 25 July 2018 | UDRP review | - Commence review of UDRP | All |
| 1 August 2018 | UDRP review |  |  |
| 8 August 2018 | UDRP review |  |  |
| 15 August 2018 | UDRP review |  |  |
| 22 August 2018 | UDRP review |  |  |
| 29 August 2018 | UDRP review |  |  |
| 5 September 2018 | UDRP review |  |  |
| 12 September 2018 | UDRP review |  |  |
| 19 September 2018 | UDRP review |  |  |
| 26 September 2018 | UDRP review |  |  |
| 3 October 2018 | UDRP review |  |  |
| 10 October 2018 | Status Summary | - Agree on discussion items with community at ICANN63 | All |
| 17 October 2018 | Pre-ICANN Meeting Week | - No meeting | Chairs & staff to confirm presentation materials for ICANN63 |
| 20-26 October 2018 | F2F at ICANN63 |  |  |
| 31 October 2018 | Post-ICANN Meeting Week | - No meeting |  |
| 7 November 2018 | UDRP review | - Review feedback from ICANN63 | All |
| 14 November 2018 | UDRP review | - Conclude initial review of UDRP | All |
| 21 November 2018 | US holiday (day before Thanksgiving) | - No meeting |  |
| 28 November 2018 | UDRP conclusions | - Begin discussion of preliminary recommendations for UDRP review | All |
| 5 December 2018 | UDRP conclusions | - Continue discussions of UDRP preliminary recommendations | All |
| 12 December 2018 | UDRP conclusions | - Continue discussions of UDRP preliminary recommendations | All |
| 19 December 2018 | UDRP conclusions | - Continue discussions of UDRP preliminary recommendations | All |
| Week of 26 December 2018 | ICANN offices closed | - No meeting |  |
| 2 January 2019 | UDRP conclusions | - Continue discussions of UDRP preliminary recommendations | All |
| 9 January 2019 | Finalize UDRP conclusions | - Agree on UDRP preliminary recommendations | All |
| 16 January 2019 | Phase Two initial report - Staff to circulate partial draft Phase Two report (on the UDRP) | - Discuss draft report on the UDRP | All; staff |
| 23 January 2019 | Phase Two initial report | - Discuss draft report on the UDRP | All |
| 30 January 2019 | Phase Two initial report | - Finalize draft report on the UDRP | All |
| Week of 6 February 2019 | Open public comment forum for Phase Two (UDRP review) | - [No meeting?] | Staff |
| 13 February 2019 | Review of remaining topics | - Consider overarching and remaining general Charter questions | All |
| 20 February 2019 | Review of remaining topics | - Consider overarching and remaining general questions | All |
| 27 February 2019 | Status Summary | - Agree on discussion items for community at ICANN64 | All |
| 6 March 2019 | Pre-ICANN Meeting Week | - No meeting | Chairs & staff to confirm presentation materials for ICANN64 |
| 9-14 March 2019 | F2F at ICANN64 |  |  |
| Week of 20 March 2019 | Close of public comment forum Post-ICANN Meeting Week | - No meeting |  |
| 27 March 2019 | Review of public comments | - Discuss public comments received on UDRP report | All |
| 3 April 2019 | Review of public comments | - Discuss public comments received on UDRP report | All |
| 10 April 2019 | Review of public comments | - Discuss public comments received on UDRP report | All |
| 17 April 2019 | Finalise Phase 2 - UDRP report | - Agree on updates to UDRP recommendations | All |
| 24 April 2019 | Finalize Phase 2 - UDRP report - Staff to update UDRP report | - Agree on updates to UDRP recommendations | All/staff |
| CONCLUSION OF PHASE TWO – CONSOLIDATION PHASE BEGINS |  |  |  |
| 1 May 2019 | Overall review of all recommendations from Phase 1 & Phase 2 |  |  |
| 8 May 2019 |  |  |  |
| 15 May 2019 |  |  |  |
| 22 May 2019 |  |  |  |
| 29 May 2019 |  |  |  |
| 5 June 2019 |  |  |  |
| 12 June 2019 |  | - Agree on overall recommendations for Phases 1 & 2 | All |
| 19 June 2019 | Pre-ICANN Meeting Week | - No meeting | Chairs & staff to confirm presentation materials for ICANN65 |
| 24-27 June 2019 | F2F at ICANN65 | - Present overall recommendations to community | All |
| 3 July 2019 | Post-ICANN Meeting Week | - No meeting |  |
| 10 July 2019 | Review all proposed Phase 1 & 2 recommendations | - Review feedback from ICANN65 | All |
| 17 July 2019 | Prepare Final Report | - Review all recommendations | All |
| 24 July 2019 |  |  |  |
| 31 July 2019 |  |  |  |
| 7 August 2019 |  |  |  |
| 14 August 2019 |  |  |  |
| 21 August 2019 |  |  |  |
| 28 August 2019 |  |  |  |
| 4 September 2019 |  |  |  |
| 11 September 2019 |  |  |  |
| 18 September 2019 |  |  |  |
| 25 September 2019 |  |  |  |
| 2 October 2019 |  |  |  |
| 9 October 2019 |  |  |  |
| 16 October 2019 |  |  |  |
| 23 October 2019 |  |  |  |
| 30 October 2019 | Pre-ICANN Meeting Week | - No meeting |  |
| 2-8 November 2019 | ICANN66 |  |  |