IANA Stewardship Transition - Process Timeline

At the inaugural meeting of the IANA Stewardship Coordination Group (ICG), there was a discussion of the timeline to produce a proposal for delivery to the NTIA.  The goal remains for the transition to take place in September 2015.

The whole Internet community has a role in the development and review of the proposal, and the following timeline is provided for review and comment. It is an aggressive timeline, but includes provisions for flexibility in its targets, which should allow all communities to participate effectively. The ICG will continuously review the timeline, report on progress, and make adjustments as needed.

The IGC is well aware of the challenges presented by the entire transition planning schedule and will continue to review this timeline on.  Partial responses and late submissions will be accepted, and every effort will be made to assimilate all received information at every step of the process.

Step 0:	Request for Communities to produce proposal text

Target: 31 July 2014

The ICG is aware that most communities have already started this work using their own processes.  The ICG will publish a detailed CFP for response by all affected communities.

Step 1:	Communities' work

Target: 31 Dec 2014

Communities develop their initial responses to the CFP. Use of open and transparent processes is strongly encouraged, to allow all interested parties to continuously review progress and to provide input during development processes.

Step 2:	Strawman proposal

Target: 28 Feb 2015

The IGC will assemble the contributions from the communities, publishing a strawman proposal and a companion analysis document.  Seek review and comments from all communities, the global Internet community, IANA and NTIA.

Begin testing (Step 4) at this point, if possible, for any components of the proposal that are ready.

Step 3:	Community review

Target: 29 May 2015

Communities review the strawman proposal, Comments from IANA and NTIA are strongly desired.

Step 4:	Final proposal

Target: 30 June 2015

ICG produces the final draft proposal. Proposal is submitted to NTIA for their review, and final community review and response is requested.

Step 5:	Acceptance report

Target: 31 August 2015

Does the community have consensus on the proposal content?  Has testing shown the system is working?

The IGC will provide a final report to the community (and NTIA) on these findings.

Step 6:	NTIA approval

Deadline: 30 Sep 2015

NTIA does whatever they need to do with the proposal.  It is unknown how much time will be needed, but we should expect several months.